## Risk List
Current Task Status / Priority |  | High | Medium | Low | Total | % Of Total
Closed |  | 4 | 3 | 2 | 9 | 36%
Work In Progress |  | 2 | 0 | 1 | 3 | 12%
Behind |  | 1 | 4 | 4 | 9 | 36%
Not Started |  | 1 | 2 | 1 | 4 | 16%
Total |  | 8 | 9 | 8 | 25 | 100%
% of Total |  | 32% | 36% | 32% | 100%
ID | Issue Description | Department | Actual Status | Date | Impact | Probability | Risk score | Priority | Solution | 0.1 | 0.3 | 0.6
1 | Estimates are inaccurate | Planning | Work In Progress | 2016-10-10 | 5 | 4 | 20 | High | Team meeting and re-estimate. | Low | Medium | High
2 | Lack of management or control | Management | Closed | 2016-10-10 | 4 | 4 | 16 | High
3 | Errors in key project management processes | Management | Closed | 2016-10-10 | 4 | 3 | 12 | Medium
4 | Change management overload | Management | Not Started | 2016-10-10 | 3 | 3 | 9 | Medium
5 | Resource shortfalls | Management | Closed | 2016-10-10 | 3 | 2 | 6 | Medium |  | 5% | 13.33% | 7.5%
6 | Learning curves lead to delays and cost overrun | Management | Closed | 2016-10-10 | 4 | 4 | 16 | High
7 | Resources are inexperienced | Management | Work In Progress | 2016-10-10 | 3 | 1 | 3 | Low |  |  |  |  | Behind
8 | Team members with negative attitudes towards the project | Management | Closed | 2016-10-10 | 2 | 4 | 8 | Medium
9 | Resource turnover | Management | Closed | 2016-10-10 | 4 | 1 | 4 | Low
10 | Scope is ill defined | Requirement | Behind | 2016-11-07 | 5 | 2 | 10 | Medium
11 | Stakeholder conflict over proposed changes | Requirement | Not Started | 2016-11-07 | 3 | 1 | 3 | Low |  | 1.25% | 0% | 15%
12 | Inaccurate function priorities | Requirement | Behind | 2016-11-07 | 5 | 3 | 15 | High
13 | Change request conflicts with requirements | Requirement | Not Started | 2016-11-07 | 4 | 3 | 12 | Medium
14 | Users reject the prototype | Requirement | Closed | 2016-11-07 | 4 | 1 | 4 | Low
15 | Stakeholder conflict | Requirement | Behind | 2016-11-07 | 3 | 1 | 3 | Low |  |  |  |  | Work In Progress
16 | Project team misunderstand requirements | Requirement | Closed | 2016-11-07 | 5 | 4 | 20 | High
17 | Requirements are ambiguous | Requirement | Closed | 2016-11-07 | 5 | 5 | 25 | High
18 | Requirements are incomplete | Requirement | Behind | 2016-11-07 | 3 | 2 | 6 | Medium |  | 2.5% | 10% | 30%
19 | Users have inaccurate expectations | Requirement | Not Started | 2016-11-07 | 5 | 3 | 15 | High
20 | Delays to training impact the project | Management | Work In Progress | 2016-12-12 | 3 | 5 | 15 | High |  |  |  |  | Closed
21 | Architecture is infeasible | Architect | Behind | 2016-12-12 | 1 | 2 | 2 | Low
22 | Architecture is not fit for purpose | Architect | Behind | 2016-12-12 | 4 | 2 | 8 | Medium
23 | Design lacks flexibility | Desgin | Behind | 2017-01-02 | 4 | 1 | 4 | Low |  | 1.25% | 6.667% | 7.5%
24 | Design is not fit for purpose | Desgin | Behind | 2017-01-02 | 4 | 2 | 8 | Medium
25 | Design is infeasible | Desgin | Behind | 2017-01-02 | 1 | 5 | 5 | Low |  |  |  |  | Not Started
26
27
28

## Sheet1 (hidden)
Department
Planning
Requirement
Architect
Desgin
Code
Test
Management