## Sheet1
WEEK | ID | TASK | TYPE | PHASE | DATE ASSIGN | ESTIMATE | ACTUAL | DUE-DATE | ASSIGN TO | STATUS
1 | 1 | Team Meeting | Meeting | Kick-off | 2016-03-10 | 1 | 1 | 2016-03-10 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 2016-03-10 | 1 | 1 | 2016-03-10 | KhoiNguyen | Complete
| 3 | Team Meeting | Meeting |  | 2016-03-10 | 1 | 1 | 2016-03-10 | TaiNguyen | Complete | W1 | 87 | Complete
| 4 | Team Meeting | Meeting |  | 2016-03-10 | 1 | 1 | 2016-03-10 | HienNguyen | Complete | W2 | 85 | Pending
| 5 | Team Meeting | Meeting |  | 2016-03-10 | 1 | 1 | 2016-03-10 | XuanThaiHien | Complete | W3 | 122 | Not implemented
| 6 | Team Meeting | Meeting |  | 2016-03-10 | 1 | 1 | 2016-03-10 | MinhDoan | Complete | W4 | 113
| 7 | Develop Team rule & policy | Kick-off |  | 2016-03-10 | 2 | 2 | 2016-04-10 | HaiTran | Complete | W5 | 202
| 8 | Develop Team rule & policy | Kick-off |  | 2016-03-10 | 4 | 2 | 2016-04-10 | HienNguyen | Complete | W6 | 123
| 9 | Develop Team rule & policy | Kick-off |  | 2016-03-10 | 1 | 2 | 2016-04-10 | KhoiNguyen | Complete | W7 | 127
| 10 | Develop Team rule & policy | Kick-off |  | 2016-03-10 | 3 | 2 | 2016-04-10 | MinhDoan | Complete | W8 | 135
| 11 | Develop Team rule & policy | Kick-off |  | 2016-03-10 | 3 | 2 | 2016-04-10 | TaiNguyen | Complete | W9 | 175
| 12 | Develop Team rule & policy | Kick-off |  | 2016-03-10 | 2 | 2 | 2016-04-10 | XuanThaiHien | Complete | W10 | 180
| 13 | Review Team rule & policy | Kick-off |  | 2016-05-10 | 3 | 4 | 2016-05-10 | HaiTran | Complete | W11 | 164
| 14 | Review Team rule & policy | Kick-off |  | 2016-05-10 | 3 | 4 | 2016-05-10 | HienNguyen | Complete | W12 | 171
| 15 | Review Team rule & policy | Kick-off |  | 2016-05-10 | 3 | 4 | 2016-05-10 | KhoiNguyen | Complete | W13 | 203
| 16 | Review Team rule & policy | Kick-off |  | 2016-05-10 | 3 | 4 | 2016-05-10 | MinhDoan | Complete | W14 | 181.5
| 17 | Review Team rule & policy | Kick-off |  | 2016-05-10 | 3 | 4 | 2016-05-10 | TaiNguyen | Complete | W15 | 90
| 18 | Review Team rule & policy | Kick-off |  | 2016-05-10 | 3 | 4 | 2016-05-10 | XuanThaiHien | Complete | W16 | 219
| 19 | Mentor Meeting | Meeting |  | 2016-06-10 | 2 | 3 | 2016-06-10 | HaiTran | Complete | W17 | 201
| 20 | Mentor Meeting | Meeting |  | 2016-06-10 | 2 | 3 | 2016-06-10 | HienNguyen | Complete | W18 | Holiday
| 21 | Mentor Meeting | Meeting |  | 2016-06-10 | 2 | 3 | 2016-06-10 | KhoiNguyen | Complete | W19 | 212
| 22 | Mentor Meeting | Meeting |  | 2016-06-10 | 2 | 3 | 2016-06-10 | MinhDoan | Complete | W20 | 189
| 23 | Mentor Meeting | Meeting |  | 2016-06-10 | 2 | 3 | 2016-06-10 | TaiNguyen | Complete
| 24 | Mentor Meeting | Meeting |  | 2016-06-10 | 2 | 3 | 2016-06-10 | XuanThaiHien | Complete
| 25 | Develop Team Charter | Kick-off |  | 2016-06-10 | 4 | 3 | 2016-07-10 | HienNguyen | Complete
| 26 | Develop Project Charter | Kick-off |  | 2016-06-10 | 3 | 2 | 2016-07-10 | HienNguyen | Complete
| 27 | Define Process Decision | Kick-off |  | 2016-07-10 | 2 | 3 | 2016-08-10 | HaiTran | Complete
| 28 | Define Process Decision | Kick-off |  | 2016-07-10 | 3 | 4 | 2016-08-10 | HienNguyen | Complete
| 29 | Define Process Decision | Kick-off |  | 2016-07-10 | 2 | 5 | 2016-08-10 | KhoiNguyen | Complete
| 30 | Define Process Decision | Kick-off |  | 2016-07-10 | 4 | 3 | 2016-08-10 | MinhDoan | Complete
| 31 | Define Process Decision | Kick-off |  | 2016-07-10 | 3 | 5 | 2016-08-10 | TaiNguyen | Complete
| 32 | Define Process Decision | Kick-off |  | 2016-07-10 | 3 | 2 | 2016-08-10 | XuanThaiHien | Complete
2 | 1 | Team Meeting | Meeting |  | 2016-10-10 | 1 | 2 | 2016-10-10 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 2016-10-10 | 1 | 2 | 2016-10-10 | HienNguyen | Complete
| 3 | Team Meeting | Meeting |  | 2016-10-10 | 1 | 2 | 2016-10-10 | KhoiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 2016-10-10 | 1 | 2 | 2016-10-10 | MinhDoan | Complete
| 5 | Team Meeting | Meeting |  | 2016-10-10 | 1 | 2 | 2016-10-10 | TaiNguyen | Complete
| 6 | Team Meeting | Meeting |  | 2016-10-10 | 1 | 2 | 2016-10-10 | XuanThaiHien | Complete
| 7 | Review Process Decision | Kick-off |  | 2016-11-10 | 2 | 5 | 2016-11-10 | HaiTran | Complete
| 8 | Review Process Decision | Kick-off |  | 2016-11-10 | 3 | 5 | 2016-11-10 | HienNguyen | Complete
| 9 | Review Process Decision | Kick-off |  | 2016-11-10 | 3 | 5 | 2016-11-10 | KhoiNguyen | Complete
| 10 | Review Process Decision | Kick-off |  | 2016-11-10 | 2 | 5 | 2016-11-10 | MinhDoan | Complete
| 11 | Review Process Decision | Kick-off |  | 2016-11-10 | 3 | 5 | 2016-11-10 | TaiNguyen | Complete
| 12 | Review Process Decision | Kick-off |  | 2016-11-10 | 3 | 5 | 2016-11-10 | XuanThaiHien | Complete
| 13 | Mentor Meeting | Meeting |  | 2016-12-10 | 1 | 2 | 2016-12-10 | HaiTran | Complete
| 14 | Mentor Meeting | Meeting |  | 2016-12-10 | 1 | 2 | 2016-12-10 | HienNguyen | Complete
| 15 | Mentor Meeting | Meeting |  | 2016-12-10 | 1 | 2 | 2016-12-10 | KhoiNguyen | Complete
| 16 | Mentor Meeting | Meeting |  | 2016-12-10 | 1 | 2 | 2016-12-10 | MinhDoan | Complete
| 17 | Mentor Meeting | Meeting |  | 2016-12-10 | 1 | 2 | 2016-12-10 | TaiNguyen | Complete
| 18 | Mentor Meeting | Meeting |  | 2016-12-10 | 1 | 2 | 2016-12-10 | XuanThaiHien | Complete
| 19 | Define SWOT technology | Kick-off |  | 2016-12-10 | 3 | 2 | 13/10/2016 | KhoiNguyen | Complete
| 20 | Define SWOT Project | Kick-off |  | 2016-12-10 | 2 | 3 | 13/10/2016 | TaiNguyen | Complete
| 21 | Review SWOT technology | Kick-off |  | 13/10/2016 | 1 | 3 | 13/10/2016 | TaiNguyen | Complete
| 22 | Review SWOT Project | Kick-off |  | 13/10/2016 | 2 | 3 | 13/10/2016 | HaiTran | Complete
| 23 | Review SWOT technology | Kick-off |  | 13/10/2016 | 2 | 3 | 13/10/2016 | KhoiNguyen | Complete
| 24 | Review SWOT Project | Kick-off |  | 13/10/2016 | 1 | 3 | 13/10/2016 | TaiNguyen | Complete
| 25 | Update Project Charter | Kick-off |  | 13/10/2016 | 4 | 2 | 14/12/2016 | HienNguyen | Complete
| 26 | Define SWOT individual | Kick-off |  | 13/10/2016 | 2 | 1 | 14/10/2016 | HienNguyen | Complete
| 27 | Define SWOT individual | Kick-off |  | 13/10/2016 | 1 | 1 | 14/10/2016 | HaiTran | Complete
| 28 | Define SWOT individual | Kick-off |  | 13/10/2016 | 2 | 2 | 14/10/2016 | MinhDoan | Complete
| 29 | Define SWOT individual | Kick-off |  | 13/10/2016 | 2 | 2 | 14/10/2016 | KhoiNguyen | Complete
| 30 | Define SWOT individual | Kick-off |  | 13/10/2016 | 2 | 1 | 14/10/2016 | TaiNguyen | Complete
| 31 | Define SWOT individual | Kick-off |  | 13/10/2016 | 2 | 1 | 14/10/2016 | XuanThaiHien | Complete
| 32 | Update Process Decision | Kick-off |  | 14/10/2016 | 3 | 4 | 15/10/2016 | TaiNguyen | Complete
3 | 1 | Mentor Meeting | Meeting | Planning | 17/10/2016 | 2 | 5 | 17/10/2016 | HaiTran | Complete
| 2 | Mentor Meeting | Meeting |  | 17/10/2016 | 2 | 5 | 17/10/2016 | MinhDoan | Complete
| 3 | Mentor Meeting | Meeting |  | 17/10/2016 | 2 | 5 | 17/10/2016 | KhoiNguyen | Complete
| 4 | Mentor Meeting | Meeting |  | 17/10/2016 | 2 | 5 | 17/10/2016 | TaiNguyen | Complete
| 5 | Mentor Meeting | Meeting |  | 17/10/2016 | 2 | 5 | 17/10/2016 | XuanThaiHien | Complete
| 6 | Mentor Meeting | Meeting |  | 17/10/2016 | 2 | 5 | 17/10/2016 | TaiNguyen | Complete
| 7 | Team Meeting | Meeting |  | 18/10/2016 | 2 | 2 | 18/10/2016 | HaiTran | Complete
| 8 | Team Meeting | Meeting |  | 18/10/2016 | 2 | 2 | 18/10/2016 | MinhDoan | Complete
| 9 | Team Meeting | Meeting |  | 18/10/2016 | 2 | 2 | 18/10/2016 | KhoiNguyen | Complete
| 10 | Team Meeting | Meeting |  | 18/10/2016 | 2 | 2 | 18/10/2016 | TaiNguyen | Complete
| 11 | Team Meeting | Meeting |  | 18/10/2016 | 2 | 2 | 18/10/2016 | XuanThaiHien | Complete
| 12 | Team Meeting | Meeting |  | 18/10/2016 | 2 | 2 | 18/10/2016 | TaiNguyen | Complete
| 13 | Define effort log template | Planning |  | 18/10/2016 | 1 | 2 | 20/10/2016 | HaiTran | Complete
| 14 | Define weekly report template | Planning |  | 18/10/2016 | 1 | 2 | 20/10/2016 | HaiTran | Complete
| 3 | Define project plan template | Planning |  | 18/10/2016 | 4 | 6 | 20/10/2016 | HienNguyen | Complete
| 4 | Define configuration template | Planning |  | 18/10/2016 | 3 | 6 | 20/10/2016 | KhoiNguyen | Complete
| 5 | Define communication plan template | Planning |  | 18/10/2016 | 2 | 3 | 20/10/2016 | HienNguyen | Complete
| 6 | Define change management template | Planning |  | 18/10/2016 | 5 | 8 | 20/10/2016 | MinhDoan | Complete
| 7 | Define measurement plan template | Planning |  | 18/10/2016 | 3 | 5 | 20/10/2016 | TaiNguyen | Complete
| 8 | Define risk management plan template | Planning |  | 19/10/2016 | 3 | 4 | 20/10/2016 | XuanThaiHien | Complete
| 9 | Define WBS template | Planning |  | 19/10/2016 | 4 | 4 | 20/10/2016 | HaiTran | Complete
| 10 | Define requirement management plan template | Planning |  | 19/10/2016 | 3 | 5 | 20/10/2016 | HaiTran | Complete
| 11 | Define achitecture and design plan template | Planning |  | 19/10/2016 | 3 | 3 | 20/10/2016 | HienNguyen | Complete
| 12 | Review Project Plan Template | Planning |  | 20/10/2016 | 3 | 4 | 21/10/2016 | HaiTran | Complete
| 13 | Review Configuration Template | Planning |  | 20/10/2016 | 4 | 4 | 21/10/2016 | TaiNguyen | Complete
| 14 | Review Communication Plan Template | Planning |  | 20/10/2016 | 3 | 1 | 21/10/2016 | KhoiNguyen | Complete
| 15 | Review Change Management Template | Planning |  | 20/10/2016 | 5 | 5 | 21/10/2016 | HienNguyen | Complete
| 16 | Review Measurement Plan Template | Planning |  | 20/10/2016 | 2 | 4 | 21/10/2016 | MinhDoan | Complete
| 17 | Review Risk Management Plan Template | Planning |  | 20/10/2016 | 3 | 4 | 21/10/2016 | TaiNguyen | Complete
| 18 | Review Requirement Management Plan Template | Planning |  | 20/10/2016 | 3 | 3 | 21/10/2016 | XuanThaiHien | Complete
| 19 | Review Architecture and Design Plan Template | Planning |  | 20/10/2016 | 6 | 5 | 21/10/2016 | HaiTran | Complete
| 20 | Update Configuration Plan Tempate | Planning |  | 22/10/2016 | 2 | 2 | 22/10/2016 | KhoiNguyen | Complete
4 | 1 | Team Meeting | Meeting |  | 24/10/2016 | 3 | 3 | 24/10/2016 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 24/10/2016 | 3 | 3 | 24/10/2016 | MinhDoan | Complete
| 3 | Team Meeting | Meeting |  | 24/10/2016 | 3 | 3 | 24/10/2016 | KhoiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 24/10/2016 | 3 | 3 | 24/10/2016 | TaiNguyen | Complete
| 5 | Team Meeting | Meeting |  | 24/10/2016 | 3 | 3 | 24/10/2016 | XuanThaiHien | Complete
| 6 | Team Meeting | Meeting |  | 24/10/2016 | 3 | 3 | 24/10/2016 | TaiNguyen | Complete
| 7 | Define test plan template | Planning |  | 25/10/2016 | 6 | 8 | 27/10/2016 | XuanThaiHien | Complete
| 8 | Define vision and scope template | Planning |  | 25/10/2016 | 3 | 4 | 27/10/2016 | MinhDoan | Complete
| 9 | Define concept of operation template | Planning |  | 25/10/2016 | 3 | 5 | 27/10/2016 | KhoiNguyen | Complete
| 10 | Define SRS template | Planning |  | 25/10/2016 | 4 | 4 | 27/10/2016 | MinhDoan | Complete
| 11 | Define detail design template | Planning |  | 25/10/2016 | 3 | 5 | 27/10/2016 | TaiNguyen | Complete
| 12 | Define function testcase template | Planning |  | 25/10/2016 | 2 | 4 | 27/10/2016 | HienNguyen | Complete
| 13 | Define user acceptance testcase template | Planning |  | 25/10/2016 | 4 | 5 | 27/10/2016 | HaiTran | Complete
| 14 | Define test report template | Planning |  | 25/10/2016 | 3 | 4 | 27/10/2016 | XuanThaiHien | Complete
| 15 | Review Test Plan Template | Planning |  | 28/10/2016 | 3 | 4 | 28/10/2016 | MinhDoan | Complete
| 16 | Review Vision and Scope Template | Planning |  | 28/10/2016 | 2 | 3 | 28/10/2016 | HaiTran | Complete
| 17 | Review Concept of Operation Template | Planning |  | 28/10/2016 | 4 | 3 | 28/10/2016 | MinhDoan | Complete
| 18 | Review SRS Template | Planning |  | 28/10/2016 | 3 | 3 | 28/10/2016 | TaiNguyen | Complete
| 19 | Update Vision and Scope Template | Planning |  | 28/10/2016 | 1 | 2 | 29/10/2016 | MinhDoan | Complete
| 20 | Update Concept of Operation Template | Planning |  | 28/10/2016 | 3 | 1 | 29/10/2016 | KhoiNguyen | Complete
| 21 | Update SRS Template | Planning |  | 28/10/2016 | 2 | 2 | 29/10/2016 | HienNguyen | Complete
| 22 | Develop Work Break Down Structure | Planning |  | 28/10/2016 | 8 | 6 | 29/10/2016 | TaiNguyen | Complete
| 23 | Develop Requirement Plan | Planning |  | 28/10/2016 | 10 | 9 | 29/10/2016 | HaiTran | Complete
| 24 | Develop Implement Plan | Planning |  | 28/10/2016 | 9 | 7 | 29/10/2016 | HienNguyen | Complete
| 25 | Develop Implement Plan | Planning |  | 28/10/2016 | 8 | 5 | 29/10/2016 | KhoiNguyen | Complete
| 26 | Develop Architecture and Design Plan | Planning |  | 28/10/2016 | 14 | 11 | 29/10/2016 | HienNguyen | Complete
5 | 1 | Team Meeting | Meeting |  | 31/10/2016 | 3 | 3 | 31/10/2016 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 31/10/2016 | 2 | 3 | 31/10/2016 | HienNguyen | Complete
| 3 | Team Meeting | Meeting |  | 31/10/2016 | 3 | 3 | 31/10/2016 | TaiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 31/10/2016 | 1 | 3 | 31/10/2016 | MinhDoan | Complete
| 5 | Team Meeting | Meeting |  | 31/10/2016 | 2 | 3 | 31/10/2016 | KhoiNguyen | Complete
| 6 | Team Meeting | Meeting |  | 31/10/2016 | 2 | 3 | 31/10/2016 | XuanThaiHien | Complete
| 7 | Review Requirement Plan | Planning |  | 2016-01-11 | 5 | 2 | 2016-01-11 | TaiNguyen | Complete
| 8 | Review Requirement Plan | Planning |  | 2016-01-11 | 3 | 2 | 2016-01-11 | HaiTran | Complete
| 9 | Review Requirement Plan | Planning |  | 2016-01-11 | 5 | 2 | 2016-01-11 | XuanThaiHien | Complete
| 10 | Review Requirement Plan | Planning |  | 2016-01-11 | 4 | 2 | 2016-01-11 | MinhDoan | Complete
| 11 | Review Requirement Plan | Planning |  | 2016-01-11 | 3 | 2 | 2016-01-11 | KhoiNguyen | Complete
| 12 | Review Requirement Plan | Planning |  | 2016-01-11 | 4 | 2 | 2016-01-11 | HienNguyen | Complete
| 13 | Review Implement Plan | Planning |  | 2016-01-11 | 2 | 1 | 2016-01-11 | HaiTran | Complete
| 14 | Review Implement Plan | Planning |  | 2016-01-11 | 1 | 1 | 2016-01-11 | HienNguyen | Complete
| 15 | Review Implement Plan | Planning |  | 2016-01-11 | 2 | 1 | 2016-01-11 | TaiNguyen | Complete
| 16 | Review Implement Plan | Planning |  | 2016-01-11 | 2 | 1 | 2016-01-11 | MinhDoan | Complete
| 17 | Review Implement Plan | Planning |  | 2016-01-11 | 1 | 1 | 2016-01-11 | KhoiNguyen | Complete
| 18 | Review Implement Plan | Planning |  | 2016-01-11 | 2 | 1 | 2016-01-11 | XuanThaiHien | Complete
| 19 | Review Architecture and Design Plan | Planning |  | 2016-01-11 | 5 | 7 | 2016-01-11 | MinhDoan | Complete
| 20 | Review Architecture and Design Plan | Planning |  | 2016-01-11 | 5 | 7 | 2016-01-11 | HaiTran | Complete
| 21 | Review Architecture and Design Plan | Planning |  | 2016-01-11 | 6 | 7 | 2016-01-11 | TaiNguyen | Complete
| 22 | Review Architecture and Design Plan | Planning |  | 2016-01-11 | 5 | 7 | 2016-01-11 | KhoiNguyen | Complete
| 23 | Review Architecture and Design Plan | Planning |  | 2016-01-11 | 7 | 7 | 2016-01-11 | HienNguyen | Complete
| 24 | Review Architecture and Design Plan | Planning |  | 2016-01-11 | 6 | 7 | 2016-01-11 | XuanThaiHien | Complete
| 25 | Update Requirement Plan | Planning |  | 2016-02-11 | 4 | 5 | 2016-02-11 | HaiTran | Complete
| 26 | Update Implement Plan | Planning |  | 2016-02-11 | 3 | 2 | 2016-02-11 | KhoiNguyen | Complete
| 27 | Update Architecture and Design Plan | Planning |  | 2016-02-11 | 4 | 6 | 2016-02-11 | HaiTran | Complete
| 28 | Develop Configuration Plan | Planning |  | 2016-03-11 | 8 | 11 | 2016-05-11 | KhoiNguyen | Complete
| 29 | Develop Test Plan | Planning |  | 2016-03-11 | 9 | 12 | 2016-05-11 | XuanThaiHien | Complete
| 30 | Develop Software Development Process | Planning |  | 2016-03-11 | 6 | 9 | 2016-05-11 | TaiNguyen | Complete
| 31 | Develop Schedule | Planning |  | 2016-03-11 | 8 | 6 | 2016-05-11 | HienNguyen | Complete
| 32 | Develop Estimation | Planning |  | 2016-03-11 | 6 | 8 | 2016-04-11 | HaiTran | Complete
| 33 | Develop Training Plan | Planning |  | 2016-03-11 | 3 | 4 | 2016-05-11 | TaiNguyen | Complete
| 34 | Develop Master Plan | Planning |  | 2016-03-11 | 2 | 3 | 2016-04-11 | HienNguyen | Complete
| 35 | Gather Question List | Planning |  | 2016-03-11 | 2 | 2 | 2016-04-11 | MinhDoan | Complete
| 36 | Review Configuration Plan | Planning |  | 2016-04-11 | 3 | 5 | 2016-05-11 | HienNguyen | Complete
| 37 | Review Test Plan | Planning |  | 2016-04-11 | 4 | 3 | 2016-05-11 | MinhDoan | Complete
| 38 | Review Software Development Process | Planning |  | 2016-04-11 | 4 | 4 | 2016-05-11 | HaiTran | Complete
| 39 | Review Software Development Process | Planning |  | 2016-04-11 | 3 | 4 | 2016-05-11 | HienNguyen | Complete
| 40 | Review Software Development Process | Planning |  | 2016-04-11 | 5 | 4 | 2016-05-11 | KhoiNguyen | Complete
| 41 | Review Software Development Process | Planning |  | 2016-04-11 | 4 | 4 | 2016-05-11 | TaiNguyen | Complete
| 42 | Review Software Development Process | Planning |  | 2016-04-11 | 3 | 4 | 2016-05-11 | XuanThaiHien | Complete
| 43 | Review Software Development Process | Planning |  | 2016-04-11 | 3 | 4 | 2016-05-11 | MinhDoan | Complete
| 44 | Review Schedule | Planning |  | 2016-04-11 | 3 | 2 | 2016-05-11 | HaiTran | Complete
| 45 | Review Schedule | Planning |  | 2016-04-11 | 1 | 2 | 2016-05-11 | HienNguyen | Complete
| 46 | Review Schedule | Planning |  | 2016-04-11 | 2 | 2 | 2016-05-11 | KhoiNguyen | Complete
| 47 | Review Schedule | Planning |  | 2016-04-11 | 2 | 2 | 2016-05-11 | TaiNguyen | Complete
| 48 | Review Schedule | Planning |  | 2016-04-11 | 1 | 2 | 2016-05-11 | XuanThaiHien | Complete
| 49 | Review Schedule | Planning |  | 2016-04-11 | 1 | 2 | 2016-05-11 | MinhDoan | Complete
| 50 | Review Training Plan | Planning |  | 2016-04-11 | 2 | 2 | 2016-05-11 | HaiTran | Complete
| 51 | Review Training Plan | Planning |  | 2016-04-11 | 1 | 2 | 2016-05-11 | MinhDoan | Complete
| 52 | Review Training Plan | Planning |  | 2016-04-11 | 1 | 2 | 2016-05-11 | KhoiNguyen | Complete
| 53 | Review Training Plan | Planning |  | 2016-04-11 | 1 | 2 | 2016-05-11 | TaiNguyen | Complete
| 54 | Review Training Plan | Planning |  | 2016-04-11 | 2 | 2 | 2016-05-11 | XuanThaiHien | Complete
| 55 | Review Training Plan | Planning |  | 2016-04-11 | 1 | 2 | 2016-05-11 | HienNguyen | Complete
6 | 1 | Team Meeting | Meeting |  | 2016-07-11 | 2 | 2 | 2016-07-11 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 2016-07-11 | 3 | 2 | 2016-07-11 | MinhDoan | Complete
| 3 | Team Meeting | Meeting |  | 2016-07-11 | 1 | 2 | 2016-07-11 | KhoiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 2016-07-11 | 3 | 2 | 2016-07-11 | TaiNguyen | Complete
| 5 | Team Meeting | Meeting |  | 2016-07-11 | 2 | 2 | 2016-07-11 | XuanThaiHien | Complete
| 6 | Team Meeting | Meeting |  | 2016-07-11 | 3 | 2 | 2016-07-11 | HienNguyen | Complete
| 7 | Mentor Meeting | Meeting |  | 2016-08-11 | 2 | 3 | 2016-08-11 | HaiTran | Complete
| 8 | Mentor Meeting | Meeting |  | 2016-08-11 | 3 | 3 | 2016-08-11 | MinhDoan | Complete
| 9 | Mentor Meeting | Meeting |  | 2016-08-11 | 2 | 3 | 2016-08-11 | KhoiNguyen | Complete
| 10 | Mentor Meeting | Meeting |  | 2016-08-11 | 3 | 3 | 2016-08-11 | TaiNguyen | Complete
| 11 | Mentor Meeting | Meeting |  | 2016-08-11 | 3 | 3 | 2016-08-11 | XuanThaiHien | Complete
| 12 | Mentor Meeting | Meeting |  | 2016-08-11 | 2 | 3 | 2016-08-11 | HienNguyen | Complete
| 13 | Training Technical | Training |  | 2016-08-11 |  | 2 | 2016-08-11 | HaiTran | Complete
| 14 | Training Technical | Training |  | 2016-08-11 |  | 2 | 2016-08-11 | MinhDoan | Complete
| 15 | Training Technical | Training |  | 2016-08-11 |  | 2 | 2016-08-11 | KhoiNguyen | Complete
| 16 | Training Technical | Training |  | 2016-08-11 |  | 2 | 2016-08-11 | TaiNguyen | Complete
| 17 | Training Technical | Training |  | 2016-08-11 |  | 2 | 2016-08-11 | XuanThaiHien | Complete
| 18 | Training Technical | Training |  | 2016-08-11 |  | 2 | 2016-08-11 | HienNguyen | Complete
| 19 | Update Software Development Process | Planning |  | 2016-08-11 | 3 | 2 | 2016-08-11 | HaiTran | Complete
| 20 | Update Schedule | Planning |  | 2016-08-11 | 3 | 2 | 2016-08-11 | HienNguyen | Complete
| 21 | Update Training Plan | Planning |  | 2016-08-11 | 2 | 1 | 2016-08-11 | TaiNguyen | Complete
| 22 | Develop Change Management Plan | Planning |  | 2016-08-11 | 10 | 14 | 2016-11-11 | MinhDoan | Complete
| 23 | Develop Risk Management Plan | Planning |  | 2016-08-11 | 16 | 15 | 2016-11-11 | XuanThaiHien | Complete
| 24 | Develop Measurement plan | Planning |  | 2016-08-11 | 4 | 5 | 2016-11-11 | TaiNguyen | Complete
| 25 | Review Change Management Plan | Planning |  | 2016-12-11 | 3 | 3 | 2016-12-11 | HaiTran | Complete
| 26 | Review Change Management Plan | Planning |  | 2016-12-11 | 2 | 3 | 2016-12-11 | MinhDoan | Complete
| 27 | Review Change Management Plan | Planning |  | 2016-12-11 | 3 | 3 | 2016-12-11 | KhoiNguyen | Complete
| 28 | Review Change Management Plan | Planning |  | 2016-12-11 | 4 | 3 | 2016-12-11 | TaiNguyen | Complete
| 29 | Review Change Management Plan | Planning |  | 2016-12-11 | 4 | 3 | 2016-12-11 | XuanThaiHien | Complete
| 30 | Review Change Management Plan | Planning |  | 2016-12-11 | 3 | 3 | 2016-12-11 | HienNguyen | Complete
| 31 | Review Risk Management Plan | Planning |  | 2016-12-11 | 3 | 2 | 2016-12-11 | HaiTran | Complete
| 32 | Review Risk Management Plan | Planning |  | 2016-12-11 | 3 | 2 | 2016-12-11 | MinhDoan | Complete
| 33 | Review Risk Management Plan | Planning |  | 2016-12-11 | 4 | 2 | 2016-12-11 | KhoiNguyen | Complete
| 34 | Review Risk Management Plan | Planning |  | 2016-12-11 | 2 | 2 | 2016-12-11 | TaiNguyen | Complete
| 35 | Review Risk Management Plan | Planning |  | 2016-12-11 | 3 | 2 | 2016-12-11 | XuanThaiHien | Complete
| 36 | Review Risk Management Plan | Planning |  | 2016-12-11 | 2 | 2 | 2016-12-11 | HienNguyen | Complete
| 37 | Review Measurement Plan | Planning |  | 2016-12-11 | 1 | 2 | 2016-12-11 | HaiTran | Complete
| 38 | Review Measurement Plan | Planning |  | 2016-12-11 | 2 | 2 | 2016-12-11 | MinhDoan | Complete
| 39 | Review Measurement Plan | Planning |  | 2016-12-11 | 2 | 2 | 2016-12-11 | KhoiNguyen | Complete
| 40 | Review Measurement Plan | Planning |  | 2016-12-11 | 3 | 2 | 2016-12-11 | TaiNguyen | Complete
| 41 | Review Measurement Plan | Planning |  | 2016-12-11 | 2 | 2 | 2016-12-11 | XuanThaiHien | Complete
| 42 | Review Measurement Plan | Planning |  | 2016-12-11 | 3 | 2 | 2016-12-11 | HienNguyen | Complete
7 | 1 | Team Meeting | Meeting |  | 14/11/2016 |  | 3 | 14/11/2016 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 14/11/2016 |  | 3 | 14/11/2016 | MinhDoan | Complete
| 3 | Team Meeting | Meeting |  | 14/11/2016 |  | 3 | 14/11/2016 | KhoiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 14/11/2016 |  | 3 | 14/11/2016 | TaiNguyen | Complete
| 5 | Team Meeting | Meeting |  | 14/11/2016 |  | 3 | 14/11/2016 | XuanThaiHien | Complete
| 6 | Team Meeting | Meeting |  | 14/11/2016 |  | 3 | 14/11/2016 | HienNguyen | Complete
| 7 | Training Technical | Training |  | 15/11/2016 | 2 | 2 | 15/11/2016 | HaiTran | Complete
| 8 | Training Technical | Training |  | 15/11/2016 | 2 | 2 | 15/11/2016 | MinhDoan | Complete
| 9 | Training Technical | Training |  | 15/11/2016 | 2 | 2 | 15/11/2016 | KhoiNguyen | Complete
| 10 | Training Technical | Training |  | 15/11/2016 | 2 | 2 | 15/11/2016 | TaiNguyen | Complete
| 11 | Training Technical | Training |  | 15/11/2016 | 2 | 2 | 15/11/2016 | XuanThaiHien | Complete
| 12 | Training Technical | Training |  | 15/11/2016 | 2 | 2 | 15/11/2016 | HienNguyen | Complete
| 13 | Update Change Management Plan | Planning |  | 16/11/2016 | 7 | 5 | 17/11/2016 | XuanThaiHien | Complete
| 14 | Update Change Management Plan | Planning |  | 16/11/2016 | 8 | 7 | 17/11/2016 | MinhDoan | Complete
| 15 | Update Risk Management Plan | Planning |  | 16/11/2016 | 6 | 8 | 17/11/2016 | HienNguyen | Complete
| 16 | Update Risk Management Plan | Planning |  | 16/11/2016 | 5 | 6 | 17/11/2016 | KhoiNguyen | Complete
| 17 | Update Measurement Plan | Planning |  | 16/11/2016 | 5 | 4 | 17/11/2016 | HaiTran | Complete
| 18 | Update Measurement Plan | Planning |  | 16/11/2016 | 6 | 4 | 17/11/2016 | TaiNguyen | Complete
| 19 | Presenstation | Planning |  | 17/11/2016 | 2 | 3 | 17/11/2016 | HaiTran | Complete
| 20 | Presenstation | Planning |  | 17/11/2016 | 2 | 3 | 17/11/2016 | HienNguyen | Complete
| 21 | Presenstation | Planning |  | 17/11/2016 | 2 | 3 | 17/11/2016 | KhoiNguyen | Complete
| 22 | Presenstation | Planning |  | 17/11/2016 | 2 | 3 | 17/11/2016 | MinhDoan | Complete
| 23 | Presenstation | Planning |  | 17/11/2016 | 2 | 3 | 17/11/2016 | TaiNguyen | Complete
| 24 | Presenstation | Planning |  | 17/11/2016 | 2 | 3 | 17/11/2016 | XuanThaiHien | Complete
| 25 | Modify Requirement Plan | Planning |  | 18/11/2016 | 4 | 5 | 19/11/2016 | HaiTran | Complete
| 26 | Modify Architecture and design plan | Planning |  | 18/11/2016 | 3 | 6 | 19/11/2016 | HienNguyen | Complete
| 27 | Modify Risk Management plan | Planning |  | 18/11/2016 | 4 | 6 | 19/11/2016 | MinhDoan | Complete
| 28 | Modify Change Management plan | Planning |  | 18/11/2016 | 3 | 5 | 19/11/2016 | TaiNguyen | Complete
| 29 | Modify Configuration Plan | Planning |  | 18/11/2016 | 5 | 7 | 19/11/2016 | KhoiNguyen | Complete
| 30 | Modify Test plan | Planning |  | 18/11/2016 | 5 | 3 | 19/11/2016 | XuanThaiHien | Complete
| 31 | Update document structure | Planning |  | 18/11/2016 | 3 | 3 | 19/11/2016 | KhoiNguyen | Complete
| 32 | Update configuration process | Planning |  | 18/11/2016 | 3 | 1 | 19/11/2016 | KhoiNguyen | Complete
| 33 | Update development process | Planning |  | 18/11/2016 | 3 | 2 | 19/11/2016 | TaiNguyen | Complete
| 34 | Update measurement and control process | Planning |  | 18/11/2016 | 2 | 2 | 19/11/2016 | TaiNguyen | Complete
| 35 | Update change management process | Planning |  | 18/11/2016 | 2 | 1 | 19/11/2016 | XuanThaiHien | Complete
| 36 | Update document structure | Planning |  | 18/11/2016 | 2 | 2 | 19/11/2016 | HaiTran | Complete
| 37 | Update schedule | Planning |  | 18/11/2016 | 3 | 2 | 19/11/2016 | HaiTran | Complete
8 | 1 | Team Meeting | Meeting | Requirement | 21/11/2016 | 2 | 3 | 21/11/2016 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 21/11/2016 | 2 | 3 | 21/11/2016 | HienNguyen | Complete
| 3 | Team Meeting | Meeting |  | 21/11/2016 | 2 | 3 | 21/11/2016 | TaiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 21/11/2016 | 2 | 3 | 21/11/2016 | MinhDoan | Complete
| 5 | Team Meeting | Meeting |  | 21/11/2016 | 2 | 3 | 21/11/2016 | XuanThaiHien | Complete
| 6 | Team Meeting | Meeting |  | 21/11/2016 | 2 | 3 | 21/11/2016 | KhoiNguyen | Complete
| 7 | Mentor Meeting | Meeting |  | 21/11/2016 | 3 | 3 | 21/11/2016 | HaiTran | Complete
| 8 | Mentor Meeting | Meeting |  | 21/11/2016 | 3 | 3 | 21/11/2016 | HienNguyen | Complete
| 9 | Mentor Meeting | Meeting |  | 21/11/2016 | 3 | 3 | 21/11/2016 | TaiNguyen | Complete
| 10 | Mentor Meeting | Meeting |  | 21/11/2016 | 3 | 3 | 21/11/2016 | MinhDoan | Complete
| 11 | Mentor Meeting | Meeting |  | 21/11/2016 | 3 | 3 | 21/11/2016 | XuanThaiHien | Complete
| 12 | Mentor Meeting | Meeting |  | 21/11/2016 | 3 | 3 | 21/11/2016 | KhoiNguyen | Complete
| 13 | Training Technical | Training |  | 22/11/2016 | 2 | 2 | 22/11/2016 | HaiTran | Complete
| 14 | Training Technical | Training |  | 22/11/2016 | 2 | 2 | 22/11/2016 | HienNguyen | Complete
| 15 | Training Technical | Training |  | 22/11/2016 | 2 | 2 | 22/11/2016 | TaiNguyen | Complete
| 16 | Training Technical | Training |  | 22/11/2016 | 2 | 2 | 22/11/2016 | MinhDoan | Complete
| 17 | Training Technical | Training |  | 22/11/2016 | 2 | 2 | 22/11/2016 | XuanThaiHien | Complete
| 18 | Training Technical | Training |  | 22/11/2016 | 2 | 2 | 22/11/2016 | KhoiNguyen | Complete
| 19 | Customer Meeting | Meeting |  | 22/11/2016 | 3 | 2 | 22/11/2016 | HaiTran | Complete
| 20 | Customer Meeting | Meeting |  | 22/11/2016 | 3 | 2 | 22/11/2016 | HienNguyen | Complete
| 21 | Customer Meeting | Meeting |  | 22/11/2016 | 3 | 2 | 22/11/2016 | TaiNguyen | Complete
| 22 | Customer Meeting | Meeting |  | 22/11/2016 | 3 | 2 | 22/11/2016 | MinhDoan | Complete
| 23 | Customer Meeting | Meeting |  | 22/11/2016 | 3 | 2 | 22/11/2016 | XuanThaiHien | Complete
| 24 | Customer Meeting | Meeting |  | 22/11/2016 | 3 | 2 | 22/11/2016 | KhoiNguyen | Complete
| 25 | Analyze Requirement | Requirement |  | 22/11/2016 | 8 | 7 | 23/11/2016 | HienNguyen | Complete
| 26 | Analyze Requirement | Requirement |  | 22/11/2016 | 6 | 6 | 23/11/2016 | HaiTran | Complete
| 27 | Analyze Requirement | Requirement |  | 22/11/2016 | 9 | 7 | 23/11/2016 | MinhDoan | Complete
| 28 | Analyze Requirement | Requirement |  | 22/11/2016 | 8 | 6 | 23/11/2016 | KhoiNguyen | Complete
| 29 | Analyze Requirement | Requirement |  | 22/11/2016 | 7 | 7 | 23/11/2016 | TaiNguyen | Complete
| 30 | Analyze Requirement | Requirement |  | 22/11/2016 | 5 | 7 | 23/11/2016 | XuanThaiHien | Complete
| 31 | Develop Business workflow "Manage Accounts" function | Requirement |  | 22/11/2016 | 4 | 5 | 23/11/2016 | HaiTran | Pending
| 32 | Develop Business workflow "Manage News" function | Requirement |  | 24/11/2016 | 6 | 4 | 25/11/2016 | HaiTran | Pending
| 33 | Develop Business workflow "Manage Banners" function | Requirement |  | 24/11/2016 | 3 | 2 | 25/11/2016 | TaiNguyen | Pending
| 34 | Develop Business workflow "Manage Pop-ups" function | Requirement |  | 24/11/2016 | 3 | 1 | 25/11/2016 | TaiNguyen | Pending
| 35 | Develop Business workflow "Manage FAQ" function | Requirement |  | 24/11/2016 | 5 | 6 | 25/11/2016 | KhoiNguyen | Pending
| 36 | Develop Business workflow "Manage Homepage" function | Requirement |  | 24/11/2016 | 6 | 8 | 26/11/2016 | HienNguyen | Pending
| 37 | Develop Business workflow "Manage Languages" function | Requirement |  | 24/11/2016 | 1 | 1 | 26/11/2016 | KhoiNguyen | Pending
| 38 | Develop Business workflow "Manage Categories " function | Requirement |  | 24/11/2016 | 6 | 5 | 26/11/2016 | MinhDoan | Pending
| 39 | Develop Business workflow "Manage Examination " function | Requirement |  | 24/11/2016 | 5 | 3 | 26/11/2016 | XuanThaiHien | Pending
9 | 1 | Team Meeting | Meeting |  | 28/11/2016 |  | 3 | 28/11/2016 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 28/11/2016 |  | 3 | 28/11/2016 | HienNguyen | Complete
| 3 | Team Meeting | Meeting |  | 28/11/2016 |  | 3 | 28/11/2016 | MinhDoan | Complete
| 4 | Team Meeting | Meeting |  | 28/11/2016 |  | 3 | 28/11/2016 | TaiNguyen | Complete
| 5 | Team Meeting | Meeting |  | 28/11/2016 |  | 3 | 28/11/2016 | KhoiNguyen | Complete
| 6 | Team Meeting | Meeting |  | 28/11/2016 |  | 3 | 28/11/2016 | XuanThaiHien | Complete
| 7 | Review Business Workflow "Manage Account"function | Requirement |  | 28/11/2016 | 4 | 5 | 28/11/2016 | HienNguyen | Complete
| 8 | Review Business Workflow "Manage Account"function | Requirement |  | 28/11/2016 | 3 | 5 | 28/11/2016 | HaiTran | Complete
| 9 | Review Business Workflow "Manage News" function | Requirement |  | 28/11/2016 | 4 | 4 | 28/11/2016 | MinhDoan | Complete
| 10 | Review Business Workflow "Manage News" function | Requirement |  | 28/11/2016 | 3 | 4 | 28/11/2016 | KhoiNguyen | Complete
| 11 | Review Business Workflow "Manage Banners" function | Requirement |  | 28/11/2016 | 3 | 3 | 28/11/2016 | TaiNguyen | Complete
| 12 | Review Business Workflow "Manage Banners" function | Requirement |  | 28/11/2016 | 2 | 3 | 28/11/2016 | XuanThaiHien | Complete
| 13 | Review Business Workflow "Manage Pop-ups" function | Requirement |  | 29/11/2016 | 3 | 2 | 29/11/2016 | MinhDoan | Complete
| 14 | Review Business Workflow "Manage Pop-ups" function | Requirement |  | 29/11/2016 | 2 | 2 | 29/11/2016 | XuanThaiHien | Complete
| 15 | Review Business Workflow "Manage FAQ" function | Requirement |  | 29/11/2016 | 4 | 2 | 29/11/2016 | KhoiNguyen | Complete
| 16 | Review Business Workflow "Manage FAQ" function | Requirement |  | 29/11/2016 | 3 | 2 | 29/11/2016 | HienNguyen | Complete
| 17 | Review Business Workflow "Manage Homepage" function | Requirement |  | 29/11/2016 | 3 | 5 | 29/11/2016 | TaiNguyen | Complete
| 18 | Review Business Workflow "Manage Homepage" function | Requirement |  | 29/11/2016 | 2 | 5 | 29/11/2016 | HaiTran | Complete
| 19 | Review Business Workflow "Manage Languages" function | Requirement |  | 29/11/2016 | 1 | 1 | 29/11/2016 | KhoiNguyen | Complete
| 20 | Review Business Workflow "Manage Languages" function | Requirement |  | 29/11/2016 | 1 | 1 | 29/11/2016 | HaiTran | Complete
| 21 | Review Business Workflow "Manage Categories " function | Requirement |  | 29/11/2016 | 3 | 4 | 29/11/2016 | TaiNguyen | Complete
| 22 | Review Business Workflow "Manage Categories " function | Requirement |  | 29/11/2016 | 4 | 4 | 29/11/2016 | HienNguyen | Complete
| 23 | Review Business Workflow "Manage Examination " function | Requirement |  | 29/11/2016 | 2 | 3 | 29/11/2016 | XuanThaiHien | Complete
| 24 | Review Business Workflow "Manage Examination " function | Requirement |  | 29/11/2016 | 3 | 3 | 29/11/2016 | MinhDoan | Complete
| 25 | Training Technical | Training |  | 29/11/2016 | 2 | 2 | 29/11/2016 | HaiTran | Complete
| 26 | Training Technical | Training |  | 29/11/2016 | 2 | 2 | 29/11/2016 | HienNguyen | Complete
| 27 | Training Technical | Training |  | 29/11/2016 | 2 | 2 | 29/11/2016 | KhoiNguyen | Complete
| 28 | Training Technical | Training |  | 29/11/2016 | 2 | 2 | 29/11/2016 | MinhDoan | Complete
| 29 | Training Technical | Training |  | 29/11/2016 | 2 | 2 | 29/11/2016 | TaiNguyen | Complete
| 30 | Training Technical | Training |  | 29/11/2016 | 2 | 2 | 29/11/2016 | XuanThaiHien | Complete
| 31 | Update Business workflow "Manage Accounts" function | Requirement |  | 30/11/2016 | 5 | 4 | 2016-01-12 | HaiTran | Complete
| 32 | Update Business workflow "Manage News" function | Requirement |  | 30/11/2016 | 5 | 7 | 2016-01-12 | HaiTran | Complete
| 33 | Update Business workflow "Manage Banners" function | Requirement |  | 30/11/2016 | 3 | 4 | 2016-01-12 | TaiNguyen | Complete
| 34 | Update Business workflow "Manage Pop-ups" function | Requirement |  | 30/11/2016 | 3 | 2 | 2016-01-12 | TaiNguyen | Complete
| 35 | Update Business workflow "Manage FAQ" function | Requirement |  | 30/11/2016 | 4 | 5 | 2016-01-12 | KhoiNguyen | Complete
| 36 | Update Business workflow "Manage Homepage" function | Requirement |  | 30/11/2016 | 3 | 5 | 2016-01-12 | HienNguyen | Complete
| 37 | Update Business workflow "Manage Categories " function | Requirement |  | 30/11/2016 | 3 | 3 | 2016-01-12 | MinhDoan | Complete
| 38 | Update Business workflow "Manage Examination " function | Requirement |  | 30/11/2016 | 2 | 3 | 2016-01-12 | XuanThaiHien | Complete
| 39 | Define Business Requirements | Requirement |  | 2016-01-12 | 4 | 6 | 2016-01-12 | MinhDoan | Complete
| 40 | Define Vision of the soulution | Requirement |  | 2016-01-12 | 5 | 5 | 2016-01-12 | HienNguyen | Complete
| 41 | Define Scope and Limitations | Requirement |  | 2016-01-12 | 3 | 6 | 2016-01-12 | KhoiNguyen | Complete
| 42 | Define Business Context | Requirement |  | 2016-01-12 | 2 | 3 | 2016-01-12 | XuanThaiHien | Complete
| 43 | Define Current System | Requirement |  | 2016-01-12 | 2 | 1 | 2016-01-12 | TaiNguyen | Complete
| 44 | Define Proposed System | Requirement |  | 2016-01-12 | 4 | 2 | 2016-01-12 | HaiTran | Complete
| 45 | Define Context Diagram | Requirement |  | 2016-02-12 | 3 | 5 | 2016-03-12 | TaiNguyen | Complete
| 46 | Define Environment System | Requirement |  | 2016-02-12 | 4 | 3 | 2016-03-12 | MinhDoan | Complete
| 47 | Define Justification of Changes | Requirement |  | 2016-02-12 | 2 | 5 | 2016-03-12 | KhoiNguyen | Complete
| 48 | Define Summary of impacts | Requirement |  | 2016-02-12 | 2 | 4 | 2016-03-12 | HienNguyen | Complete
| 49 | Define analysis summarizing future system | Requirement |  | 2016-02-12 | 3 | 5 | 2016-03-12 | HaiTran | Complete
| 50 | Develop prototype for website | Requirement |  | 2016-02-12 | 6 | 9 | 2016-03-12 | TaiNguyen | Complete
10 | 1 | Team Meeting | Meeting |  | 2016-05-12 | 2 | 2 | 2016-05-12 | HienNguyen | Complete
| 2 | Team Meeting | Meeting |  | 2016-05-12 | 2 | 2 | 2016-05-12 | HaiTran | Complete
| 3 | Team Meeting | Meeting |  | 2016-05-12 | 2 | 2 | 2016-05-12 | KhoiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 2016-05-12 | 2 | 2 | 2016-05-12 | TaiNguyen | Complete
| 5 | Team Meeting | Meeting |  | 2016-05-12 | 2 | 2 | 2016-05-12 | MinhDoan | Complete
| 6 | Team Meeting | Meeting |  | 2016-05-12 | 2 | 2 | 2016-05-12 | XuanThaiHien | Complete
| 7 | Review Business Requirements | Requirement |  | 2016-05-12 | 3 | 4 | 2016-05-12 | MinhDoan | Complete
| 8 | Review Business Requirements | Requirement |  | 2016-05-12 | 2 | 4 | 2016-05-12 | KhoiNguyen | Complete
| 9 | Review Vision of the soulution | Requirement |  | 2016-05-12 | 3 | 2 | 2016-05-12 | HaiTran | Complete
| 10 | Review Vision of the soulution | Requirement |  | 2016-05-12 | 2 | 2 | 2016-05-12 | HienNguyen | Complete
| 11 | Review Scope and Limitations | Requirement |  | 2016-05-12 | 2 | 2 | 2016-05-12 | XuanThaiHien | Complete
| 12 | Review Scope and Limitations | Requirement |  | 2016-05-12 | 2 | 2 | 2016-05-12 | MinhDoan | Complete
| 13 | Review Business Context | Requirement |  | 2016-05-12 | 3 | 5 | 2016-05-12 | TaiNguyen | Complete
| 14 | Review Business Context | Requirement |  | 2016-05-12 | 4 | 5 | 2016-05-12 | MinhDoan | Complete
| 15 | Review Proposed System | Requirement |  | 2016-06-12 | 4 | 6 | 2016-06-12 | HienNguyen | Complete
| 16 | Review Proposed System | Requirement |  | 2016-06-12 | 5 | 6 | 2016-06-12 | TaiNguyen | Complete
| 17 | Review Context Diagram | Requirement |  | 2016-06-12 | 6 | 5 | 2016-06-12 | KhoiNguyen | Complete
| 18 | Review Context Diagram | Requirement |  | 2016-06-12 | 5 | 5 | 2016-06-12 | HienNguyen | Complete
| 19 | Review prototype for website | Requirement |  | 2016-06-12 | 6 | 6 | 2016-06-12 | HaiTran | Complete
| 20 | Review prototype for website | Requirement |  | 2016-06-12 | 5 | 6 | 2016-06-12 | TaiNguyen | Complete
| 21 | Collect into Concept of Operation document | Requirement |  | 2016-06-12 | 1 | 1 | 2016-06-12 | MinhDoan | Complete
| 22 | Training Technical | Training |  | 2016-06-12 | 2 | 2 | 2016-06-12 | HienNguyen | Complete
| 23 | Training Technical | Training |  | 2016-06-12 | 2 | 2 | 2016-06-12 | HaiTran | Complete
| 24 | Training Technical | Training |  | 2016-06-12 | 2 | 2 | 2016-06-12 | TaiNguyen | Complete
| 25 | Training Technical | Training |  | 2016-06-12 | 2 | 2 | 2016-06-12 | KhoiNguyen | Complete
| 26 | Training Technical | Training |  | 2016-06-12 | 2 | 2 | 2016-06-12 | MinhDoan | Complete
| 27 | Training Technical | Training |  | 2016-06-12 | 2 | 2 | 2016-06-12 | XuanThaiHien | Complete
| 28 | Customer Meeting | Meeting |  | 2016-07-12 | 2 | 3 | 2016-07-12 | HienNguyen | Complete
| 29 | Customer Meeting | Meeting |  | 2016-07-12 | 2 | 3 | 2016-07-12 | HaiTran | Complete
| 30 | Customer Meeting | Meeting |  | 2016-07-12 | 2 | 3 | 2016-07-12 | TaiNguyen | Complete
| 31 | Customer Meeting | Meeting |  | 2016-07-12 | 2 | 3 | 2016-07-12 | KhoiNguyen | Complete
| 32 | Customer Meeting | Meeting |  | 2016-07-12 | 2 | 3 | 2016-07-12 | MinhDoan | Complete
| 33 | Customer Meeting | Meeting |  | 2016-07-12 | 2 | 3 | 2016-07-12 | XuanThaiHien | Complete
| 34 | Write Usecase description "Manage Accounts" Function | Requirement |  | 2016-07-12 | 7 | 8 | 2016-08-12 | HienNguyen | Complete
| 35 | Write Usecase description "Manage News" Function | Requirement |  | 2016-07-12 | 8 | 10 | 2016-08-12 | HaiTran | Complete
| 36 | Write Usecase description "Manage Homepage" Function | Requirement |  | 2016-07-12 | 5 | 5 | 2016-08-12 | TaiNguyen | Complete
| 37 | Write Usecase description "Manage Q&A" Function | Requirement |  | 2016-07-12 | 3 | 5 | 2016-08-12 | KhoiNguyen | Complete
| 38 | Write Usecase description "Manage Banners" Function | Requirement |  | 2016-07-12 | 4 | 4 | 2016-08-12 | MinhDoan | Complete
| 39 | Write Usecase description "Manage Pop-ups Function | Requirement |  | 2016-07-12 | 3 | 4 | 2016-08-12 | MinhDoan | Complete
| 40 | Write Usecase description "Manage Categories" Function | Requirement |  | 2016-07-12 | 5 | 5 | 2016-08-12 | HaiTran | Complete
| 41 | Write Usecase description "Manage Languages" Function | Requirement |  | 2016-07-12 | 2 | 2 | 2016-08-12 | KhoiNguyen | Complete
| 42 | Write Usecase description "Manage Examination" Function | Requirement |  | 2016-07-12 | 3 | 3 | 2016-08-12 | XuanThaiHien | Complete
| 43 | Draw Usecase Diagram "Manage Accouts" Function | Requirement |  | 2016-08-12 | 5 | 5 | 2016-09-12 | HienNguyen | Complete
| 44 | Draw Usecase Diagram "Manage News" Function | Requirement |  | 2016-08-12 | 4 | 4 | 2016-09-12 | HaiTran | Complete
| 45 | Draw Usecase Diagram "Manage Q&A" Function | Requirement |  | 2016-08-12 | 4 | 4 | 2016-09-12 | TaiNguyen | Complete
| 46 | Draw Usecase Diagram "Manage Homepage" Function | Requirement |  | 2016-08-12 | 4 | 3 | 2016-09-12 | KhoiNguyen | Complete
| 47 | Draw Usecase Diagram "Manage Banners" Function | Requirement |  | 2016-08-12 | 3 | 3 | 2016-09-12 | MinhDoan | Complete
| 48 | Draw Usecase Diagram "Manage Pop-ups" Function | Requirement |  | 2016-08-12 | 2 | 3 | 2016-09-12 | MinhDoan | Complete
| 49 | Draw Usecase Diagram "Manage Languages" Function | Requirement |  | 2016-08-12 | 1 | 1 | 2016-09-12 | HaiTran | Complete
| 50 | Draw Usecase Diagram "Manage Categories" Function | Requirement |  | 2016-08-12 | 3 | 4 | 2016-09-12 | KhoiNguyen | Complete
| 51 | Draw Usecase Diagram "Manage Examination" Function | Requirement |  | 2016-08-12 | 3 | 4 | 2016-09-12 | XuanThaiHien | Complete
11 | 1 | Team Meeting | Meeting |  | 2016-12-12 | 2 | 2 | 2016-12-12 | MinhDoan | Complete
| 2 | Team Meeting | Meeting |  | 2016-12-12 | 2 | 2 | 2016-12-12 | HaiTran | Complete
| 3 | Team Meeting | Meeting |  | 2016-12-12 | 2 | 2 | 2016-12-12 | HienNguyen | Complete
| 4 | Team Meeting | Meeting |  | 2016-12-12 | 2 | 2 | 2016-12-12 | TaiNguyen | Complete
| 5 | Team Meeting | Meeting |  | 2016-12-12 | 2 | 2 | 2016-12-12 | KhoiNguyen | Complete
| 6 | Team Meeting | Meeting |  | 2016-12-12 | 2 | 2 | 2016-12-12 | XuanThaiHien | Complete
| 7 | Review Usecase description "Manage Accounts" Function | Requirement |  | 2016-12-12 | 5 | 4 | 2016-12-12 | HaiTran | Complete
| 8 | Review Usecase description "Manage Accounts" Function | Requirement |  | 2016-12-12 | 4 | 4 | 2016-12-12 | HienNguyen | Complete
| 9 | Review Usecase description "Manage News" Function | Requirement |  | 2016-12-12 | 6 | 4 | 2016-12-12 | KhoiNguyen | Complete
| 10 | Review Usecase description "Manage News" Function | Requirement |  | 2016-12-12 | 4 | 5 | 2016-12-12 | TaiNguyen | Complete
| 11 | Review Usecase description "Manage Homepage" Function | Requirement |  | 2016-12-12 | 3 | 4 | 2016-12-12 | MinhDoan | Complete
| 12 | Review Usecase description "Manage Homepage" Function | Requirement |  | 2016-12-12 | 3 | 2 | 2016-12-12 | XuanThaiHien | Pending
| 13 | Review Usecase description "Manage Q&A" Function | Requirement |  | 13/12/2016 | 4 | 3 | 13/12/2016 | TaiNguyen | Complete
| 14 | Review Usecase description "Manage Q&A" Function | Requirement |  | 13/12/2016 | 3 | 3 | 13/12/2016 | MinhDoan | Complete
| 15 | Review Usecase description "Manage Banners" Function | Requirement |  | 13/12/2016 | 2 | 3 | 13/12/2016 | HaiTran | Complete
| 16 | Review Usecase description "Manage Banners" Function | Requirement |  | 13/12/2016 | 3 | 2 | 13/12/2016 | KhoiNguyen | Complete
| 17 | Review Usecase description "Manage Pop-ups Function | Requirement |  | 13/12/2016 | 2 | 2 | 13/12/2016 | XuanThaiHien | Complete
| 18 | Review Usecase description "Manage Pop-ups Function | Requirement |  | 13/12/2016 | 3 | 2 | 13/12/2016 | HienNguyen | Complete
| 19 | Review Usecase description "Manage Categories" Function | Requirement |  | 13/12/2016 | 4 | 5 | 13/12/2016 | TaiNguyen | Complete
| 20 | Review Usecase description "Manage Categories" Function | Requirement |  | 13/12/2016 | 5 | 3 | 13/12/2016 | HaiTran | Complete
| 21 | Review Usecase description "Manage Languages" Function | Requirement |  | 13/12/2016 | 2 | 1 | 13/12/2016 | KhoiNguyen | Complete
| 22 | Review Usecase description "Manage Languages" Function | Requirement |  | 13/12/2016 | 1 | 1 | 13/12/2016 | MinhDoan | Complete
| 23 | Review Usecase description "Manage Examination" Function | Requirement |  | 13/12/2016 | 3 | 4 | 13/12/2016 | HienNguyen | Complete
| 24 | Training Technical | Training |  | 13/12/2016 | 2 | 2 | 13/12/2016 | HaiTran | Complete
| 25 | Training Technical | Training |  | 13/12/2016 | 2 | 2 | 13/12/2016 | HienNguyen | Complete
| 26 | Training Technical | Training |  | 13/12/2016 | 2 | 2 | 13/12/2016 | MinhDoan | Complete
| 27 | Training Technical | Training |  | 13/12/2016 | 2 | 2 | 13/12/2016 | TaiNguyen | Complete
| 28 | Training Technical | Training |  | 13/12/2016 | 2 | 2 | 13/12/2016 | KhoiNguyen | Complete
| 29 | Review Usecase Diagram "Manage Accouts" Function | Requirement |  | 14/12/2016 | 4 | 5 | 14/12/2016 | HienNguyen | Complete
| 30 | Review Usecase Diagram "Manage News" Function | Requirement |  | 14/12/2016 | 6 | 5 | 14/12/2016 | TaiNguyen | Complete
| 31 | Review Usecase Diagram "Manage Q&A" Function | Requirement |  | 14/12/2016 | 3 | 2 | 14/12/2016 | MinhDoan | Complete
| 32 | Review Usecase Diagram "Manage Homepage" Function | Requirement |  | 14/12/2016 | 4 | 2 | 14/12/2016 | HaiTran | Complete
| 33 | Review Usecase Diagram "Manage Banners" Function | Requirement |  | 14/12/2016 | 2 | 3 | 14/12/2016 | KhoiNguyen | Complete
| 34 | Review Usecase Diagram "Manage Pop-ups" Function | Requirement |  | 14/12/2016 | 3 | 3 | 14/12/2016 | KhoiNguyen | Complete
| 35 | Review Usecase Diagram "Manage Languages" Function | Requirement |  | 14/12/2016 | 2 | 1 | 14/12/2016 | XuanThaiHien | Pending
| 36 | Review Usecase Diagram "Manage Categories" Function | Requirement |  | 14/12/2016 | 3 | 3 | 14/12/2016 | HaiTran | Complete
| 37 | Review Usecase Diagram "Manage Examination" Function | Requirement |  | 14/12/2016 | 2 | 3 | 14/12/2016 | MinhDoan | Complete
| 38 | Collect into Usecase Specification document | Requirement |  | 14/12/2016 | 1 | 1 | 14/12/2016 | MinhDoan | Complete
| 39 | Define Product Functions | Requirement |  | 15/12/2016 | 1 | 1 | 15/12/2016 | MinhDoan | Complete
| 40 | Define user classes and characteristics | Requirement |  | 15/12/2016 | 3 | 3 | 15/12/2016 | HienNguyen | Complete
| 41 | Define Operating environment | Requirement |  | 15/12/2016 | 2 | 1 | 15/12/2016 | TaiNguyen | Complete
| 42 | Define Business constraint | Requirement |  | 15/12/2016 | 1 | 2 | 15/12/2016 | KhoiNguyen | Complete
| 43 | Define Business rules | Requirement |  | 15/12/2016 | 2 | 1 | 15/12/2016 | XuanThaiHien | Complete
| 44 | Define Quality Attribute | Requirement |  | 15/12/2016 | 4 | 3 | 15/12/2016 | HaiTran | Complete
| 45 | Develop UI "Manage Accounts" Function | Requirement |  | 16/12/2016 | 5 | 6 | 17/12/2016 | HaiTran | Pending
| 46 | Develop UI "Manage News" Function | Requirement |  | 16/12/2016 | 6 | 8 | 17/12/2016 | TaiNguyen | Pending
| 47 | Develop UI "Manage Q&A" Function | Requirement |  | 16/12/2016 | 4 | 6 | 17/12/2016 | HienNguyen | Pending
| 48 | Develop UI "Manage Homepage" Function | Requirement |  | 16/12/2016 | 5 | 7 | 17/12/2016 | KhoiNguyen | Pending
| 49 | Develop UI "Manage Banners" Function | Requirement |  | 16/12/2016 | 3 | 5 | 17/12/2016 | MinhDoan | Pending
| 50 | Develop UI "Manage Pop-ups" Function | Requirement |  | 16/12/2016 | 3 | 5 | 17/12/2016 | MinhDoan | Pending
| 51 | Develop UI "Manage Languages" Function | Requirement |  | 16/12/2016 | 2 | 1 | 17/12/2016 | KhoiNguyen | Pending
| 52 | Develop UI "Manage Categories" Function | Requirement |  | 16/12/2016 | 5 | 8 | 17/12/2016 | HaiTran | Pending
| 53 | Develop UI "Manage Examination" Function | Requirement |  | 16/12/2016 | 3 | 5 | 17/12/2016 | XuanThaiHien | Pending
12 | 1 | Team Meeting | Meeting |  | 19/12/2016 | 2 | 2 | 19/12/2016 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 19/12/2016 | 2 | 2 | 19/12/2016 | HienNguyen | Complete
| 3 | Team Meeting | Meeting |  | 19/12/2016 | 2 | 2 | 19/12/2016 | TaiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 19/12/2016 | 2 | 2 | 19/12/2016 | MinhDoan | Complete
| 5 | Team Meeting | Meeting |  | 19/12/2016 | 2 | 2 | 19/12/2016 | KhoiNguyen | Complete
| 6 | Update Usecase description "Manage Accounts" Function | Requirement |  | 19/12/2016 | 3 | 4 | 19/12/2016 | HienNguyen | Complete
| 7 | Update Usecase description "Manage News" Function | Requirement |  | 19/12/2016 | 4 | 4 | 19/12/2016 | HaiTran | Complete
| 8 | Update Usecase description "Manage Homepage" Function | Requirement |  | 19/12/2016 | 2 | 3 | 19/12/2016 | TaiNguyen | Complete
| 9 | Update Usecase description "Manage Q&A" Function | Requirement |  | 19/12/2016 | 2 | 3 | 19/12/2016 | KhoiNguyen | Complete
| 10 | Update Usecase description "Manage Banners" Function | Requirement |  | 19/12/2016 | 2 | 3 | 19/12/2016 | MinhDoan | Complete
| 11 | Update Usecase description "Manage Pop-ups Function | Requirement |  | 19/12/2016 | 2 | 3 | 19/12/2016 | MinhDoan | Complete
| 12 | Update Usecase description "Manage Categories" Function | Requirement |  | 19/12/2016 | 3 | 4 | 19/12/2016 | HaiTran | Complete
| 13 | Update Usecase description "Manage Languages" Function | Requirement |  | 19/12/2016 | 2 | 1 | 19/12/2016 | KhoiNguyen | Complete
| 14 | Update Usecase description "Manage Examination" Function | Requirement |  | 19/12/2016 | 2 | 3 | 19/12/2016 | XuanThaiHien | Pending
| 15 | Update Usecase Diagram "Manage Accouts" Function | Requirement |  | 20/12/2016 | 2 | 3 | 20/12/2016 | HienNguyen | Complete
| 16 | Update Usecase Diagram "Manage News" Function | Requirement |  | 20/12/2016 | 2 | 2 | 20/12/2016 | HaiTran | Complete
| 17 | Update Usecase Diagram "Manage Q&A" Function | Requirement |  | 20/12/2016 | 3 | 2 | 20/12/2016 | TaiNguyen | Complete
| 18 | Update Usecase Diagram "Manage Homepage" Function | Requirement |  | 20/12/2016 | 2 | 2 | 20/12/2016 | KhoiNguyen | Complete
| 19 | Update Usecase Diagram "Manage Banners" Function | Requirement |  | 20/12/2016 | 2 | 3 | 20/12/2016 | MinhDoan | Complete
| 20 | Update Usecase Diagram "Manage Pop-ups" Function | Requirement |  | 20/12/2016 | 3 | 2 | 20/12/2016 | MinhDoan | Complete
| 21 | Update Usecase Diagram "Manage Languages" Function | Requirement |  | 20/12/2016 | 1 | 2 | 20/12/2016 | HaiTran | Complete
| 22 | Update Usecase Diagram "Manage Categories" Function | Requirement |  | 20/12/2016 | 3 | 3 | 20/12/2016 | KhoiNguyen | Complete
| 23 | Update Usecase Diagram "Manage Examination" Function | Requirement |  | 20/12/2016 | 3 | 2 | 20/12/2016 | XuanThaiHien | Pending
| 24 | Training Technical | Training |  | 20/12/2016 | 2 | 2 | 20/12/2016 | HaiTran | Complete
| 25 | Training Technical | Training |  | 20/12/2016 | 2 | 2 | 20/12/2016 | HienNguyen | Complete
| 26 | Training Technical | Training |  | 20/12/2016 | 2 | 2 | 20/12/2016 | MinhDoan | Complete
| 27 | Training Technical | Training |  | 20/12/2016 | 2 | 2 | 20/12/2016 | TaiNguyen | Complete
| 28 | Training Technical | Training |  | 20/12/2016 | 2 | 2 | 20/12/2016 | KhoiNguyen | Complete
| 29 | Customer Meeting | Meeting |  | 21/12/2016 | 3 | 2 | 21/12/2016 | HienNguyen | Complete
| 30 | Customer Meeting | Meeting |  | 21/12/2016 | 3 | 2 | 21/12/2016 | HaiTran | Complete
| 31 | Customer Meeting | Meeting |  | 21/12/2016 | 3 | 2 | 21/12/2016 | TaiNguyen | Complete
| 32 | Customer Meeting | Meeting |  | 21/12/2016 | 3 | 2 | 21/12/2016 | KhoiNguyen | Complete
| 33 | Customer Meeting | Meeting |  | 21/12/2016 | 3 | 2 | 21/12/2016 | MinhDoan | Complete
| 34 | Develop "Manage News" Functional Testcase | Requirement |  | 21/12/2016 | 7 | 8 | 23/12/2016 | HaiTran | Complete
| 35 | Develop "Manage Account" Functional Testcase | Requirement |  | 21/12/2016 | 6 | 6 | 23/12/2016 | HienNguyen | Complete
| 36 | Develop "Manage Homepage" Functional Testcase | Requirement |  | 21/12/2016 | 5 | 6 | 23/12/2016 | TaiNguyen | Complete
| 37 | Develop "Manage Categories" Functional Testcase | Requirement |  | 21/12/2016 | 6 | 7 | 23/12/2016 | KhoiNguyen | Complete
| 38 | Develop "Manage Banners" Functional Testcase | Requirement |  | 21/12/2016 | 6 | 5 | 23/12/2016 | MinhDoan | Complete
| 39 | Develop "Manage Pop-ups" Functional Testcase | Requirement |  | 21/12/2016 | 6 | 7 | 23/12/2016 | MinhDoan | Complete
| 40 | Develop "Manage Examination" Functional Testcase | Requirement |  | 21/12/2016 | 4 | 4 | 23/12/2016 | XuanThaiHien | Complete
| 41 | Develop "Manage Q&A" Functional Testcase | Requirement |  | 21/12/2016 | 5 | 6 | 24/12/2016 | XuanThaiHien | Complete
| 42 | Develop "Manage Languages" Functional Testcase | Requirement |  | 21/12/2016 | 3 | 2 | 24/12/2016 | KhoiNguyen | Complete
| 43 | Develop "Manage Account" User Acceptance Testcase | Requirement |  | 21/12/2016 | 7 | 6 | 24/12/2016 | HaiTran | Complete
| 44 | Develop "Manage News" User Acceptance Testcase | Requirement |  | 21/12/2016 | 7 | 5 | 24/12/2016 | HienNguyen | Complete
| 45 | Develop "Manage Homepage" User Acceptance Testcase | Requirement |  | 21/12/2016 | 6 | 5 | 24/12/2016 | TaiNguyen | Complete
| 46 | Develop "Manage Banners" User Acceptance Testcase | Requirement |  | 21/12/2016 | 3 | 4 | 24/12/2016 | MinhDoan | Complete
| 47 | Develop "Manage Pop-ups" User Acceptance Testcase | Requirement |  | 21/12/2016 | 3 | 4 | 24/12/2016 | MinhDoan | Complete
| 48 | Develop "Manage Categories" User Acceptance Testcase | Requirement |  | 21/12/2016 | 6 | 6 | 24/12/2016 | KhoiNguyen | Complete
| 49 | Develop "Manage Examination" User Acceptance Testcase | Requirement |  | 21/12/2016 | 6 | 4 | 24/12/2016 | XuanThaiHien | Complete
| 50 | Develop "Manage Q&A" User Acceptance Testcase | Requirement |  | 21/12/2016 | 3 | 5 | 24/12/2016 | KhoiNguyen | Complete
| 51 | Develop "Manage Languages" User Acceptance Testcase | Requirement |  | 21/12/2016 | 2 | 2 | 24/12/2016 | HaiTran | Complete
13 | 1 | Team Meeting | Meeting | Architect | 26/12/2016 | 2 | 2 | 26/12/2016 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 26/12/2016 | 2 | 2 | 26/12/2016 | HienNguyen | Complete
| 3 | Team Meeting | Meeting |  | 26/12/2016 | 2 | 2 | 26/12/2016 | MinhDoan | Complete
| 4 | Team Meeting | Meeting |  | 26/12/2016 | 2 | 2 | 26/12/2016 | TaiNguyen | Complete
| 5 | Team Meeting | Meeting |  | 26/12/2016 | 2 | 2 | 26/12/2016 | KhoiNguyen | Complete
| 6 | Review "Manage News" Functional Testcase | Requirement |  | 26/12/2016 | 4 | 5 | 26/12/2016 | HaiTran | Complete
| 7 | Review "Manage News" Functional Testcase | Requirement |  | 26/12/2016 | 3 | 6 | 26/12/2016 | HienNguyen | Complete
| 8 | Review "Manage Account" Functional Testcase | Requirement |  | 26/12/2016 | 5 | 7 | 26/12/2016 | TaiNguyen | Complete
| 9 | Review "Manage Account" Functional Testcase | Requirement |  | 26/12/2016 | 4 | 5 | 26/12/2016 | MinhDoan | Complete
| 10 | Review "Manage Homepage" Functional Testcase | Requirement |  | 26/12/2016 | 4 | 3 | 26/12/2016 | KhoiNguyen | Complete
| 11 | Review "Manage Homepage" Functional Testcase | Requirement |  | 26/12/2016 | 2 | 2 | 26/12/2016 | XuanThaiHien | Complete
| 12 | Review "Manage Categories" Functional Testcase | Requirement |  | 27/12/2016 | 3 | 3 | 27/12/2016 | KhoiNguyen | Complete
| 13 | Review "Manage Categories" Functional Testcase | Requirement |  | 27/12/2016 | 3 | 4 | 27/12/2016 | HienNguyen | Complete
| 14 | Review "Manage Banners" Functional Testcase | Requirement |  | 27/12/2016 | 2 | 2 | 27/12/2016 | MinhDoan | Complete
| 15 | Review "Manage Banners" Functional Testcase | Requirement |  | 27/12/2016 | 3 | 2 | 27/12/2016 | XuanThaiHien | Complete
| 16 | Review "Manage Pop-ups" Functional Testcase | Requirement |  | 27/12/2016 | 2 | 2 | 27/12/2016 | HaiTran | Complete
| 17 | Review "Manage Pop-ups" Functional Testcase | Requirement |  | 27/12/2016 | 2 | 1 | 27/12/2016 | TaiNguyen | Complete
| 18 | Review "Manage Examination" Functional Testcase | Requirement |  | 27/12/2016 | 2 | 2 | 27/12/2016 | TaiNguyen | Complete
| 19 | Review "Manage Examination" Functional Testcase | Requirement |  | 27/12/2016 | 1 | 2 | 27/12/2016 | MinhDoan | Complete
| 20 | Training Technical | Training |  | 27/12/2016 | 2 | 2 | 27/12/2016 | HaiTran | Complete
| 21 | Training Technical | Training |  | 27/12/2016 | 2 | 2 | 27/12/2016 | HienNguyen | Complete
| 22 | Training Technical | Training |  | 27/12/2016 | 2 | 2 | 27/12/2016 | KhoiNguyen | Complete
| 23 | Training Technical | Training |  | 27/12/2016 | 2 | 2 | 27/12/2016 | MinhDoan | Complete
| 24 | Training Technical | Training |  | 27/12/2016 | 2 | 2 | 27/12/2016 | TaiNguyen | Complete
| 25 | Review "Manage Q&A" Functional Testcase | Requirement |  | 28/12/2016 | 2 | 3 | 28/12/2016 | MinhDoan | Complete
| 26 | Review "Manage Q&A" Functional Testcase | Requirement |  | 28/12/2016 | 3 | 2 | 28/12/2016 | KhoiNguyen | Complete
| 27 | Review "Manage Languages" Functional Testcase | Requirement |  | 28/12/2016 | 1 | 2 | 28/12/2016 | HienNguyen | Complete
| 28 | Review "Manage Languages" Functional Testcase | Requirement |  | 28/12/2016 | 1 | 1 | 28/12/2016 | XuanThaiHien | Complete
| 29 | Review "Manage Account" User Acceptance Testcase | Requirement |  | 28/12/2016 | 5 | 6 | 28/12/2016 | HaiTran | Complete
| 30 | Review "Manage Account" User Acceptance Testcase | Requirement |  | 28/12/2016 | 4 | 6 | 28/12/2016 | TaiNguyen | Complete
| 31 | Review "Manage News" User Acceptance Testcase | Requirement |  | 28/12/2016 | 4 | 6 | 28/12/2016 | HienNguyen | Complete
| 32 | Review "Manage News" User Acceptance Testcase | Requirement |  | 28/12/2016 | 5 | 6 | 28/12/2016 | KhoiNguyen | Complete
| 33 | Review "Manage Homepage" User Acceptance Testcase | Requirement |  | 28/12/2016 | 3 | 4 | 28/12/2016 | MinhDoan | Complete
| 34 | Review "Manage Homepage" User Acceptance Testcase | Requirement |  | 28/12/2016 | 2 | 3 | 28/12/2016 | TaiNguyen | Complete
| 35 | Review "Manage Banners" User Acceptance Testcase | Requirement |  | 28/12/2016 | 2 | 1 | 28/12/2016 | XuanThaiHien | Complete
| 36 | Review "Manage Banners" User Acceptance Testcase | Requirement |  | 28/12/2016 | 2 | 3 | 28/12/2016 | HaiTran | Complete
| 37 | Review "Manage Pop-ups" User Acceptance Testcase | Requirement |  | 29/12/2016 | 2 | 1 | 29/12/2016 | XuanThaiHien | Complete
| 38 | Review "Manage Pop-ups" User Acceptance Testcase | Requirement |  | 29/12/2016 | 2 | 3 | 29/12/2016 | MinhDoan | Complete
| 39 | Review "Manage Categories" User Acceptance Testcase | Requirement |  | 29/12/2016 | 4 | 6 | 29/12/2016 | TaiNguyen | Complete
| 40 | Review "Manage Categories" User Acceptance Testcase | Requirement |  | 29/12/2016 | 5 | 6 | 29/12/2016 | HienNguyen | Complete
| 41 | Review "Manage Examination" User Acceptance Testcase | Requirement |  | 29/12/2016 | 3 | 4 | 29/12/2016 | KhoiNguyen | Complete
| 42 | Review "Manage Examination" User Acceptance Testcase | Requirement |  | 29/12/2016 | 2 | 3 | 29/12/2016 | HaiTran | Complete
| 43 | Review "Manage Q&A" User Acceptance Testcase | Requirement |  | 29/12/2016 | 2 | 3 | 29/12/2016 | HaiTran | Complete
| 44 | Review "Manage Q&A" User Acceptance Testcase | Requirement |  | 29/12/2016 | 2 | 2 | 29/12/2016 | TaiNguyen | Complete
| 45 | Review "Manage Languages" User Acceptance Testcase | Requirement |  | 29/12/2016 | 1 | 1 | 29/12/2016 | MinhDoan | Complete
| 46 | Review "Manage Languages" User Acceptance Testcase | Requirement |  | 29/12/2016 | 1 | 1 | 29/12/2016 | HienNguyen | Complete
| 47 | Update "Manage News" Functional Testcase | Requirement |  | 29/12/2016 | 3 | 3 | 29/12/2016 | HaiTran | Complete
| 48 | Update "Manage Account" Functional Testcase | Requirement |  | 29/12/2016 | 2 | 3 | 29/12/2016 | HienNguyen | Complete
| 49 | Update "Manage Homepage" Functional Testcase | Requirement |  | 29/12/2016 | 2 | 2 | 29/12/2016 | TaiNguyen | Complete
| 50 | Update "Manage Categories" Functional Testcase | Requirement |  | 29/12/2016 | 3 | 2 | 29/12/2016 | KhoiNguyen | Complete
| 51 | Update "Manage Banners" Functional Testcase | Requirement |  | 29/12/2016 | 2 | 2 | 29/12/2016 | MinhDoan | Complete
| 52 | Update "Manage Pop-ups" Functional Testcase | Requirement |  | 29/12/2016 | 2 | 3 | 29/12/2016 | MinhDoan | Complete
| 53 | Update "Manage Examination" Functional Testcase | Requirement |  | 29/12/2016 | 3 | 3 | 29/12/2016 | XuanThaiHien | Complete
| 54 | Update "Manage Q&A" Functional Testcase | Requirement |  | 29/12/2016 | 3 | 2 | 29/12/2016 | XuanThaiHien | Complete
| 55 | Update "Manage Languages" Functional Testcase | Requirement |  | 29/12/2016 | 2 | 1 | 29/12/2016 | KhoiNguyen | Complete
| 56 | Collect Testcase | Requirement |  | 29/12/2016 | 1 | 2 | 29/12/2016 | KhoiNguyen | Complete
| 57 | Research Physical view | Architect |  | 30/12/2016 | 3 | 5 | 31/12/2016 | HienNguyen | Complete
| 58 | Research Static view | Architect |  | 30/12/2016 | 4 | 5 | 31/12/2016 | TaiNguyen | Complete
| 59 | Research Dynamic view | Architect |  | 30/12/2016 | 6 | 4 | 31/12/2016 | MinhDoan | Complete
| 60 | Research Physical view | Architect |  | 30/12/2016 | 4 | 3 | 31/12/2016 | KhoiNguyen | Complete
| 61 | Research Static view | Architect |  | 30/12/2016 | 5 | 4 | 31/12/2016 | HaiTran | Complete
| 62 | Research Dynamic view | Architect |  | 30/12/2016 | 3 | 4 | 31/12/2016 | XuanThaiHien | Complete
| 63 | Draw Physical view draft | Architect |  | 30/12/2016 | 3 | 4 | 31/12/2016 | HienNguyen | Complete
| 64 | Draw Static view draft | Architect |  | 30/12/2016 | 4 | 3 | 31/12/2016 | TaiNguyen | Complete
| 65 | Draw Dynamic view draft | Architect |  | 30/12/2016 | 5 | 4 | 31/12/2016 | MinhDoan | Complete
| 66 | Writting rationel | Architect |  | 30/12/2016 | 3 | 1 | 31/12/2016 | HaiTran | Complete
| 67 | Draw Physical view draft | Architect |  | 30/12/2016 | 3 | 4 | 31/12/2016 | KhoiNguyen | Complete
14 | 1 | Team Meeting | Meeting |  | 2017-02-01 | 2 | 2 | 2017-02-01 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 2017-02-01 | 2 | 2 | 2017-02-01 | HienNguyen | Complete
| 3 | Team Meeting | Meeting |  | 2017-02-01 | 2 | 2 | 2017-02-01 | KhoiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 2017-02-01 | 2 | 2 | 2017-02-01 | TaiNguyen | Complete
| 5 | Team Meeting | Meeting |  | 2017-02-01 | 2 | 2 | 2017-02-01 | MinhDoan | Complete
| 6 | Team Meeting | Meeting |  | 2017-02-01 | 2 | 2 | 2017-02-01 | XuanThaiHien | Complete
| 7 | Draw Physical View | Architect |  | 2017-02-01 | 4 | 7 | 2017-02-01 | HienNguyen | Pending
| 8 | Draw Static View Level 1 | Architect |  | 2017-02-01 | 5 | 6 | 2017-02-01 | HaiTran | Pending
| 9 | Draw Static View Level 2 | Architect |  | 2017-02-01 | 6 | 5 | 2017-02-01 | KhoiNguyen | Pending
| 10 | Draw Static View Level 2 | Architect |  | 2017-02-01 | 4 | 3 | 2017-02-01 | HaiTran | Pending
| 11 | Draw Dynamic View Level 1 | Architect |  | 2017-02-01 | 7 | 9 | 2017-02-01 | TaiNguyen | Pending
| 12 | Draw Dynamic View Level 2 | Architect |  | 2017-02-01 | 6 | 8 | 2017-02-01 | MinhDoan | Pending
| 13 | Mentor Meeting | Meeting |  | 2017-03-01 | 3 | 2 | 2017-03-01 | HaiTran | Complete
| 14 | Mentor Meeting | Meeting |  | 2017-03-01 | 3 | 2 | 2017-03-01 | HienNguyen | Complete
| 15 | Mentor Meeting | Meeting |  | 2017-03-01 | 3 | 2 | 2017-03-01 | KhoiNguyen | Complete
| 16 | Mentor Meeting | Meeting |  | 2017-03-01 | 3 | 2 | 2017-03-01 | TaiNguyen | Complete
| 17 | Mentor Meeting | Meeting |  | 2017-03-01 | 3 | 2 | 2017-03-01 | MinhDoan | Complete
| 18 | Mentor Meeting | Meeting |  | 2017-03-01 | 3 | 2 | 2017-03-01 | XuanThaiHien | Complete
| 19 | Training Technical | Training |  | 2017-03-01 | 2 | 2 | 2017-03-01 | HaiTran | Complete
| 20 | Training Technical | Training |  | 2017-03-01 | 2 | 2 | 2017-03-01 | HienNguyen | Complete
| 21 | Training Technical | Training |  | 2017-03-01 | 2 | 2 | 2017-03-01 | KhoiNguyen | Complete
| 22 | Training Technical | Training |  | 2017-03-01 | 2 | 2 | 2017-03-01 | TaiNguyen | Complete
| 23 | Training Technical | Training |  | 2017-03-01 | 2 | 2 | 2017-03-01 | MinhDoan | Complete
| 24 | Draw Physical View | Architect |  | 2017-03-01 | 3 | 3 | 2017-03-01 | HienNguyen
| 25 | Draw Static View Level 1 | Architect |  | 2017-03-01 | 4 | 3 | 2017-03-01 | HaiTran
| 26 | Draw Static View Level 2 | Architect |  | 2017-03-01 | 5 | 4 | 2017-03-01 | KhoiNguyen
| 27 | Draw Static View Level 2 | Architect |  | 2017-03-01 | 4 | 4 | 2017-03-01 | HaiTran
| 28 | Draw Dynamic View Level 1 | Architect |  | 2017-03-01 | 3 | 4 | 2017-03-01 | TaiNguyen
| 29 | Draw Dynamic View Level 2 | Architect |  | 2017-03-01 | 5 | 3 | 2017-03-01 | MinhDoan
| 30 | Review Physical View | Architect |  | 2017-04-01 | 2 | 2 | 2017-04-01 | HaiTran
| 31 | Review Physical View | Architect |  | 2017-04-01 | 2 | 2 | 2017-04-01 | HienNguyen
| 32 | Review Physical View | Architect |  | 2017-04-01 | 2 | 2 | 2017-04-01 | MinhDoan
| 33 | Review Physical View | Architect |  | 2017-04-01 | 2 | 2 | 2017-04-01 | TaiNguyen
| 34 | Review Physical View | Architect |  | 2017-04-01 | 2 | 2 | 2017-04-01 | KhoiNguyen
| 35 | Review Physical View | Architect |  | 2017-04-01 | 2 | 2 | 2017-04-01 | XuanThaiHien
| 36 | Review Static View | Architect |  | 2017-04-01 | 3 | 2 | 2017-04-01 | HaiTran
| 37 | Review Static View | Architect |  | 2017-04-01 | 2 | 2 | 2017-04-01 | HienNguyen
| 38 | Review Static View | Architect |  | 2017-04-01 | 3 | 2 | 2017-04-01 | MinhDoan
| 39 | Review Static View | Architect |  | 2017-04-01 | 4 | 2 | 2017-04-01 | TaiNguyen
| 40 | Review Static View | Architect |  | 2017-04-01 | 2 | 2 | 2017-04-01 | KhoiNguyen
| 41 | Review Static View | Architect |  | 2017-04-01 | 2 | 2 | 2017-04-01 | XuanThaiHien
| 42 | Review Dynamic | Architect |  | 2017-04-01 | 2 | 3 | 2017-05-01 | HaiTran
| 43 | Review Dynamic | Architect |  | 2017-04-01 | 3 | 3 | 2017-05-01 | HienNguyen
| 44 | Review Dynamic | Architect |  | 2017-04-01 | 2 | 3 | 2017-05-01 | MinhDoan
| 45 | Review Dynamic | Architect |  | 2017-04-01 | 2 | 3 | 2017-05-01 | TaiNguyen
| 46 | Review Dynamic | Architect |  | 2017-04-01 | 3 | 3 | 2017-05-01 | KhoiNguyen
| 47 | Review Dynamic | Architect |  | 2017-04-01 | 2 | 3 | 2017-05-01 | XuanThaiHien
| 48 | Mentor Meeting | Meeting |  | 2017-05-01 | 2 | 4 | 2017-05-01 | HaiTran
| 49 | Mentor Meeting | Meeting |  | 2017-05-01 | 2 | 4 | 2017-05-01 | HienNguyen
| 50 | Mentor Meeting | Meeting |  | 2017-05-01 | 2 | 4 | 2017-05-01 | MinhDoan
| 51 | Mentor Meeting | Meeting |  | 2017-05-01 | 2 | 4 | 2017-05-01 | TaiNguyen
| 52 | Mentor Meeting | Meeting |  | 2017-05-01 | 2 | 4 | 2017-05-01 | KhoiNguyen
| 53 | Mentor Meeting | Meeting |  | 2017-05-01 | 2 | 4 | 2017-05-01 | XuanThaiHien
| 54 | Research pattern 3 layers in dynamic view | Architect |  | 2017-06-01 | 3 | 2 | 2017-07-01 | HienNguyen | Complete
| 55 | Research pattern 3 layers in dynamic view | Architect |  | 2017-06-01 | 2 | 1 | 2017-07-01 | KhoiNguyen | Complete
| 56 | Update Dynamic View | Architect |  | 2017-06-01 | 2 | 4 | 2017-07-01 | KhoiNguyen | Pending
| 57 | Update Static View | Architect |  | 2017-06-01 | 2 | 3 | 2017-07-01 | TaiNguyen | Pending
| 58 | Research tactics for physical view | Architect |  | 2017-06-01 | 1 | 2 | 2017-07-01 | MinhDoan | Complete
| 59 | Research tactics for quality attributes | Architect |  | 2017-06-01 | 3 | 4 | 2017-07-01 | MinhDoan | Pending
| 60 | Apply tactics performance, usability for physical view | Architect |  | 2017-06-01 | 1 | 2 | 2017-07-01 | XuanThaiHien | Pending
| 61 | Tactics performance, usability for physical view | Architect |  | 2017-06-01 | 5 | 2 | 2017-07-01 | XuanThaiHien | Pending
| 62 | Update Physical View | Architect |  | 2017-06-01 | 2 | 2.5 | 2017-07-01 | TaiNguyen | Complete
15 | 1 | Team Meeting | Meeting |  | 2017-09-01 | 2 | 2 | 2017-09-01 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 2017-09-01 | 2 | 2 | 2017-09-01 | HienNguyen | Complete
| 3 | Team Meeting | Meeting |  | 2017-09-01 | 2 | 2 | 2017-09-01 | KhoiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 2017-09-01 | 2 | 2 | 2017-09-01 | MinhDoan | Complete
| 5 | Team Meeting | Meeting |  | 2017-09-01 | 2 | 2 | 2017-09-01 | TaiNguyen | Complete
| 6 | Update Physical View | Architect |  | 2017-09-01 | 3 | 4 | 2017-09-01 | HienNguyen | Complete
| 7 | Update Static View | Architect |  | 2017-09-01 | 6 | 5 | 2017-09-01 | HaiTran | Complete
| 8 | Update Dynamic View | Architect |  | 2017-09-01 | 4 | 6 | 2017-09-01 | KhoiNguyen | Complete
| 9 | Customer Meeting | Meeting |  | 2017-10-01 | 2 | 2 | 2017-10-01 | HaiTran | Complete
| 10 | Customer Meeting | Meeting |  | 2017-10-01 | 2 | 2 | 2017-10-01 | HienNguyen | Complete
| 11 | Customer Meeting | Meeting |  | 2017-10-01 | 2 | 2 | 2017-10-01 | KhoiNguyen | Complete
| 12 | Customer Meeting | Meeting |  | 2017-10-01 | 2 | 2 | 2017-10-01 | MinhDoan | Complete
| 13 | Customer Meeting | Meeting |  | 2017-10-01 | 2 | 2 | 2017-10-01 | TaiNguyen | Complete
| 14 | Training Technical | Training |  | 2017-10-01 | 2 | 2 | 2017-10-01 | HaiTran | Complete
| 15 | Training Technical | Training |  | 2017-10-01 | 2 | 2 | 2017-10-01 | HienNguyen | Complete
| 16 | Training Technical | Training |  | 2017-10-01 | 2 | 2 | 2017-10-01 | KhoiNguyen | Complete
| 17 | Training Technical | Training |  | 2017-10-01 | 2 | 2 | 2017-10-01 | MinhDoan | Complete
| 18 | Training Technical | Training |  | 2017-10-01 | 2 | 2 | 2017-10-01 | TaiNguyen | Complete
| 19 | Research Redis Technology | Architect |  | 2017-11-01 | 3 | 4 | 2017-11-01 | HienNguyen | Complete
| 20 | Research Elastic Technology | Architect |  | 2017-11-01 | 3 | 3 | 2017-11-01 | TaiNguyen | Complete
| 21 | Research MongoDB | Architect |  | 2017-11-01 | 3 | 2 | 2017-11-01 | HaiTran | Complete
| 22 | Update Physical View | Architect |  | 2017-11-01 | 3 | 4 | 2017-11-01 | KhoiNguyen | Complete
| 23 | Update Static View | Architect |  | 2017-11-01 | 3 | 3 | 2017-11-01 | TaiNguyen | Complete
| 24 | Update Dynamic View | Architect |  | 2017-11-01 | 4 | 5 | 2017-11-01 | HaiTran | Complete
| 25 | Mentor Meeting | Meeting |  | 2017-12-01 | 2 | 4 | 2017-12-01 | HaiTran | Complete
| 26 | Mentor Meeting | Meeting |  | 2017-12-01 | 2 | 4 | 2017-12-01 | HienNguyen | Complete
| 27 | Mentor Meeting | Meeting |  | 2017-12-01 | 2 | 4 | 2017-12-01 | KhoiNguyen | Complete
| 28 | Mentor Meeting | Meeting |  | 2017-12-01 | 2 | 4 | 2017-12-01 | MinhDoan | Complete
| 29 | Mentor Meeting | Meeting |  | 2017-12-01 | 2 | 4 | 2017-12-01 | TaiNguyen | Complete
| 30 | Mentor Meeting | Meeting |  | 2017-12-01 | 2 | 4 | 2017-12-01 | XuanThaiHien | Complete
16 | 1 | Team Meeting | Meeting | Detailed Design | 16/1/2017 | 2 | 2 | 16/1/2017 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 16/1/2017 | 2 | 2 | 16/1/2017 | HienNguyen | Complete
| 3 | Team Meeting | Meeting |  | 16/1/2017 | 2 | 2 | 16/1/2017 | MinhDoan | Complete
| 4 | Team Meeting | Meeting |  | 16/1/2017 | 2 | 2 | 16/1/2017 | TaiNguyen | Complete
| 5 | Team Meeting | Meeting |  | 16/1/2017 | 2 | 2 | 16/1/2017 | KhoiNguyen | Complete
| 6 | Design Database | Detail design |  | 16/1/2017 | 2 | 3 | 16/1/2017 | HaiTran | Complete
| 7 | Design Database | Detail design |  | 16/1/2017 | 3 | 3 | 16/1/2017 | TaiNguyen | Complete
| 8 | Draw class diagram function "Manage Account" | Detail design |  | 16/1/2017 | 5 | 6 | 16/1/2017 | TaiNguyen | Complete
| 9 | Draw class diagram function "Manage News" | Detail design |  | 16/1/2017 | 4 | 5 | 16/1/2017 | HienNguyen | Complete
| 10 | Draw class diagram function "Manage FAQ" | Detail design |  | 16/1/2017 | 7 | 6 | 16/1/2017 | MinhDoan | Complete
| 11 | Draw class diagram function "Manage Homepage" | Detail design |  | 16/1/2017 | 6 | 5 | 16/1/2017 | KhoiNguyen | Complete
| 12 | Draw class diagram function "Manage Categories" | Detail design |  | 16/1/2017 | 5 | 7 | 16/1/2017 | TaiNguyen | Complete
| 13 | Draw class diagram function "Manage Banners" | Detail design |  | 16/1/2017 | 3 | 3 | 16/1/2017 | HienNguyen | Complete
| 14 | Training Technical | Training |  | 17/1/2017 | 2 | 2 | 17/1/2017 | HaiTran | Complete
| 15 | Training Technical | Training |  | 17/1/2017 | 2 | 2 | 17/1/2017 | HienNguyen | Complete
| 16 | Training Technical | Training |  | 17/1/2017 | 2 | 2 | 17/1/2017 | MinhDoan | Complete
| 17 | Training Technical | Training |  | 17/1/2017 | 2 | 2 | 17/1/2017 | TaiNguyen | Complete
| 18 | Training Technical | Training |  | 17/1/2017 | 2 | 2 | 17/1/2017 | KhoiNguyen | Complete
| 19 | Draw class diagram function "Manage Popups" | Detail design |  | 17/1/2017 | 7 | 6 | 17/1/2017 | MinhDoan | Complete
| 20 | Draw class diagram function "Manage Languages" | Detail design |  | 17/1/2017 | 2 | 1 | 17/1/2017 | TaiNguyen | Complete
| 21 | Draw class diagram function "Manage Examination" | Detail design |  | 17/1/2017 | 4 | 6 | 17/1/2017 | XuanThaiHien | Not implemented
| 22 | Draw sequence diagram function "Manage Account" | Detail design |  | 17/1/2017 | 5 | 7 | 17/1/2017 | HaiTran | Complete
| 23 | Draw sequence diagram function "Manage News" | Detail design |  | 17/1/2017 | 5 | 6 | 17/1/2017 | KhoiNguyen | Complete
| 24 | Draw sequence diagram function "Manage Categories" | Detail design |  | 18/1/2017 | 7 | 8 | 18/1/2017 | MinhDoan | Complete
| 25 | Draw sequence diagram function "Manage Banners" | Detail design |  | 18/1/2017 | 2 | 4 | 18/1/2017 | HienNguyen | Complete
| 26 | Draw sequence diagram function "Manage Popups" | Detail design |  | 18/1/2017 | 7 | 8 | 18/1/2017 | MinhDoan | Complete
| 27 | Draw sequence diagram function "Manage Homepage" | Detail design |  | 18/1/2017 | 4 | 5 | 18/1/2017 | HaiTran | Complete
| 28 | Draw sequence diagram function "Manage Examination" | Detail design |  | 18/1/2017 | 3 | 4 | 18/1/2017 | HienNguyen | Complete
| 29 | Draw sequence diagram function "Manage Language" | Detail design |  | 18/1/2017 | 2 | 1 | 18/1/2017 | XuanThaiHien | Complete
| 30 | Draw sequence diagram function "Manage FAQ" | Detail design |  | 18/1/2017 | 2 | 3 | 18/1/2017 | XuanThaiHien | Complete
| 31 | Mentor Meeting | Meeting |  | 19/1/2017 | 2 | 3 | 19/1/2017 | TaiNguyen | Complete
| 32 | Mentor Meeting | Meeting |  | 19/1/2017 | 2 | 3 | 19/1/2017 | XuanThaiHien | Complete
| 33 | Mentor Meeting | Meeting |  | 19/1/2017 | 2 | 3 | 19/1/2017 | HaiTran | Complete
| 34 | Mentor Meeting | Meeting |  | 19/1/2017 | 2 | 3 | 19/1/2017 | KhoiNguyen | Complete
| 35 | Mentor Meeting | Meeting |  | 19/1/2017 | 2 | 3 | 19/1/2017 | MinhDoan | Complete
| 36 | Mentor Meeting | Meeting |  | 19/1/2017 | 2 | 3 | 19/1/2017 | HienNguyen | Complete
| 37 | Review class diagram function "Manage Account" | Detail design |  | 19/1/2017 | 3 | 2 | 19/1/2017 | HienNguyen | Complete
| 38 | Review class diagram function "Manage Account" | Detail design |  | 19/1/2017 | 2 | 2 | 19/1/2017 | TaiNguyen | Complete
| 39 | Review class diagram function "Manage News" | Detail design |  | 19/1/2017 | 3 | 2 | 19/1/2017 | HaiTran | Complete
| 40 | Review class diagram function "Manage News" | Detail design |  | 19/1/2017 | 2 | 2 | 19/1/2017 | KhoiNguyen | Complete
| 41 | Review class diagram function "Manage FAQ" | Detail design |  | 19/1/2017 | 2 | 1 | 19/1/2017 | MinhDoan | Complete
| 42 | Review class diagram function "Manage FAQ" | Detail design |  | 19/1/2017 | 1 | 1 | 19/1/2017 | XuanThaiHien | Complete
| 43 | Review class diagram function "Manage Homepage" | Detail design |  | 19/1/2017 | 2 | 2 | 19/1/2017 | MinhDoan | Complete
| 44 | Review class diagram function "Manage Categories" | Detail design |  | 19/1/2017 | 2 | 3 | 19/1/2017 | TaiNguyen | Complete
| 45 | Review class diagram function "Manage Categories" | Detail design |  | 19/1/2017 | 3 | 3 | 19/1/2017 | HienNguyen | Complete
| 46 | Review class diagram function "Manage Banners" | Detail design |  | 19/1/2017 | 2 | 2 | 19/1/2017 | HaiTran | Complete
| 47 | Review class diagram function "Manage Popups" | Detail design |  | 20/1/2017 | 2 | 2 | 20/1/2017 | HaiTran | Complete
| 48 | Review class diagram function "Manage Languages" | Detail design |  | 20/1/2017 | 1 | 1 | 20/1/2017 | XuanThaiHien | Complete
| 49 | Review class diagram function "Manage Examination" | Detail design |  | 20/1/2017 | 2 | 3 | 20/1/2017 | MinhDoan | Complete
| 50 | Review sequence diagram function "Manage Account" | Detail design |  | 20/1/2017 | 4 | 5 | 20/1/2017 | TaiNguyen | Complete
| 51 | Review sequence diagram function "Manage Account" | Detail design |  | 20/1/2017 | 3 | 4 | 20/1/2017 | HienNguyen | Complete
| 52 | Review sequence diagram function "Manage News" | Detail design |  | 20/1/2017 | 4 | 4 | 20/1/2017 | TaiNguyen | Complete
| 53 | Review sequence diagram function "Manage News" | Detail design |  | 20/1/2017 | 3 | 4 | 20/1/2017 | HaiTran | Complete
| 54 | Review sequence diagram function "Manage Categories" | Detail design |  | 20/1/2017 | 2 | 3 | 20/1/2017 | MinhDoan | Complete
| 55 | Review sequence diagram function "Manage Categories" | Detail design |  | 20/1/2017 | 2 | 2 | 20/1/2017 | KhoiNguyen | Complete
| 56 | Review sequence diagram function "Manage Banners" | Detail design |  | 20/1/2017 | 2 | 2 | 20/1/2017 | TaiNguyen | Complete
| 57 | Review sequence diagram function "Manage Popups" | Detail design |  | 20/1/2017 | 2 | 2 | 20/1/2017 | HienNguyen | Complete
| 58 | Review sequence diagram function "Manage Homepage" | Detail design |  | 20/1/2017 | 3 | 2 | 20/1/2017 | MinhDoan | Complete
| 59 | Review sequence diagram function "Manage Examination" | Detail design |  | 20/1/2017 | 3 | 3 | 20/1/2017 | XuanThaiHien | Complete
| 60 | Review sequence diagram function "Manage Language" | Detail design |  | 20/1/2017 | 2 | 1 | 20/1/2017 | KhoiNguyen | Complete
| 61 | Review sequence diagram function "Manage FAQ" | Detail design |  | 20/1/2017 | 2 | 2 | 20/1/2017 | XuanThaiHien | Complete
| 62 | Review class diagram function "Manage Account" | Detail design |  | 21/1/2017 | 5 | 5 | 21/1/2017 | TaiNguyen | Complete
| 63 | Update sequence diagram function "Manage Account" | Detail design |  | 21/1/2017 | 4 | 6 | 21/1/2017 | HienNguyen | Complete
| 64 | Update sequence diagram function "Manage News" | Detail design |  | 21/1/2017 | 5 | 7 | 21/1/2017 | HaiTran | Complete
| 65 | Update sequence diagram function "Manage Categories" | Detail design |  | 21/1/2017 | 4 | 4 | 21/1/2017 | KhoiNguyen | Complete
| 66 | Collect diagram into document | Detail design |  | 21/1/2017 | 2 | 2 | 21/1/2017 | MinhDoan | Complete
17 | 1 | Team Meeting | Meeting | Implement | 23/1/2017 | 2 | 2 | 23/1/2017 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 23/1/2017 | 2 | 2 | 23/1/2017 | TaiNguyen | Complete
| 3 | Team Meeting | Meeting |  | 23/1/2017 | 2 | 2 | 23/1/2017 | HienNguyen | Complete
| 4 | Team Meeting | Meeting |  | 23/1/2017 | 2 | 2 | 23/1/2017 | MinhDoan | Complete
| 5 | Team Meeting | Meeting |  | 23/1/2017 | 2 | 2 | 23/1/2017 | KhoiNguyen | Complete
| 6 | Mentor Meeting | Meeting |  | 23/1/2017 | 3 | 4 | 23/1/2017 | HaiTran | Complete
| 7 | Mentor Meeting | Meeting |  | 23/1/2017 | 3 | 4 | 23/1/2017 | TaiNguyen | Complete
| 8 | Mentor Meeting | Meeting |  | 23/1/2017 | 3 | 4 | 23/1/2017 | HienNguyen | Complete
| 9 | Mentor Meeting | Meeting |  | 23/1/2017 | 3 | 4 | 23/1/2017 | MinhDoan | Complete
| 10 | Mentor Meeting | Meeting |  | 23/1/2017 | 3 | 4 | 23/1/2017 | KhoiNguyen | Complete
| 11 | Training Technical | Training |  | 24/1/2017 | 2 | 2 | 24/1/2017 | HaiTran | Complete
| 12 | Training Technical | Training |  | 24/1/2017 | 2 | 2 | 24/1/2017 | TaiNguyen | Complete
| 13 | Training Technical | Training |  | 24/1/2017 | 2 | 2 | 24/1/2017 | HienNguyen | Complete
| 14 | Training Technical | Training |  | 24/1/2017 | 2 | 2 | 24/1/2017 | MinhDoan | Complete
| 15 | Training Technical | Training |  | 24/1/2017 | 2 | 2 | 24/1/2017 | KhoiNguyen | Complete
| 16 | Create "Account" table | Detail design |  | 24/1/2017 | 4 | 3 | 24/1/2017 | TaiNguyen | Complete
| 17 | Create "News" table | Detail design |  | 24/1/2017 | 3 | 3 | 24/1/2017 | HienNguyen | Complete
| 18 | Create "Categories" table | Detail design |  | 24/1/2017 | 3 | 3 | 24/1/2017 | HaiTran | Complete
| 19 | Create "Banners" table | Detail design |  | 24/1/2017 | 4 | 2 | 24/1/2017 | KhoiNguyen | Complete
| 20 | Create "Popups" table | Detail design |  | 24/1/2017 | 4 | 2 | 24/1/2017 | KhoiNguyen | Complete
| 21 | Create "Examination" table | Detail design |  | 24/1/2017 | 3 | 3 | 24/1/2017 | MinhDoan | Complete
| 22 | Create "FAQ" table | Detail design |  | 24/1/2017 | 3 | 3 | 24/1/2017 | MinhDoan | Complete
| 23 | Create "Homepage" table | Detail design |  | 24/1/2017 | 3 | 3 | 24/1/2017 | HaiTran | Complete
| 24 | Create "Language" table | Detail design |  | 24/1/2017 | 2 | 1 | 24/1/2017 | HienNguyen | Complete
| 25 | Implement Create Account Function | Programming |  | 24/1/2017 | 3 | 4 | 24/1/2017 | HaiTran | Complete
| 26 | Implement Create Account Function | Programming |  | 24/1/2017 | 4 | 4 | 24/1/2017 | HienNguyen | Complete
| 27 | Implement Create Account Function | Programming |  | 24/1/2017 | 5 | 4 | 24/1/2017 | KhoiNguyen | Complete
| 28 | Implement Create Account Function | Programming |  | 24/1/2017 | 4 | 3 | 24/1/2017 | TaiNguyen | Complete
| 29 | Implement Create Account Function | Programming |  | 24/1/2017 | 3 |  | 24/1/2017 | MinhDoan | Not implemented
| 30 | Implement Create Account Function | Programming |  | 24/1/2017 | 4 |  | 24/1/2017 | XuanThaiHien | Not implemented
| 31 | Implement server | Programming |  | 25/1/2017 | 20 | 22 | 27/1/2017 | HaiTran | Complete
| 32 | Implement server | Programming |  | 25/1/2017 | 24 | 16 | 27/1/2017 | KhoiNguyen | Complete
| 33 | Implement connection from Redis to MongoDB | Programming |  | 25/1/2017 | 15 | 16 | 26/1/2017 | HienNguyen | Complete
| 34 | Implement connection from ElasticSearch to MongoDB | Programming |  | 25/1/2017 | 22 | 25 | 27/1/2016 | TaiNguyen | Complete
| 35 | Implement connection to MongoDB | Programming |  | 25/1/2017 | 14 | 16 | 27/1/2016 | MinhDoan | Complete
| 36 | Implement Login Function | Programming |  | 27/1/2017 | 7 | 8 | 28/1/2017 | HaiTran | Complete
| 37 | Implement Login Function | Programming |  | 27/1/2017 | 6 | 6 | 28/1/2017 | HienNguyen | Complete
| 38 | Implement Login Function | Programming |  | 27/1/2017 | 6 | 7 | 28/1/2017 | TaiNguyen | Complete
| 39 | Implement Login Function | Programming |  | 27/1/2017 | 7 | 7 | 28/1/2017 | KhoiNguyen | Complete
| 40 | Implement Login Function | Programming |  | 27/1/2017 | 6 |  | 28/1/2017 | MinhDoan | Not implemented
| 41 | Implement Login Function | Programming |  | 27/1/2017 | 7 |  | 28/1/2017 | XuanThaiHien | Not implemented
18 | TET HOLIDAY
19 | 1 | Team Meeting | Meeting | Implement | 2017-06-02 | 2 | 2 | 2017-06-02 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 2017-06-02 | 2 | 2 | 2017-06-02 | MinhDoan | Complete
| 3 | Team Meeting | Meeting |  | 2017-06-02 | 2 | 2 | 2017-06-02 | KhoiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 2017-06-02 | 2 | 2 | 2017-06-02 | TaiNguyen | Complete
| 5 | Team Meeting | Meeting |  | 2017-06-02 | 2 | 2 | 2017-06-02 | HienNguyen | Complete
| 6 | Mentor Meeting | Meeting |  | 2017-06-02 | 2 | 4 | 2017-06-02 | HaiTran | Complete
| 7 | Mentor Meeting | Meeting |  | 2017-06-02 | 2 | 4 | 2017-06-02 | MinhDoan | Complete
| 8 | Mentor Meeting | Meeting |  | 2017-06-02 | 2 | 4 | 2017-06-02 | KhoiNguyen | Complete
| 9 | Mentor Meeting | Meeting |  | 2017-06-02 | 2 | 4 | 2017-06-02 | TaiNguyen | Complete
| 10 | Mentor Meeting | Meeting |  | 2017-06-02 | 2 | 4 | 2017-06-02 | HienNguyen | Complete
| 11 | Mentor Meeting | Meeting |  | 2017-06-02 | 2 | 4 | 2017-06-02 | XuanThaiHien | Complete
| 12 | Training Technical | Training |  | 2017-07-02 | 2 | 2 | 2017-07-02 | HaiTran | Complete
| 13 | Training Technical | Training |  | 2017-07-02 | 2 | 2 | 2017-07-02 | MinhDoan | Complete
| 14 | Training Technical | Training |  | 2017-07-02 | 2 | 2 | 2017-07-02 | KhoiNguyen | Complete
| 15 | Training Technical | Training |  | 2017-07-02 | 2 | 2 | 2017-07-02 | TaiNguyen | Complete
| 16 | Training Technical | Training |  | 2017-07-02 | 2 | 2 | 2017-07-02 | HienNguyen | Complete
| 17 | Training Technical | Training |  | 2017-07-02 | 2 | 2 | 2017-07-02 | XuanThaiHien | Complete
| 18 | Implement "Show Detail Account" function | Programming |  | 2017-07-02 | 14 | 15 | 2017-08-02 | MinhDoan | Complete
| 19 | Implement "View List Account" function | Programming |  | 2017-07-02 | 10 | 12 | 2017-08-02 | KhoiNguyen | Complete
| 20 | Implement "Edit Account" function | Programming |  | 2017-07-02 | 16 | 16 | 2017-08-02 | HienNguyen | Complete
| 21 | Implement "Activate Account" function | Programming |  | 2017-07-02 | 17 | 16 | 2017-08-02 | TaiNguyen | Complete
| 22 | Implement"Deactivate Account" function | Programming |  | 2017-07-02 | 16 | 15 | 2017-08-02 | HaiTran | Complete
| 23 | Demo "Login" function | Programming |  | 2017-09-02 | 2 | 1 | 2017-09-02 | HienNguyen | Complete
| 24 | Demo "Login" function | Programming |  | 2017-09-02 | 2 | 1 | 2017-09-02 | HaiTran | Complete
| 25 | Demo "Login" function | Programming |  | 2017-09-02 | 2 | 1 | 2017-09-02 | MinhDoan | Complete
| 26 | Demo "Login" function | Programming |  | 2017-09-02 | 2 | 1 | 2017-09-02 | TaiNguyen | Complete
| 27 | Demo "Login" function | Programming |  | 2017-09-02 | 2 | 1 | 2017-09-02 | KhoiNguyen | Complete
| 28 | Demo "Create Account" function | Programming |  | 2017-09-02 | 1 | 1 | 2017-09-02 | HienNguyen | Complete
| 29 | Demo "Create Account" function | Programming |  | 2017-09-02 | 1 | 1 | 2017-09-02 | MinhDoan | Complete
| 30 | Demo "Create Account" function | Programming |  | 2017-09-02 | 1 | 1 | 2017-09-02 | KhoiNguyen | Complete
| 31 | Demo "Create Account" function | Programming |  | 2017-09-02 | 1 | 1 | 2017-09-02 | HaiTran | Complete
| 32 | Demo "Create Account" function | Programming |  | 2017-09-02 | 1 | 1 | 2017-09-02 | TaiNguyen | Complete
| 33 | Demo " Show Account" function | Programming |  | 2017-09-02 | 1 | 1 | 2017-09-02 | KhoiNguyen | Complete
| 34 | Demo " Show Account" function | Programming |  | 2017-09-02 | 1 | 1 | 2017-09-02 | HaiTran | Complete
| 35 | Demo " Show Account" function | Programming |  | 2017-09-02 | 1 | 1 | 2017-09-02 | HienNguyen | Complete
| 36 | Demo " Show Account" function | Programming |  | 2017-09-02 | 1 | 1 | 2017-09-02 | TaiNguyen | Complete
| 37 | Demo " Show Account" function | Programming |  | 2017-09-02 | 1 | 1 | 2017-09-02 | MinhDoan | Complete
| 38 | Demo "Edit Account" function | Programming |  | 2017-09-02 | 2 | 2 | 2017-09-02 | HaiTran | Complete
| 39 | Demo "Edit Account" function | Programming |  | 2017-09-02 | 2 | 2 | 2017-09-02 | HienNguyen | Complete
| 40 | Demo "Edit Account" function | Programming |  | 2017-09-02 | 2 | 2 | 2017-09-02 | TaiNguyen | Complete
| 41 | Demo "Edit Account" function | Programming |  | 2017-09-02 | 2 | 2 | 2017-09-02 | MinhDoan | Complete
| 42 | Demo "Edit Account" function | Programming |  | 2017-09-02 | 2 | 2 | 2017-09-02 | KhoiNguyen | Complete
| 43 | Implement "Create draft" function | Programming |  | 2017-10-01 | 15 | 16 | 2017-11-01 | HaiTran | Pending
| 44 | Implement "View News" function | Programming |  | 2017-10-01 | 14 | 14 | 2017-11-01 | HienNguyen | Pending
| 45 | Implement "Transfer News" function | Programming |  | 2017-10-01 | 18 | 20 | 2017-11-01 | TaiNguyen | Pending
| 46 | Implement"Edit News" function | Programming |  | 2017-10-01 | 15 | 17 | 2017-11-01 | KhoiNguyen | Pending
20 | 1 | Team Meeting | Meeting |  | 13/2/2017 | 2 | 2 | 13/2/2017 | HienNguyen | Complete
| 2 | Team Meeting | Meeting |  | 13/2/2017 | 2 | 2 | 13/2/2017 | HaiTran | Complete
| 3 | Team Meeting | Meeting |  | 13/2/2017 | 2 | 2 | 13/2/2017 | MinhDoan | Complete
| 4 | Team Meeting | Meeting |  | 13/2/2017 | 2 | 2 | 13/2/2017 | KhoiNguyen | Complete
| 5 | Team Meeting | Meeting |  | 13/2/2017 | 2 | 2 | 13/2/2017 | TaiNguyen | Complete
| 6 | Implement "Create draft" function | Programming |  | 13/2/2017 | 12 | 14 | 14/2/2017 | HaiTran | Complete
| 7 | Implement "Transfer News" function | Programming |  | 13/2/2017 | 15 | 16 | 14/2/2017 | TaiNguyen | Complete
| 8 | Implement"Edit News" function | Programming |  | 13/2/2017 | 14 | 16 | 14/2/2017 | KhoiNguyen | Complete
| 9 | Demo "View News" function | Programming |  | 13/2/2017 | 2 | 2 | 13/2/2017 | HienNguyen | Complete
| 10 | Demo "View News" function | Programming |  | 13/2/2017 | 2 | 2 | 13/2/2017 | HaiTran | Complete
| 11 | Demo "View News" function | Programming |  | 13/2/2017 | 2 | 2 | 13/2/2017 | MinhDoan | Complete
| 12 | Demo "View News" function | Programming |  | 13/2/2017 | 2 | 2 | 13/2/2017 | KhoiNguyen | Complete
| 13 | Demo "View News" function | Programming |  | 13/2/2017 | 2 | 2 | 13/2/2017 | TaiNguyen | Complete
| 14 | Training Technical | Training |  | 14/2/2017 | 2 | 2 | 14/2/2017 | HaiTran | Complete
| 15 | Training Technical | Training |  | 14/2/2017 | 2 | 2 | 14/2/2017 | TaiNguyen | Complete
| 16 | Training Technical | Training |  | 14/2/2017 | 2 | 2 | 14/2/2017 | MinhDoan | Complete
| 17 | Training Technical | Training |  | 14/2/2017 | 2 | 2 | 14/2/2017 | KhoiNguyen | Complete
| 18 | Training Technical | Training |  | 14/2/2017 | 2 | 2 | 14/2/2017 | HienNguyen | Complete
| 19 | Demo "Create Draft" function | Programming |  | 14/2/2017 | 1 | 2 | 14/2/2017 | HaiTran | Complete
| 20 | Demo "Create Draft" function | Programming |  | 14/2/2017 | 1 | 2 | 14/2/2017 | MinhDoan | Complete
| 21 | Demo "Create Draft" function | Programming |  | 14/2/2017 | 1 | 2 | 14/2/2017 | TaiNguyen | Complete
| 22 | Demo "Create Draft" function | Programming |  | 14/2/2017 | 1 | 2 | 14/2/2017 | KhoiNguyen | Complete
| 23 | Demo "Create Draft" function | Programming |  | 14/2/2017 | 1 | 2 | 14/2/2017 | HienNguyen | Complete
| 24 | Demo "Edit News" function | Programming |  | 14/2/2017 | 1 | 3 | 14/2/2017 | KhoiNguyen | Complete
| 25 | Demo "Edit News" function | Programming |  | 14/2/2017 | 1 | 3 | 14/2/2017 | HaiTran | Complete
| 26 | Demo "Edit News" function | Programming |  | 14/2/2017 | 1 | 3 | 14/2/2017 | HienNguyen | Complete
| 27 | Demo "Edit News" function | Programming |  | 14/2/2017 | 1 | 3 | 14/2/2017 | TaiNguyen | Complete
| 28 | Demo "Edit News" function | Programming |  | 14/2/2017 | 1 | 3 | 14/2/2017 | MinhDoan | Complete
| 29 | Mentor Meeting | Meeting |  | 15/2/2017 | 2 | 4 | 15/2/2017 | HaiTran | Complete
| 30 | Mentor Meeting | Meeting |  | 15/2/2017 | 2 | 4 | 15/2/2017 | HienNguyen | Complete
| 31 | Mentor Meeting | Meeting |  | 15/2/2017 | 2 | 4 | 15/2/2017 | KhoiNguyen | Complete
| 32 | Mentor Meeting | Meeting |  | 15/2/2017 | 2 | 4 | 15/2/2017 | MinhDoan | Complete
| 33 | Mentor Meeting | Meeting |  | 15/2/2017 | 2 | 4 | 15/2/2017 | TaiNguyen | Complete
| 34 | Implement "Approve News" function | Programming |  | 16/2/2017 | 14 | 17 | 18/2/2017 | TaiNguyen | Pending
| 35 | Implement "Deactivate News" function | Programming |  | 16/2/2017 | 16 | 18 | 18/2/2017 | HienNguyen | Pending
| 36 | Implement "Sort News" function | Programming |  | 16/2/2017 | 16 | 17 | 18/2/2017 | HaiTran | Pending
| 37 | Implement "Search News" function | Programming |  | 16/2/2017 | 17 | 16 | 18/2/2017 | KhoiNguyen | Pending
21 | 1 | Team Meeting | Meeting |  | 20/2/2017 | 2 | 2 | 20/2/2017 | HienNguyen | Complete
| 2 | Team Meeting | Meeting |  | 20/2/2017 | 2 | 2 | 20/2/2017 | HaiTran | Complete
| 3 | Team Meeting | Meeting |  | 20/2/2017 | 2 | 2 | 20/2/2017 | KhoiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 20/2/2017 | 2 | 2 | 20/2/2017 | TaiNguyen | Complete
| 5 | Team Meeting | Meeting |  | 20/2/2017 | 2 | 2 | 20/2/2017 | MinhDoan | Complete
| 6 | Team Meeting | Meeting |  | 20/2/2017 | 2 | 2 | 20/2/2017 | XuanThaiHien | Complete
| 7 | Implement "Create draft" function on server | Programming |  | 20/2/2017 | 8 | 6 | 22/2/2017 | HienNguyen | Complete
| 8 | Implement "Create draft" function on server | Programming |  | 20/2/2017 | 8 | 6 | 22/2/2017 | KhoiNguyen | Complete
| 9 | Implement "Create draft" function on frontend | Programming |  | 20/2/2017 | 15 | 16 | 22/2/2017 | TaiNguyen | Complete
| 10 | Implement "Create draft" function on frontend | Programming |  | 20/2/2017 | 14 | 14 | 22/2/2017 | MinhDoan | Complete
| 11 | Implement "View News" function on server | Programming |  | 20/2/2017 | 16 | 16 | 22/2/2017 | HienNguyen | Complete
| 12 | Implement "View News" function on server | Programming |  | 20/2/2017 | 14 | 16 | 22/2/2017 | HaiTran | Complete
| 13 | Implement "View News" function on frontend for user | Programming |  | 20/2/2017 | 20 | 18 | 22/2/2017 | HaiTran | Complete
| 14 | Implement "View News" function on frontend for admin | Programming |  | 20/2/2017 | 18 | 15 | 22/2/2017 | TaiNguyen | Complete
| 15 | Training Technical | Training |  | 23/2/2017 | 2 | 2 | 23/2/2017 | HaiTran | Complete
| 16 | Training Technical | Training |  | 23/2/2017 | 2 | 2 | 23/2/2017 | HienNguyen | Complete
| 17 | Training Technical | Training |  | 23/2/2017 | 2 | 2 | 23/2/2017 | TaiNguyen | Complete
| 18 | Training Technical | Training |  | 23/2/2017 | 2 | 2 | 23/2/2017 | MinhDoan | Complete
| 19 | Training Technical | Training |  | 23/2/2017 | 2 | 2 | 23/2/2017 | KhoiNguyen | Complete
| 20 | Implement "Transfer News" function on server | Programming |  | 23/2/2017 | 6 | 7 | 24/2/2017 | HienNguyen | Complete
| 21 | Implement "Transfer News" function on frontend | Programming |  | 23/2/2017 | 8 | 7 | 24/2/2017 | TaiNguyen | Complete
| 22 | Implement "Transfer News" function on frontend | Programming |  | 23/2/2017 | 6 | 6 | 24/2/2017 | HaiTran | Complete
| 23 | Implement "Edit News" function on server | Programming |  | 23/2/2017 | 10 | 11 | 24/2/2017 | HienNguyen | Complete
| 24 | Implement "Edit News" function on server | Programming |  | 23/2/2017 | 5 | 7 | 24/2/2017 | KhoiNguyen | Complete
| 25 | Implement "Edit News"function on frontend | Programming |  | 23/2/2017 | 6 | 6 | 24/2/2017 | TaiNguyen | Complete
| 26 | Implement "Edit News"function on frontend | Programming |  | 23/2/2017 | 4 | 5 | 24/2/2017 | HaiTran | Complete
| 27 | Import data into database for function "Manage News" | Programming |  | 23/2/2017 | 3 | 4 | 24/2/2017 | MinhDoan | Complete
| 28 | Mentor Meeting | Meeting |  | 24/2/2017 | 2 | 3 | 24/2/2017 | HaiTran | Complete
| 29 | Mentor Meeting | Meeting |  | 24/2/2017 | 2 | 3 | 24/2/2017 | HienNguyen | Complete
| 30 | Mentor Meeting | Meeting |  | 24/2/2017 | 2 | 3 | 24/2/2017 | TaiNguyen | Complete
| 31 | Mentor Meeting | Meeting |  | 24/2/2017 | 2 | 3 | 24/2/2017 | MinhDoan | Complete
| 32 | Mentor Meeting | Meeting |  | 24/2/2017 | 2 | 3 | 24/2/2017 | KhoiNguyen | Complete
| 33 | Mentor Meeting | Meeting |  | 24/2/2017 | 2 | 3 | 24/2/2017 | XuanThaiHien | Complete
| 34 | Presentation EOMP2 | EOMP |  | 25/2/2017 | 2 | 2 | 25/2/2017 | HaiTran | Complete
| 35 | Presentation EOMP2 | EOMP |  | 25/2/2017 | 2 | 2 | 25/2/2017 | MinhDoan | Complete
| 36 | Presentation EOMP2 | EOMP |  | 25/2/2017 | 2 | 2 | 25/2/2017 | HienNguyen | Complete
| 37 | Presentation EOMP2 | EOMP |  | 25/2/2017 | 2 | 2 | 25/2/2017 | XuanThaiHien | Complete
| 38 | Presentation EOMP2 | EOMP |  | 25/2/2017 | 2 | 2 | 25/2/2017 | KhoiNguyen | Complete
| 39 | Presentation EOMP2 | EOMP |  | 25/2/2017 | 2 | 2 | 25/2/2017 | TaiNguyen | Complete
| 40 | Team Meeting | Meeting |  | 25/2/2017 | 1 | 1 | 25/2/2017 | HaiTran | Complete
| 41 | Team Meeting | Meeting |  | 25/2/2017 | 1 | 1 | 25/2/2017 | MinhDoan | Complete
| 42 | Team Meeting | Meeting |  | 25/2/2017 | 1 | 1 | 25/2/2017 | HienNguyen | Complete
| 43 | Team Meeting | Meeting |  | 25/2/2017 | 1 | 1 | 25/2/2017 | XuanThaiHien | Complete
| 44 | Team Meeting | Meeting |  | 25/2/2017 | 1 | 1 | 25/2/2017 | KhoiNguyen | Complete
| 45 | Team Meeting | Meeting |  | 25/2/2017 | 1 | 1 | 25/2/2017 | TaiNguyen | Complete
22 | 1 | Team Meeting | Meeting |  | 27/2/2017 | 2 | 2 | 27/2/2017 | HienNguyen | Complete
| 2 | Team Meeting | Meeting |  | 27/2/2017 | 2 | 2 | 27/2/2017 | HaiTran | Complete
| 3 | Team Meeting | Meeting |  | 27/2/2017 | 2 | 2 | 27/2/2017 | TaiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 27/2/2017 | 2 | 2 | 27/2/2017 | KhoiNguyen | Complete
| 5 | Team Meeting | Meeting |  | 27/2/2017 | 2 | 2 | 27/2/2017 | MinhDoan | Complete
| 6 | Implement "Approve News" function on server | Programming |  | 27/2/2017 | 13 | 15 | 28/2/2017 | HienNguyen | Complete
| 7 | Implement "Approve News" function on server | Programming |  | 27/2/2017 | 10 | 13 | 28/2/2017 | HaiTran | Complete
| 8 | Implement "Approve News" function on frontend | Programming |  | 27/2/2017 | 12 | 13 | 28/2/2017 | TaiNguyen | Complete
| 9 | Implement "Approve News" function on frontend | Programming |  | 27/2/2017 | 12 | 10 | 28/2/2017 | KhoiNguyen | Complete
| 10 | Implement "Deactive News" function on server | Programming |  | 27/2/2017 | 8 | 7 | 28/2/2017 | HienNguyen | Complete
| 11 | Implement "Deactive News" function on server | Programming |  | 27/2/2017 | 7 | 5 | 28/2/2017 | KhoiNguyen | Complete
| 12 | Implement "Deactive News" function on frontend | Programming |  | 27/2/2017 | 8 | 5 | 28/2/2017 | HaiTran | Complete
| 13 | Training Technical | Training |  | 2017-01-03 | 2 | 2 | 2017-01-03 | HienNguyen | Complete
| 14 | Training Technical | Training |  | 2017-01-03 | 2 | 2 | 2017-01-03 | HaiTran | Complete
| 15 | Training Technical | Training |  | 2017-01-03 | 2 | 2 | 2017-01-03 | TaiNguyen | Complete
| 16 | Training Technical | Training |  | 2017-01-03 | 2 | 2 | 2017-01-03 | KhoiNguyen | Complete
| 17 | Training Technical | Training |  | 2017-01-03 | 2 | 2 | 2017-01-03 | MinhDoan | Complete
| 18 | Implement "Search News" function on server | Programming |  | 2017-01-03 | 15 | 16 | 2017-03-03 | HienNguyen | Complete
| 19 | Implement "Search News" function on server | Programming |  | 2017-01-03 | 15 | 14 | 2017-03-03 | HaiTran | Complete
| 20 | Implement "Search News" function on frontend | Programming |  | 2017-01-03 | 17 | 18 | 2017-03-03 | TaiNguyen | Complete
| 21 | Implement "Sort News" function on server | Programming |  | 2017-01-03 | 14 | 16 | 2017-03-03 | HienNguyen | Complete
| 22 | Implement "Sort News" function on server | Programming |  | 2017-01-03 | 12 | 10 | 2017-03-03 | KhoiNguyen | Complete
| 23 | Implement "Sort News" function on frontend | Programming |  | 2017-01-03 | 13 | 13 | 2017-03-03 | TaiNguyen | Complete
| 24 | Mentor Meeting | Meeting |  | 2017-03-03 | 2 | 2 | 2017-03-03 | HaiTran | Complete
| 25 | Mentor Meeting | Meeting |  | 2017-03-03 | 2 | 2 | 2017-03-03 | HienNguyen | Complete
| 26 | Mentor Meeting | Meeting |  | 2017-03-03 | 2 | 2 | 2017-03-03 | TaiNguyen | Complete
| 27 | Mentor Meeting | Meeting |  | 2017-03-03 | 2 | 2 | 2017-03-03 | MinhDoan | Complete
| 28 | Mentor Meeting | Meeting |  | 2017-03-03 | 2 | 2 | 2017-03-03 | KhoiNguyen | Complete
| 29 | Implement "View categories" function on server | Programming |  | 2017-04-03 | 10 | 10 | 2017-04-03 | HienNguyen | Complete
| 30 | Implement "View categories" function on server | Programming |  | 2017-04-03 | 10 | 12 | 2017-04-03 | HaiTran | Complete
| 31 | Import data into database for function "Manage Categories" | Programming |  | 2017-04-03 | 6 | 5 | 2017-04-03 | KhoiNguyen | Complete
| 32 | Implement "View categories" function on frontend | Programming |  | 2017-04-03 | 10 | 10 | 2017-04-03 | TaiNguyen | Complete
| 33 | Implement "View categories" function on frontend | Programming |  | 2017-04-03 | 9 | 8 | 2017-04-03 | HaiTran | Complete
23 | 1 | Team Meeting | Meeting |  | 2017-06-03 | 2 | 2 | 2017-06-03 | HienNguyen | Complete
| 2 | Team Meeting | Meeting |  | 2017-06-03 | 2 | 2 | 2017-06-03 | HaiTran | Complete
| 3 | Team Meeting | Meeting |  | 2017-06-03 | 2 | 2 | 2017-06-03 | TaiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 2017-06-03 | 2 | 2 | 2017-06-03 | KhoiNguyen | Complete
| 5 | Team Meeting | Meeting |  | 2017-06-03 | 2 | 2 | 2017-06-03 | MinhDoan | Complete
| 6 | Implement "Add categories" function on server | Programming |  | 2017-06-03 | 15 | 16 | 2017-07-03 | HienNguyen | Complete
| 7 | Implement "Add categories" function on server | Programming |  | 2017-06-03 | 12 | 14 | 2017-07-03 | HaiTran | Complete
| 8 | Implement "Add categories" function on frontend | Programming |  | 2017-06-03 | 10 | 12 | 2017-07-03 | TaiNguyen | Complete
| 9 | Implement "Add categories" function on frontend | Programming |  | 2017-06-03 | 8 | 6 | 2017-07-03 | KhoiNguyen | Complete
| 10 | Implement frontend News on ionic 2 | Programming |  | 2017-06-03 | 20 |  | 2017-08-03 | MinhDoan | Not implemented
| 11 | Implement frontend News on ionic 2 | Programming |  | 2017-06-03 | 20 |  | 2017-08-03 | XuanThaiHien | Not implemented
| 12 | Training Technical | Training |  | 2017-07-03 | 2 | 2 | 2017-07-03 | HaiTran | Complete
| 13 | Training Technical | Training |  | 2017-07-03 | 2 | 2 | 2017-07-03 | HienNguyen | Complete
| 14 | Training Technical | Training |  | 2017-07-03 | 2 | 2 | 2017-07-03 | TaiNguyen | Complete
| 15 | Training Technical | Training |  | 2017-07-03 | 2 | 2 | 2017-07-03 | KhoiNguyen | Complete
| 16 | Training Technical | Training |  | 2017-07-03 | 2 | 2 | 2017-07-03 | MinhDoan | Complete
| 17 | Implement "Edit categories" function on server | Programming |  | 2017-07-03 | 20 | 22 | 2017-09-03 | HienNguyen | Complete
| 18 | Implement "Edit categories" function on server | Programming |  | 2017-07-03 | 18 | 14 | 2017-09-03 | HaiTran | Complete
| 19 | Implement "Edit categories" function on frontend | Programming |  | 2017-07-03 | 17 | 19 | 2017-09-03 | TaiNguyen | Complete
| 20 | Implement "Edit categories" function on frontend | Programming |  | 2017-07-03 | 15 | 16 | 2017-09-03 | MinhDoan | Complete
| 21 | Mentor Meeting | Meeting |  | 2017-10-03 | 2 | 3 | 2017-10-03 | HaiTran | Complete
| 22 | Mentor Meeting | Meeting |  | 2017-10-03 | 2 | 3 | 2017-10-03 | HienNguyen | Complete
| 23 | Mentor Meeting | Meeting |  | 2017-10-03 | 2 | 3 | 2017-10-03 | TaiNguyen | Complete
| 24 | Mentor Meeting | Meeting |  | 2017-10-03 | 2 | 3 | 2017-10-03 | MinhDoan | Complete
| 25 | Mentor Meeting | Meeting |  | 2017-10-03 | 2 | 3 | 2017-10-03 | KhoiNguyen | Complete
| 26 | Mentor Meeting | Meeting |  | 2017-10-03 | 2 | 3 | 2017-10-03 | XuanThaiHien | Complete
| 27 | Implement "Delete categories" function on server | Programming |  | 2017-10-03 | 8 | 6 | 2017-11-03 | HienNguyen | Complete
| 28 | Implement "Delete categories" function on server | Programming |  | 2017-10-03 | 5 | 5 | 2017-11-03 | HaiTran | Complete
| 29 | Implement "Delete categories" function on frontend | Programming |  | 2017-10-03 | 6 | 6 | 2017-11-03 | TaiNguyen | Complete
| 30 | Implement "Create Banner" function on server | Programming |  | 2017-10-03 | 18 | 17 | 2017-11-03 | HienNguyen | Complete
| 31 | Implement "Create Banner" function on server | Programming |  | 2017-10-03 | 14 | 12 | 2017-11-03 | HaiTran | Complete
| 32 | Implement "Create Banner" function on frontend | Programming |  | 2017-10-03 | 18 | 18 | 2017-11-03 | TaiNguyen | Complete
| 33 | Implement "Create Banner" function on frontend | Programming |  | 2017-10-03 | 16 | 18 | 2017-11-03 | HaiTran | Complete
24 | 1 | Team Meeting | Meeting |  | 13/3/2017 | 2 | 2 | 13/3/2017 | HienNguyen | Complete
| 2 | Team Meeting | Meeting |  | 13/3/2017 | 2 | 2 | 13/3/2017 | HaiTran | Complete
| 3 | Team Meeting | Meeting |  | 13/3/2017 | 2 | 2 | 13/3/2017 | TaiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 13/3/2017 | 2 | 2 | 13/3/2017 | MinhDoan | Complete
| 5 | Team Meeting | Meeting |  | 13/3/2017 | 2 | 2 | 13/3/2017 | KhoiNguyen | Complete
| 6 | Implement "Arrange Banner" function on server | Programming |  | 13/3/2017 | 16 | 18 | 14/3/2017 | HienNguyen | Complete
| 7 | Implement "Arrange Banner" function on server | Programming |  | 13/3/2017 | 15 | 16 | 14/3/2017 | HaiTran | Complete
| 8 | Implement "Arrange Banner" function on frontend | Programming |  | 13/3/2017 | 14 | 15 | 14/3/2017 | TaiNguyen | Complete
| 9 | Training Technical | Trainirng |  | 14/3/2017 | 2 | 2 | 14/3/2017 | MinhDoan | Complete
| 10 | Training Technical | Trainirng |  | 14/3/2017 | 2 | 2 | 14/3/2017 | KhoiNguyen | Complete
| 11 | Training Technical | Trainirng |  | 14/3/2017 | 2 | 2 | 14/3/2017 | HienNguyen | Complete
| 12 | Training Technical | Trainirng |  | 14/3/2017 | 2 | 2 | 14/3/2017 | HaiTran | Complete
| 13 | Training Technical | Trainirng |  | 14/3/2017 | 2 | 2 | 14/3/2017 | TaiNguyen | Complete
| 14 | Implement "Create Popups" function on server | Programming |  | 14/3/2017 | 14 | 12 | 15/3/2017 | HienNguyen | Complete
| 15 | Implement "Create Popups" function on server | Programming |  | 14/3/2017 | 14 | 12 | 15/3/2017 | HaiTran | Complete
| 16 | Implement "Create Popups" function on frontend | Programming |  | 14/3/2017 | 12 | 12 | 15/3/2017 | TaiNguyen | Complete
| 17 | Implement "Arrange Popups" function on server | Programming |  | 15/3/2017 | 16 | 14 | 16/3/2017 | HienNguyen | Complete
| 18 | Implement "Arrange Popups" function on server | Programming |  | 15/3/2017 | 15 | 14 | 16/3/2017 | HaiTran | Complete
| 19 | Implement "Arrange Popups" function on frontend | Programming |  | 15/3/2017 | 12 | 15 | 16/3/2017 | TaiNguyen | Complete
| 20 | Create unit test for "News" function | Programming |  | 17/3/2017 | 9 | 7 | 17/3/2017 | KhoiNguyen | Complete
| 21 | Create unit test for "News" function | Programming |  | 17/3/2017 | 8 | 7 | 17/3/2017 | MinhDoan | Complete
| 22 | Research publish code to server | Programming |  | 17/3/2017 | 7 | 8 | 17/3/2017 | HienNguyen | Pending
| 23 | Research publish code to server | Programming |  | 17/3/2017 | 7 | 8 | 17/3/2017 | HaiTran | Pending
| 24 | Research publish code to server | Programming |  | 17/3/2017 | 7 | 8 | 17/3/2017 | TaiNguyen | Pending
| 25 | Mentor Meeting | Meeting |  | 18/3/2017 | 2 | 3 | 18/3/2017 | HaiTran | Complete
| 26 | Mentor Meeting | Meeting |  | 18/3/2017 | 2 | 3 | 18/3/2017 | HienNguyen | Complete
| 27 | Mentor Meeting | Meeting |  | 18/3/2017 | 2 | 3 | 18/3/2017 | TaiNguyen | Complete
| 28 | Mentor Meeting | Meeting |  | 18/3/2017 | 2 | 3 | 18/3/2017 | MinhDoan | Complete
| 29 | Mentor Meeting | Meeting |  | 18/3/2017 | 2 | 3 | 18/3/2017 | KhoiNguyen | Complete
25 | 1 | Team Meeting | Meeting |  | 20/3/2017 | 2 | 2 | 20/3/2017 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 20/3/2017 | 2 | 2 | 20/3/2017 | TaiNguyen | Complete
| 3 | Team Meeting | Meeting |  | 20/3/2017 | 2 | 2 | 20/3/2017 | HienNguyen | Complete
| 4 | Implement "Import score" function | Programming |  | 20/3/2017 | 25 | 26 | 22/3/2017 | HienNguyen | Pending
| 5 | Implement "Import score" function | Programming |  | 20/3/2017 | 26 | 26 | 22/3/2017 | HaiTran | Pending
| 6 | Implement "Import score" function | Programming |  | 20/3/2017 | 25 | 26 | 22/3/2017 | TaiNguyen | Pending
| 7 | Training Technical | Programming |  | 21/3/2017 | 2 | 2 | 21/3/2017 | HaiTran | Complete
| 8 | Training Technical | Programming |  | 21/3/2017 | 2 | 2 | 21/3/2017 | HienNguyen | Complete
| 9 | Training Technical | Programming |  | 21/3/2017 | 2 | 2 | 21/3/2017 | TaiNguyen | Complete
| 10 | Mentor Meeting | Meeting |  | 23/3/2017 | 2 | 4 | 23/3/2017 | HaiTran | Complete
| 11 | Mentor Meeting | Meeting |  | 23/3/2017 | 2 | 4 | 23/3/2017 | HienNguyen | Complete
| 12 | Mentor Meeting | Meeting |  | 23/3/2017 | 2 | 4 | 23/3/2017 | TaiNguyen | Complete
| 13 | Mentor Meeting | Meeting |  | 23/3/2017 | 2 | 4 | 23/3/2017 | KhoiNguyen | Complete
| 14 | Test "News" function | Testing |  | 24/3/2017 | 15 | 16 | 25/3/2017 | KhoiNguyen | Complete
| 15 | Test "News" function | Testing |  | 24/3/2017 | 15 | 15 | 25/3/2017 | MinhDoan | Complete
26 | 1 | Team Meeting | Meeting |  | 27/3/2017 | 2 | 2 | 27/3/2017 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 27/3/2017 | 2 | 2 | 27/3/2017 | HienNguyen | Complete
| 3 | Team Meeting | Meeting |  | 27/3/2017 | 2 | 2 | 27/3/2017 | TaiNguyen | Complete
| 4 | Fix "News" function | Programming |  | 27/3/2017 | 15 | 14 | 28/3/2017 | HaiTran | Complete
| 5 | Fix "News" function | Programming |  | 27/3/2017 | 15 | 14 | 28/3/2017 | HienNguyen | Complete
| 6 | Fix "News" function | Programming |  | 27/3/2017 | 15 | 14 | 28/3/2017 | TaiNguyen | Complete
| 7 | Training Technical | Training |  | 28/3/2017 | 2 | 2 | 28/3/2017 | HaiTran | Complete
| 8 | Training Technical | Training |  | 28/3/2017 | 2 | 2 | 28/3/2017 | TaiNguyen | Complete
| 9 | Training Technical | Training |  | 28/3/2017 | 2 | 2 | 28/3/2017 | HienNguyen | Complete
| 10 | Re-test "News" function | Testing |  | 28/3/2017 | 6 | 6 | 28/3/2017 | MinhDoan | Complete
| 11 | Re-test "News" function | Testing |  | 28/3/2017 | 7 | 6 | 28/3/2017 | KhoiNguyen | Complete
| 12 | Create unit test for "Category" function | Testing |  | 29/3/2017 | 17 | 16 | 30/3/2017 | MinhDoan | Complete
| 13 | Create unit test for "Category" function | Testing |  | 29/3/2017 | 18 | 16 | 30/3/2017 | KhoiNguyen | Complete
| 14 | Implement "Import score" function | Programming |  | 30/3/2017 | 15 | 15 | 31/3/2017 | TaiNguyen | Complete
| 15 | Implement "Import score" function | Programming |  | 30/3/2017 | 16 | 15 | 31/3/2017 | HienNguyen | Complete
| 16 | Implement "Import score" function | Programming |  | 30/3/2017 | 16 | 15 | 31/3/2017 | HaiTran | Complete
| 17 | Test "Category" function | Testing |  | 2017-01-04 | 8 | 7 | 2017-01-04 | KhoiNguyen | Complete
| 18 | Test "Category" function | Testing |  | 2017-01-04 | 7 | 7 | 2017-01-04 | MinhDoan | Complete
| 19 | Fix "Category" function | Programming |  | 2017-01-04 | 8 | 7 | 2017-01-04 | TaiNguyen | Complete
| 20 | Fix "Category" function | Programming |  | 2017-01-04 | 8 | 8 | 2017-01-04 | HaiTran | Complete
| 21 | Fix "Category" function | Programming |  | 2017-01-04 | 8 | 7 | 2017-01-04 | HienNguyen | Complete
| 22 | Mentor Meeting | Meeting |  | 2017-01-04 | 2 | 3 | 2017-01-04 | HaiTran | Complete
| 23 | Mentor Meeting | Meeting |  | 2017-01-04 | 2 | 3 | 2017-01-04 | HienNguyen | Complete
| 24 | Mentor Meeting | Meeting |  | 2017-01-04 | 2 | 3 | 2017-01-04 | TaiNguyen | Complete
| 25 | Mentor Meeting | Meeting |  | 2017-01-04 | 2 | 3 | 2017-01-04 | MinhDoan | Complete
| 26 | Mentor Meeting | Meeting |  | 2017-01-04 | 2 | 3 | 2017-01-04 | KhoiNguyen | Complete
27 | 1 | Team Meeting | Meeting |  | 2017-03-04 | 2 | 2 | 2017-03-04 | TaiNguyen | Complete
| 2 | Team Meeting | Meeting |  | 2017-03-04 | 2 | 2 | 2017-03-04 | HienNguyen | Complete
| 3 | Team Meeting | Meeting |  | 2017-03-04 | 2 | 2 | 2017-03-04 | HaiTran | Complete
| 4 | Re-test "Category" function | Testing |  | 2017-03-04 | 6 | 7 | 2017-03-04 | MinhDoan | Complete
| 5 | Re-test "Category" function | Testing |  | 2017-03-04 | 7 | 7 | 2017-03-04 | KhoiNguyen | Complete
| 6 | Create unit test "Account" function | Testing |  | 2017-04-04 | 8 | 7 | 2017-04-04 | KhoiNguyen | Complete
| 7 | Create unit test "Account" function | Testing |  | 2017-04-04 | 8 | 6 | 2017-04-04 | MinhDoan | Complete
| 8 | Training Technical | Training |  | 2017-04-04 | 2 | 2 | 2017-04-04 | TaiNguyen | Complete
| 9 | Training Technical | Training |  | 2017-04-04 | 2 | 2 | 2017-04-04 | HienNguyen | Complete
| 10 | Training Technical | Training |  | 2017-04-04 | 2 | 2 | 2017-04-04 | HaiTran | Complete
| 11 | Implement "FAQ" function on server | Programming |  | 2017-05-04 | 18 | 18 | 2017-06-04 | HienNguyen | Complete
| 12 | Implement "FAQ" function on front-end | Programming |  | 2017-05-04 | 17 | 18 | 2017-06-04 | HaiTran | Complete
| 13 | Implement "FAQ" function on CMS | Programming |  | 2017-05-04 | 17 | 18 | 2017-06-04 | TaiNguyen | Complete
| 14 | Test "Account" function | Testing |  | 2017-06-04 | 6 | 7 | 2017-06-04 | KhoiNguyen | Complete
| 15 | Test "Account" function | Testing |  | 2017-06-04 | 7 | 7 | 2017-06-04 | MinhDoan | Complete
| 16 | Fix "Account" function | Programming |  | 2017-07-04 | 5 | 6 | 2017-07-04 | TaiNguyen | Complete
| 17 | Fix "Account" function | Programming |  | 2017-07-04 | 6 | 6 | 2017-07-04 | HaiTran | Complete
| 18 | Fix "Account" function | Programming |  | 2017-07-04 | 6 | 6 | 2017-07-04 | HienNguyen | Complete
| 19 | Mentor Meeting | Meeting |  | 2017-08-04 | 2 | 3 | 2017-08-04 | KhoiNguyen | Complete
| 20 | Mentor Meeting | Meeting |  | 2017-08-04 | 2 | 3 | 2017-08-04 | MinhDoan | Complete
| 21 | Mentor Meeting | Meeting |  | 2017-08-04 | 2 | 3 | 2017-08-04 | TaiNguyen | Complete
| 22 | Mentor Meeting | Meeting |  | 2017-08-04 | 2 | 3 | 2017-08-04 | HaiTran | Complete
| 23 | Mentor Meeting | Meeting |  | 2017-08-04 | 2 | 3 | 2017-08-04 | HienNguyen | Complete
28 | 1 | Team Meeting | Meeting |  | 2017-10-04 | 2 | 2 | 2017-10-04 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 2017-10-04 | 2 | 2 | 2017-10-04 | HienNguyen | Complete
| 3 | Team Meeting | Meeting |  | 2017-10-04 | 2 | 2 | 2017-10-04 | TaiNguyen | Complete
| 4 | Create unit test "Banner" function | Testing |  | 2017-10-04 | 8 | 7 | 2017-11-04 | KhoiNguyen | Complete
| 5 | Create unit test "Banner" function | Testing |  | 2017-10-04 | 7 | 7 | 2017-11-04 | MinhDoan | Complete
| 6 | Training Technical | Training |  | 2017-11-04 | 2 | 2 | 2017-11-04 | TaiNguyen | Complete
| 7 | Training Technical | Training |  | 2017-11-04 | 2 | 2 | 2017-11-04 | HaiTran | Complete
| 8 | Training Technical | Training |  | 2017-11-04 | 2 | 2 | 2017-11-04 | HienNguyen | Complete
| 9 | Re-test "Account" function | Testing |  | 2017-11-04 | 3 | 4 | 2017-11-04 | MinhDoan | Complete
| 10 | Re-test "Account" function | Testing |  | 2017-11-04 | 3 | 3 | 2017-11-04 | KhoiNguyen | Complete
| 11 | Test "Banner" function | Testing |  | 2017-12-04 | 6 | 7 | 2017-12-04 | MinhDoan | Complete
| 12 | Test "Banner" function | Testing |  | 2017-12-04 | 7 | 7 | 2017-12-04 | KhoiNguyen | Complete
| 13 | Fix "Banner" function | Programming |  | 13/4/2017 | 6 | 8 | 13/4/2017 | HienNguyen | Complete
| 14 | Fix "Banner" function | Programming |  | 13/4/2017 | 7 | 7 | 13/4/2017 | HaiTran | Complete
| 15 | Fix "Banner" function | Programming |  | 13/4/2017 | 6 | 7 | 13/4/2017 | TaiNguyen | Complete
| 16 | Create unit test "Import score" function | Testing |  | 14/4/2017 | 6 | 5 | 14/4/2017 | KhoiNguyen | Complete
| 17 | Create unit test "Import score" function | Testing |  | 14/4/2017 | 6 | 6 | 14/4/2017 | MinhDoan | Complete
| 18 | Re-test "Banner" function | Testing |  | 15/4/2017 | 4 | 5 | 15/4/2017 | KhoiNguyen | Complete
| 19 | Mentor Meeting | Meeting |  | 15/4/2017 | 2 | 3 | 15/4/2017 | KhoiNguyen | Complete
| 20 | Mentor Meeting | Meeting |  | 15/4/2017 | 2 | 3 | 15/4/2017 | TaiNguyen | Complete
| 21 | Mentor Meeting | Meeting |  | 15/4/2017 | 2 | 3 | 15/4/2017 | HienNguyen | Complete
| 22 | Mentor Meeting | Meeting |  | 15/4/2017 | 2 | 3 | 15/4/2017 | HaiTran | Complete
29 | 1 | Team Meeting | Meeting |  | 17/4/2017 | 2 | 2 | 17/4/2017 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 17/4/2017 | 2 | 2 | 17/4/2017 | HienNguyen | Complete
| 2 | Team Meeting | Meeting |  | 17/4/2017 | 2 | 2 | 17/4/2017 | TaiNguyen | Complete
| 3 | Test "Import score" function | Testing |  | 17/4/2017 | 5 | 6 | 17/4/2017 | KhoiNguyen | Complete
| 4 | Test "Import score" function | Testing |  | 17/4/2017 | 6 | 6 | 17/4/2017 | MinhDoan | Complete
| 5 | Fix " Import score" function | Programming |  | 17/4/2017 | 7 | 7 | 18/4/2017 | TaiNguyen | Complete
| 6 | Fix " Import score" function | Programming |  | 17/4/2017 | 7 | 8 | 18/4/2017 | HienNguyen | Complete
| 7 | Training Technical | Training |  | 18/4/2017 | 2 | 2 | 18/4/2017 | HienNguyen | Complete
| 8 | Training Technical | Training |  | 18/4/2017 | 2 | 2 | 18/4/2017 | HaiTran | Complete
| 9 | Training Technical | Training |  | 18/4/2017 | 2 | 2 | 18/4/2017 | TaiNguyen | Complete
| 10 | Re-test "Import score" function | Testing |  | 18/4/2017 | 5 | 6 | 18/4/2017 | KhoiNguyen | Complete
| 11 | Customer Meeting | Meeting |  | 19/4/2017 | 2 | 2 | 19/4/2017 | TaiNguyen | Complete
| 12 | Customer Meeting | Meeting |  | 19/4/2017 | 2 | 2 | 19/4/2017 | KhoiNguyen | Complete
| 13 | Customer Meeting | Meeting |  | 19/4/2017 | 2 | 2 | 19/4/2017 | HaiTran | Complete
| 14 | Customer Meeting | Meeting |  | 19/4/2017 | 2 | 2 | 19/4/2017 | HienNguyen | Complete
| 15 | Design UX | Programming |  | 19/4/2017 | 5 | 6 | 19/4/2017 | TaiNguyen | Complete
| 16 | Design UX | Programming |  | 19/4/2017 | 6 | 6 | 19/4/2017 | HaiTran | Complete
| 17 | Mentor Meeting | Meeting |  | 20/4/2017 | 2 | 2 | 20/4/2017 | HaiTran | Complete
| 18 | Mentor Meeting | Meeting |  | 20/4/2017 | 2 | 2 | 20/4/2017 | TaiNguyen | Complete
| 19 | Mentor Meeting | Meeting |  | 20/4/2017 | 2 | 2 | 20/4/2017 | HienNguyen | Complete
| 20 | Mentor Meeting | Meeting |  | 20/4/2017 | 2 | 2 | 20/4/2017 | KhoiNguyen | Complete
| 21 | Modify "Planning" document | Planning |  | 20/4/2017 | 5 | 4 | 20/4/2017 | HaiTran | Complete
| 22 | Modify "Requirement" document | Requirement |  | 20/4/2017 | 5 | 6 | 20/4/2017 | MinhDoan | Complete
| 23 | Create unit test "FAQ" function | Testing |  | 21/4/2017 | 7 | 7 | 21/4/2017 | MinhDoan | Complete
| 24 | Create unit test "FAQ" function | Testing |  | 21/4/2017 | 6 | 7 | 21/4/2017 | KhoiNguyen | Complete
| 25 | Mentor Meeting | Meeting |  | 22/4/2017 | 2 | 3 | 22/4/2017 | KhoiNguyen | Complete
| 26 | Mentor Meeting | Meeting |  | 22/4/2017 | 2 | 3 | 22/4/2017 | HaiTran | Complete
| 27 | Mentor Meeting | Meeting |  | 22/4/2017 | 2 | 3 | 22/4/2017 | HienNguyen | Complete
| 28 | Mentor Meeting | Meeting |  | 22/4/2017 | 2 | 3 | 22/4/2017 | TaiNguyen | Complete
| 29 | Test "FAQ" funtion | Testing |  | 22/4/2017 | 4 | 5 | 22/4/2017 | KhoiNguyen | Complete
| 30 | Test "FAQ" funtion | Testing |  | 22/4/2017 | 5 | 5 | 22/4/2017 | MinhDoan | Complete
| 31 | Fix "FAQ" function | Testing |  | 22/4/2017 | 5 | 6 | 22/4/2017 | HienNguyen | Complete
| 32 | Fix "FAQ" function | Testing |  | 22/4/2017 | 6 | 6 | 22/4/2017 | TaiNguyen | Complete
| 33 | Fix "FAQ" function | Testing |  | 22/4/2017 | 5 | 6 | 22/4/2017 | HaiTran | Complete
30 | 1 | Team Meeting | Meeting |  | 24/4/2017 | 2 | 2 | 24/4/2017 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 24/4/2017 | 2 | 2 | 24/4/2017 | TaiNguyen | Complete
| 3 | Team Meeting | Meeting |  | 24/4/2017 | 2 | 2 | 24/4/2017 | HienNguyen | Complete
| 4 | Team Meeting | Meeting |  | 24/4/2017 | 2 | 2 | 24/4/2017 | MinhDoan | Complete
| 5 | Team Meeting | Meeting |  | 24/4/2017 | 2 | 2 | 24/4/2017 | KhoiNguyen | Complete
| 6 | Re-test "FAQ" function | Testing |  | 24/4/2017 | 5 | 5 | 24/4/2017 | MinhDoan | Complete
| 7 | Re-test "FAQ" function | Testing |  | 24/4/2017 | 5 | 4 | 24/4/2017 | KhoiNguyen | Complete
| 8 | Technical training | Training |  | 25/4/2017 | 2 | 2 | 25/4/2017 | TaiNguyen | Complete
| 9 | Technical training | Training |  | 25/4/2017 | 2 | 2 | 25/4/2017 | HaiTran | Complete
| 10 | Technical training | Training |  | 25/4/2017 | 2 | 2 | 25/4/2017 | HienNguyen | Complete
| 11 | Integrate project to host server | Programming |  | 25/4/2017 | 4 | 4 | 25/4/2017 | HienNguyen | Complete
| 12 | Integrate project to host server | Programming |  | 25/4/2017 | 4 | 4 | 25/4/2017 | HaiTran | Complete
| 13 | Integrate project to host server | Programming |  | 25/4/2017 | 4 | 4 | 25/4/2017 | TaiNguyen | Complete
| 14 | Test release 1 | Testing |  | 25/4/2017 | 9 | 8 | 26/4/2017 | MinhDoan | Complete
| 15 | Test release 1 | Testing |  | 25/4/2017 | 8 | 7 | 26/4/2017 | KhoiNguyen | Complete
| 16 | Fix release 1 | Programming |  | 26/4/2017 | 4 | 3 | 26/4/2017 | TaiNguyen | Complete
| 17 | Fix release 1 | Programming |  | 26/4/2017 | 3 | 3 | 26/4/2017 | HaiTran | Complete
| 18 | Fix release 1 | Programming |  | 26/4/2017 | 3 | 3 | 26/4/2017 | HienNguyen | Complete
| 19 | Re-test release 1 | Testing |  | 27/4/2017 | 3 | 2 | 27/4/2017 | MinhDoan | Complete
| 20 | Re-test release 1 | Testing |  | 27/4/2017 | 3 | 2 | 27/4/2017 | KhoiNguyen | Complete
| 21 | Mentor Meeting | Meeting |  | 28/4/2017 | 3 | 2 | 28/4/2017 | HaiTran | Complete
| 22 | Mentor Meeting | Meeting |  | 28/4/2017 | 3 | 2 | 28/4/2017 | HienNguyen | Complete
| 23 | Mentor Meeting | Meeting |  | 28/4/2017 | 3 | 2 | 28/4/2017 | TaiNguyen | Complete
| 24 | Mentor Meeting | Meeting |  | 28/4/2017 | 3 | 2 | 28/4/2017 | MinhDoan | Complete
| 25 | Mentor Meeting | Meeting |  | 28/4/2017 | 3 | 2 | 28/4/2017 | KhoiNguyen | Complete
| 26 | Report test release 1 | Testing |  | 29/4/2017 | 3 | 3 | 29/4/2017 | MinhDoan | Complete
| 27 | Report test release 1 | Testing |  | 29/4/2017 | 3 | 3 | 29/4/2017 | KhoiNguyen | Complete
31 | 1 | Team Meeting | Meeting |  | 2017-03-05 | 2 | 2 | 2017-03-05 | HienNguyen | Complete
| 2 | Team Meeting | Meeting |  | 2017-03-05 | 2 | 2 | 2017-03-05 | HaiTran | Complete
| 3 | Team Meeting | Meeting |  | 2017-03-05 | 2 | 2 | 2017-03-05 | TaiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 2017-03-05 | 2 | 2 | 2017-03-05 | MinhDoan | Complete
| 5 | Team Meeting | Meeting |  | 2017-03-05 | 2 | 2 | 2017-03-05 | KhoiNguyen | Complete
| 6 | Test release 2 | Testing |  | 2017-03-05 | 4 | 5 | 2017-04-05 | KhoiNguyen | Complete
| 7 | Test release 2 | Testing |  | 2017-03-05 | 4 | 3 | 2017-04-05 | MinhDoan | Complete
| 8 | Fix release 2 | Programming |  | 2017-03-05 | 6 | 5 | 2017-04-05 | TaiNguyen | Complete
| 9 | Fix release 2 | Programming |  | 2017-03-05 | 5 | 5 | 2017-04-05 | HaiTran | Complete
| 10 | Fix release 2 | Programming |  | 2017-03-05 | 6 | 5 | 2017-04-05 | HienNguyen | Complete
| 11 | Mentor Meeting | Meeting |  | 2017-05-05 | 3 | 3 | 2017-05-05 | KhoiNguyen | Complete
| 12 | Mentor Meeting | Meeting |  | 2017-05-05 | 3 | 3 | 2017-05-05 | MinhDoan | Complete
| 13 | Mentor Meeting | Meeting |  | 2017-05-05 | 3 | 3 | 2017-05-05 | TaiNguyen | Complete
| 14 | Mentor Meeting | Meeting |  | 2017-05-05 | 3 | 3 | 2017-05-05 | HaiTran | Complete
| 15 | Mentor Meeting | Meeting |  | 2017-05-05 | 3 | 3 | 2017-05-05 | HienNguyen | Complete
| 16 | Re-test release 2 | Testing |  | 2017-05-05 | 3 | 3 | 2017-05-05 | MinhDoan | Complete
| 17 | Re-test release 2 | Testing |  | 2017-05-05 | 3 | 3 | 2017-05-05 | KhoiNguyen | Complete
| 18 | Report test release 2 | Testing |  | 2017-06-05 | 4 | 2 | 2017-06-05 | MinhDoan | Complete
| 19 | Report test release 2 | Testing |  | 2017-06-05 | 4 | 2 | 2017-06-05 | KhoiNguyen | Complete
32 | 1 | Team Meeting | Meeting |  | 2017-08-05 | 2 | 2 | 2017-08-05 | HaiTran | Complete
| 2 | Team Meeting | Meeting |  | 2017-08-05 | 2 | 2 | 2017-08-05 | HienNguyen | Complete
| 3 | Team Meeting | Meeting |  | 2017-08-05 | 2 | 2 | 2017-08-05 | MinhDoan | Complete
| 4 | Team Meeting | Meeting |  | 2017-08-05 | 2 | 2 | 2017-08-05 | KhoiNguyen | Complete
| 5 | Team Meeting | Meeting |  | 2017-08-05 | 2 | 2 | 2017-08-05 | TaiNguyen | Complete
| 6 | Test release 3 | Testing |  | 2017-08-05 | 4 | 3 | 2017-08-05 | KhoiNguyen | Complete
| 7 | Test release 3 | Testing |  | 2017-08-05 | 4 | 3 | 2017-08-05 | MinhDoan | Complete
| 8 | Technical training | Training |  | 2017-09-05 | 2 | 3 | 2017-09-05 | HaiTran | Complete
| 9 | Technical training | Training |  | 2017-09-05 | 2 | 3 | 2017-09-05 | HienNguyen | Complete
| 10 | Technical training | Training |  | 2017-09-05 | 2 | 3 | 2017-09-05 | TaiNguyen | Complete
| 11 | Fix release 3 | Programming |  | 2017-09-05 | 3 | 3 | 2017-09-05 | HaiTran | Complete
| 12 | Fix release 3 | Programming |  | 2017-09-05 | 3 | 3 | 2017-09-05 | HienNguyen | Complete
| 13 | Fix release 3 | Programming |  | 2017-09-05 | 3 | 3 | 2017-09-05 | TaiNguyen | Complete
| 14 | Report test release 3 | Testing |  | 2017-10-05 | 2 | 2 | 2017-10-05 | MinhDoan | Complete
| 15 | Report test release 3 | Testing |  | 2017-10-05 | 2 | 2 | 2017-10-05 | KhoiNguyen | Complete
| 16 | Change server save image | Programming |  | 2017-10-05 | 7 | 9 | 2017-11-05 | HienNguyen | Complete
| 17 | Config to connect image server | Programming |  | 2017-10-05 | 7 | 7 | 2017-11-05 | TaiNguyen | Complete
| 18 | Config to connect image server | Programming |  | 2017-10-05 | 6 | 7 | 2017-11-05 | HaiTran | Complete
| 19 | Test release 2 | Testing |  | 2017-11-05 | 3 | 2 | 2017-11-05 | MinhDoan | Complete
| 20 | Test release 2 | Testing |  | 2017-11-05 | 3 | 2 | 2017-11-05 | KhoiNguyen | Complete
| 21 | Report test release 2 | Testing |  | 2017-11-05 | 2 | 2 | 2017-11-05 | MinhDoan | Complete
| 22 | Report test release 2 | Testing |  | 2017-11-05 | 2 | 2 | 2017-11-05 | KhoiNguyen | Complete
| 23 | Mentor Meeting | Meeting |  | 2017-12-05 | 2 | 3 | 2017-12-05 | HaiTran | Complete
| 24 | Mentor Meeting | Meeting |  | 2017-12-05 | 2 | 3 | 2017-12-05 | TaiNguyen | Complete
| 25 | Mentor Meeting | Meeting |  | 2017-12-05 | 2 | 3 | 2017-12-05 | MinhDoan | Complete
| 26 | Mentor Meeting | Meeting |  | 2017-12-05 | 2 | 3 | 2017-12-05 | KhoiNguyen | Complete
| 27 | Mentor Meeting | Meeting |  | 2017-12-05 | 2 | 3 | 2017-12-05 | HienNguyen | Complete
33 | 1 | Team Meeting | Meeting |  | 15/5/2017 | 2 | 2 | 15/5/2017 | KhoiNguyen | Complete
| 2 | Team Meeting | Meeting |  | 15/5/2017 | 2 | 2 | 15/5/2017 | MinhDoan | Complete
| 3 | Team Meeting | Meeting |  | 15/5/2017 | 2 | 2 | 15/5/2017 | HaiTran | Complete
| 4 | Team Meeting | Meeting |  | 15/5/2017 | 2 | 2 | 15/5/2017 | TaiNguyen | Complete
| 5 | Team Meeting | Meeting |  | 15/5/2017 | 2 | 2 | 15/5/2017 | HienNguyen | Complete
| 6 | Change image server on editor | Programming |  | 15/5/2017 | 10 | 10 | 16/5/2017 | TaiNguyen | Complete
| 7 | Change image server on editor | Programming |  | 15/5/2017 | 11 | 10 | 16/5/2017 | HienNguyen | Complete
| 8 | Change image server on editor | Programming |  | 15/5/2017 | 11 | 10 | 16/5/2017 | HaiTran | Complete
| 9 | Test release 1 | Testing |  | 16/5/2017 | 6 | 6 | 16/5/2017 | MinhDoan | Complete
| 10 | Test release 1 | Testing |  | 16/5/2017 | 5 | 6 | 16/5/2017 | KhoiNguyen | Complete
| 11 | Report test release 1 | Testing |  | 17/5/2017 | 3 | 2 | 17/5/2017 | MinhDoan | Complete
| 12 | Report test release 1 | Testing |  | 17/5/2017 | 3 | 2 | 17/5/2017 | KhoiNguyen | Complete
| 13 | Modify "Architecture and design" document-physical view | Architect |  | 17/5/2017 | 12 | 13 | 18/5/2017 | HienNguyen | Complete
| 14 | Modify "Architecture and design" document-static view level 1 | Architect |  | 17/5/2017 | 12 | 14 | 18/5/2017 | MinhDoan | Complete
| 15 | Modify "Architecture and design" document-static view level 2 | Architect |  | 17/5/2017 | 13 | 14 | 18/5/2017 | KhoiNguyen | Complete
| 16 | Modify "Architecture and design" document-dynamic view level 1 | Architect |  | 17/5/2017 | 12 | 12 | 18/5/2017 | TaiNguyen | Complete
| 17 | Modify "Architecture and design" document-dynamic view level 2 | Architect |  | 17/5/2017 | 14 | 14 | 18/5/2017 | HaiTran | Complete
| 18 | Mentor Meeting | Meeting |  | 19/5/2017 | 2 | 2 | 19/5/2017 | HienNguyen | Complete
| 19 | Mentor Meeting | Meeting |  | 19/5/2017 | 2 | 2 | 19/5/2017 | MinhDoan | Complete
| 20 | Mentor Meeting | Meeting |  | 19/5/2017 | 2 | 2 | 19/5/2017 | KhoiNguyen | Complete
| 21 | Mentor Meeting | Meeting |  | 19/5/2017 | 2 | 2 | 19/5/2017 | TaiNguyen | Complete
| 22 | Mentor Meeting | Meeting |  | 19/5/2017 | 2 | 2 | 19/5/2017 | HaiTran | Complete
| 23 | Technical training | Training |  | 19/5/2017 | 2 | 2 | 19/5/2017 | TaiNguyen | Complete
| 24 | Technical training | Training |  | 19/5/2017 | 2 | 2 | 19/5/2017 | HaiTran | Complete
| 25 | Technical training | Training |  | 19/5/2017 | 2 | 2 | 19/5/2017 | HienNguyen | Complete
| 26 | Modify "Detail design" document | Detail design |  | 19/5/2017 | 9 | 7 | 20/5/2017 | HaiTran | Complete
| 27 | Modify "Detail design" document | Detail design |  | 19/5/2017 | 8 | 8 | 20/5/2017 | HienNguyen | Complete
| 28 | Modify "Detail design" document | Detail design |  | 19/5/2017 | 8 | 8 | 20/5/2017 | TaiNguyen | Complete
| 29 | Modify "Detail design" document | Detail design |  | 19/5/2017 | 9 | 8 | 20/5/2017 | MinhDoan | Complete
| 30 | Modify "Detail design" document | Detail design |  | 19/5/2017 | 8 | 7 | 20/5/2017 | KhoiNguyen | Complete
34 | 1 | Team Meeting | Meeting | Closing | 22/5/2017 | 2 | 2 | 22/5/2017 | TaiNguyen | Complete
| 2 | Team Meeting | Meeting |  | 22/5/2017 | 2 | 2 | 22/5/2017 | HienNguyen | Complete
| 3 | Team Meeting | Meeting |  | 22/5/2017 | 2 | 2 | 22/5/2017 | KhoiNguyen | Complete
| 4 | Team Meeting | Meeting |  | 22/5/2017 | 2 | 2 | 22/5/2017 | HaiTran | Complete
| 5 | Team Meeting | Meeting |  | 22/5/2017 | 2 | 2 | 22/5/2017 | MinhDoan | Complete
| 6 | Modify "Project plan" document | Planning |  | 22/5/2017 | 10 | 10 | 23/5/2017 | TaiNguyen | Complete
| 7 | Modify "Project charter" document | Planning |  | 22/5/2017 | 9 | 11 | 23/5/2017 | HienNguyen | Complete
| 8 | Modify "Milestone" document | Planning |  | 22/5/2017 | 10 | 10 | 23/5/2017 | KhoiNguyen | Complete
| 9 | Modify "Master Plan" document | Planning |  | 22/5/2017 | 9 | 10 | 23/5/2017 | MinhDoan | Complete
| 10 | Modify Schedule | Planning |  | 22/5/2017 | 12 | 13 | 23/5/2017 | HaiTran | Complete
| 11 | Customer Meeting | Meeting |  | 24/5/2017 | 1 | 3 | 24/5/2017 | TaiNguyen | Complete
| 12 | Customer Meeting | Meeting |  | 24/5/2017 | 1 | 3 | 24/5/2017 | HienNguyen | Complete
| 13 | Customer Meeting | Meeting |  | 24/5/2017 | 1 | 3 | 24/5/2017 | KhoiNguyen | Complete
| 14 | Customer Meeting | Meeting |  | 24/5/2017 | 1 | 3 | 24/5/2017 | MinhDoan | Complete
| 15 | Customer Meeting | Meeting |  | 24/5/2017 | 1 | 3 | 24/5/2017 | HaiTran | Complete
| 16 | Modify usecase description
| 17 | Modify Requirement plan
| 18 | Modify Test plan
| 19 | Modify Configuration plan
| 20 | Modify Measurement plan
| 21 | Modify Architecture and design plan
| 22 | Modify Change Management plan
| 23 | Modify Risk Management plan
24
25
26
27
28
29