## Sheet1
ASSIGN TASK
WEEK 01 | ID | TASK | TYPE | DATE ASSIGN | ESTIMATE | ACTUAL | DUE-DATE | ASSIGN TO | STATUS
WEEK 01
WEEK 01
WEEK 01 | [9 empty] | Complete
WEEK 01 | [9 empty] | Pending
WEEK 01 | [9 empty] | Not implemented
WEEK 01
WEEK 01
WEEK 01
WEEK 01
WEEK 14 | 1 | Review usecase description | Requirement | 2017-02-01 | 4 | 3 | 2017-03-01 | HaiTran | Complete
WEEK 14 | 2 | Draw static view detailed | Architect | 2017-03-01 | 2 | 1 | 2017-04-01 | HaiTran | Pending
WEEK 14 | 3 | Update requirement | Requirement | 2017-04-01 | 2 | 3 | 2017-06-01 | HaiTran | Complete
WEEK 14 | 4 | Update usecase | Requirement | 2017-06-01 | 3 | 3 | 2017-06-01 | HaiTran | Complete
WEEK 14 | 5 | Update dynamic view lv 0 | Architect | 2017-02-01 | 4 | 2 | 2017-03-01 | HienNguyen | Pending
WEEK 14 | 6 | Research pattern 3 layers in dynamic view | Architect | 2017-03-01 | 3 | 2 | 2017-04-01 | HienNguyen | Complete
WEEK 14 | 7 | Update usecase | Requirement | 2017-04-01 | 5 | 3 | 2017-06-01 | HienNguyen | Complete
WEEK 14 | 8 | Research pattern 3 layers in dynamic view | Architect | 2017-02-01 | 2 | 1 | 2017-03-01 | KhoiNguyen | Complete
WEEK 14 | 9 | Update dynamic view lv 0 | Architect | 2017-04-01 | 2 | 4 | 2017-04-01 | KhoiNguyen | Pending
WEEK 14 | 10 | Update document structure | Planning | 2017-05-01 | 3 | 3 | 2017-06-01 | KhoiNguyen | Complete
WEEK 14 | 11 | Draw static view | Architect | 2017-01-01 | 4 | 3 | 2017-03-01 | TaiNguyen | Complete
WEEK 14 | 12 | Update Static view | Architect | 2017-03-01 | 2 | 3 | 2017-04-01 | TaiNguyen | Pending
WEEK 14 | 13 | Update usecase | Requirement | 2017-04-01 | 2 | 2 | 2017-06-01 | TaiNguyen | Complete
WEEK 14 | 14 | Draw physical view | Architect | 2017-02-01 | 2 | 2.5 | 2017-03-01 | MinhDoan | Pending
WEEK 14 | 15 | Fix physical view | Architect | 2017-04-01 | 2 | 1 | 2017-04-01 | MinhDoan | Pending
WEEK 14 | 16 | Research tactics for quality attributes | Architect | 2017-05-01 | 3 | 4 | 2017-06-01 | MinhDoan | Complete
WEEK 14 | 17 | Update usecase | Requirement | 2017-06-01 | 2 | 1 | 2017-06-01 | MinhDoan | Complete
WEEK 14 | 18 | Research tactics for physical view | Architect | 2017-02-01 | 1 | 2 | 2017-03-01 | XuanThaiHien | Pending
WEEK 14 | 19 | Tactics performance, usability for physical view | Architect | 2017-03-01 | 5 | 2 | 2017-04-01 | XuanThaiHien | Complete
WEEK 14 | 20 | Draw physical view draft | Architect | 2017-02-01 | 4 | 2 | 2017-03-01 | XuanThaiHien | Pending
WEEK 14 | 21 | Apply tactics performance, usability for physical view | Architect | 2017-03-01 | 1 | 2 | 2017-04-01 | XuanThaiHien | Pending
WEEK 15 | 1 | Update Usecase | Requirement | 2017-09-01 | 5 | 4 | 2017-10-01 | HaiTran | Complete
WEEK 15 | 2 | Review Usecase descriptioin | Requirement | 2017-11-01 | 6 | 3 | 2017-11-01 | HaiTran | Complete
WEEK 15 | 3 | Update Process Requirement Development | Planning | 2017-12-01 | 3 | 2 | 2017-12-01 | HaiTran | Complete
WEEK 15 | 4 | Research Static view | Architect | 2017-12-01 | 3 | 2 | 2017-12-01 | HaiTran | Complete
WEEK 15 | 5 | Update usecase diagram | Requirement | 14/1/2017 | 2 | 1 | 15/1/2017 | HaiTran | Complete
WEEK 15 | 6 | Update Function list usecase | Requirement | 15/1/2017 | 1 | 1 | 15/1/2017 | HaiTran | Complete
WEEK 15 | 7 | Validate "Manage Banners","Manage Languages" usecase description | Requirement | 15/1/2017 | 1 | 1 | 15/1/2017 | HaiTran | Complete
WEEK 15 | 8 | Review Requirement | Requirement | 2017-10-01 | 3 | 2 | 2017-11-01 | HienNguyen | Complete
WEEK 15 | 9 | Update usecase description | Requirement | 2017-11-01 | 4 | 3 | 2017-11-01 | HienNguyen | Complete
WEEK 15 | 10 | Modify architecture and design process | Architect | 2017-11-01 | 2 | 3 | 2017-11-01 | HienNguyen | Complete
WEEK 15 | 11 | Modify dynamic view | Architect | 2017-12-01 | 2 | 1 | 2017-12-01 | HienNguyen | Complete
WEEK 15 | 12 | Research Redis engine | Architect | 15/1/2017 | 1 | 1 | 15/1/2017 | HienNguyen | Complete
WEEK 15 | 13 | Review requirement | Requirement | 2017-10-01 | 4 | 2 | 2017-10-01 | KhoiNguyen | Complete
WEEK 15 | 14 | Update usecase | Requirement | 2017-11-01 | 5 | 4 | 2017-12-01 | KhoiNguyen | Complete
WEEK 15 | 15 | Update configuration process | Planning | 2017-11-01 | 3 | 1 | 2017-11-01 | KhoiNguyen | Complete
WEEK 15 | 16 | Modify Dynamic view | Architect | 2017-12-01 | 3 | 2 | 2017-12-01 | KhoiNguyen | Pending
WEEK 15 | 17 | Validate SRS document | Requirement | 14/1/2017 | 2 | 2 | 14/1/2017 | KhoiNguyen | Complete
WEEK 15 | 18 | Validate "Manage Q&A","Manage Popups" usecase description | Requirement | 15/1/2017 | 2 | 3 | 15/1/2017 | KhoiNguyen | Complete
WEEK 15 | 19 | Review requirement | Requirement | 2017-10-01 | 4 | 2 | 2017-10-01 | TaiNguyen | Complete
WEEK 15 | 20 | Update usecase | Requirement | 2017-11-01 | 3 | 2 | 2017-11-01 | TaiNguyen | Complete
WEEK 15 | 21 | Update development process | Planning | 2017-11-01 | 3 | 2 | 2017-11-01 | TaiNguyen | Complete
WEEK 15 | 22 | Update measurement and control process | Planning | 2017-12-01 | 2 | 2 | 2017-12-01 | TaiNguyen | Complete
WEEK 15 | 23 | Modify static view | Architect | 2017-12-01 | 2 | 3 | 2017-12-01 | TaiNguyen | Pending
WEEK 15 | 24 | Research elastic search engine | Architect | 15/1/2017 | 1 | 3 | 15/1/2017 | TaiNguyen | Complete
WEEK 15 | 25 | Review requirement | Requirement | 2017-10-01 | 4 | 2 | 2017-10-01 | MinhDoan | Complete
WEEK 15 | 26 | Update usecase | Requirement | 2017-11-01 | 3 | 2 | 2017-11-01 | MinhDoan | Complete
WEEK 15 | 27 | Update change management process | Planning | 2017-11-01 | 3 | 4 | 2017-11-01 | MinhDoan | Complete
WEEK 15 | 28 | Modify Physical view | Architect | 2017-12-01 | 2 | 3 | 2017-12-01 | MinhDoan | Pending
WEEK 15 | 29 | Validate ConOps document | Requirement | 14/1/2017 | 2 | 1 | 14/1/2017 | MinhDoan | Complete
WEEK 15 | 30 | Validate Vision and Scope document | Requirement | 14/1/2017 | 1 | 1 | 15/1/2017 | MinhDoan | Complete
WEEK 15 | 31 | Write "Manage Homepage" usecase description | Requirement | 15/1/2017 | 1 | 2 | 15/1/2017 | MinhDoan | Complete
WEEK 15 | 32 | Review requirement | Requirement | 2017-10-01 | 3 | 2 | 2017-10-01 | XuanThaiHien | Complete
WEEK 15 | 33 | Update document structure | Planning | 2017-11-01 | 2 | 2 | 2017-11-01 | XuanThaiHien | Complete
WEEK 15 | 34 | Modify Physical view | Architect | 2017-12-01 | 2 | 3 | 2017-12-01 | XuanThaiHien | Pending
WEEK 15 | 35 | Validate "Manage News","Manage Account" usecase description | Requirement | 15/1/2017 | 3 | 4 | 15/1/2017 | XuanThaiHien | Complete
WEEK 16 | 1 | Demo connect redis engine | Architect | 16/1/2017 | 6 | 4 | 18/1/2017 | HienNguyen | Complete
WEEK 16 | 2 | Demo index data into mongo db | Architect | 16/1/2017 | 4 |  | 18/1/2017 | TaiNguyen | Pending
WEEK 16 | 3 | Demo connect relastic search with mongo db | Architect | 16/1/2017 | 5 |  | 18/1/2017 | TaiNguyen
WEEK 16 | 4 | Demo function "Create Account" using angular 2, mongodb | Coding | 18/1/2017 |  |  |  | XuanThaiHien
WEEK 16 | 5 | Demo function "Create Account" using angular 2, mongodb | Coding | 18/1/2017 |  |  |  | KhoiNguyen
WEEK 16 | 7 | Update schedule | Planning | 16/1/2017 | 3 | 2 | 18/1/2017 | HaiTran | Complete
WEEK 16 | 8 | Update static view | Architect | 18/1/2017 | 4 |  | 19/1/2017 | HaiTran
WEEK 16 | 9 | Update physical view | Architect | 18/1/2017 | 5 |  | 19/1/2017 | HienNguyen
WEEK 16 | 10 | Update physical view | Architect | 18/1/2017 | 5 |  | 19/1/2017 | HaiTran
WEEK 17 | 1 | Modify Physical view | Architect | 23/1/2017 |  |  |  | HienNguyen
WEEK 17 | 2 | Modify Static view | Architect | 23/1/2017 |  |  |  | HaiTran
WEEK 17 | 3 | Modify Dynamic view | Architect | 23/1/2017 |  |  |  | KhoiNguyen
WEEK 17 | 4 | Code Function "Login" | Coding | 23/1/2017 |  |  |  | TaiNguyen
WEEK 17 | 5 | Code Function "Login" | Coding | 23/1/2017 |  |  |  | MinhDoan
WEEK 17 | 6 | Code Function "Login" | Coding | 23/1/2017 |  |  |  | XuanThaiHien
WEEK 17 | 7 | Code Function "Login" | Coding | 23/1/2017 |  |  |  | HienNguyen
WEEK 17 | 8 | Code Function "Login" | Coding | 23/1/2017 |  |  |  | HaiTran
WEEK 17 | 9 | Code Function "Login" | Coding | 23/1/2017 |  |  |  | KhoiNguyen
WEEK 17 | 10 | Modify Database design | Detailed Design | 23/1/2017 |  |  |  | TaiNguyen