## Report
WEEKLY REPORT
WEEK:14
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Review usecase description | 2017-02-01 | 2017-02-01 | HaiTran | 4 | 3
2 | Draw static view detailed | 2017-03-01 | 2017-03-01 |  | 2 | 1
3 | Update requirement | 2017-04-01 | 2017-04-01 |  | 2 | 3
4 | Update usecase | 2017-06-01 | 2017-06-01 |  | 3 | 3
5 | Update dynamic view lv 0 | 2017-02-01 | 2017-03-01 | HienNguyen | 4 | 2
6 | Research pattern 3 layers in dynamic view | 2017-03-01 | 2017-03-01 |  | 3 | 2
7 | Update usecase | 2017-04-01 | 2017-04-01 |  | 5 | 3
8 | Research pattern 3 layers in dynamic view | 2017-02-01 | 2017-02-01 | KhoiNguyen | 2 | 1
9 | Update dynamic view lv 0 | 2017-04-01 | 2017-04-01 |  | 2 | 4
10 | Update document structure | 2017-05-01 | 2017-05-01 |  | 3 | 3
11 | Draw static view | 2017-01-01 | 2017-01-01 | TaiNguyen | 4 | 3
12 | Update Static view | 2017-03-01 | 2017-03-01 |  | 2 | 3
13 | Update usecase | 2017-04-01 | 2017-05-01 |  | 2 | 2
14 | Draw physical view | 2017-02-01 | 2017-02-01 | MinhDoan | 2 | 2.5
15 | Fix physical view | 2017-04-01 | 2017-04-01 |  | 2 | 1
16 | Research tactics for quality attributes | 2017-05-01 | 2017-06-01 |  | 3 | 4
17 | Update usecase | 2017-06-01 | 2017-06-01 |  | 2 | 1
18 | Research tactics for physical view | 2017-02-01 | 2017-02-01 | XuanThaiHien | 1 | 2
19 | Tactics performance, usability for physical view | 2017-03-01 | 2017-03-01 |  | 5 | 2
20 | Research tactics for physical view | 2017-02-01 | 2017-02-01 |  | 4 | 2
21 | Tactics performance, usability for physical view | 2017-03-01 | 2017-03-01 |  | 1 | 2
[5 empty] | Estimate | Actual
|  | Total |  | HaiTran | 11 | 10
|  |  |  | HienNguyen | 12 | 7
|  |  |  | KhoiNguyen | 7 | 8
|  |  |  | TaiNguyen | 8 | 8
|  |  |  | MinhDoan | 9 | 8.5
|  |  |  | XuanThaiHien | 11 | 8

## HaiTran (hidden)
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time
1 | Review usecase description | 2017-02-01 | 2017-02-01 | 4 | 3
2 | Draw static view detailed | 2017-03-01 | 2017-03-01 | 5 | 3
3 | Update requirement | 2017-04-01 | 2017-04-01 | 2 | 3
4 | Update usecase | 2017-06-01 | 2017-06-01 | 3 | 3

## HienNguyen (hidden)
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time
1 | Update dynamic view lv 0 | 2017-02-01 | 2017-03-01 | 4 | 2
2 | Research pattern 3 layers in dynamic view | 2017-03-01 | 2017-03-01 | 3 | 2
3 | Update usecase | 2017-04-01 | 2017-04-01 | 5 | 3

## KhoiNguyen (hidden)
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time
1 | Research pattern 3 layers in dynamic view | 2017-02-01 | 2017-02-01 | 2 | 1
2 | Update dynamic view lv 0 | 2017-04-01 | 2017-04-01 | 2 | 4
3 | Update document structure | 2017-05-01 | 2017-05-01 | 3 | 3

## TaiNguyen (hidden)
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time
1 | Draw static view | 2017-01-01 | 2017-01-01 | 4 | 3
2 | Update Static view | 2017-03-01 | 2017-03-01 | 2 | 3
3 | Update usecase | 2017-04-01 | 2017-05-01 | 2 | 2

## MinhDoan (hidden)
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time
1 | Draw physical view | 2017-02-01 | 2017-02-01 | 2 | 2.5
2 | Fix physical view | 2017-04-01 | 2017-04-01 | 2 | 1
3 | Research tactics for quality attributes | 2017-05-01 | 2017-06-01 | 3 | 4
4 | Update usecase | 2017-06-01 | 2017-06-01 | 2 | 1

## XuanThaiHien (hidden)
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time
1 | Research tactics for physical view | 2017-02-01 | 2017-02-01 | 4 | 2
2 | Tactics performance, usability for physical view | 2017-03-01 | 2017-03-01 | 5 | 2
1 | Research tactics for physical view | 2017-02-01 | 2017-02-01 | 4 | 2
2 | Tactics performance, usability for physical view | 2017-03-01 | 2017-03-01 | 5 | 2