## Sheet1
EFFORT LOG
WEEK:15
No. | Task | From | To | Estimate Time | Actual Time
1 | Review requirement | 2017-10-01 | 2017-10-01 | 3 | 2
2 | Update document structure | 2017-11-01 | 2017-11-01 | 2 | 5
3 | Modify Physical view | 2017-12-01 | 2017-12-01 | 2 | 3
4 | Validate "Manage News","Manage Account" usecase description | 15/1/2017 | 15/1/2017 | 3 | 4