## Sheet1
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time
1 | Demo connect redis engine | 16/1/2017 | 2017-01-18 | 6 | 4
9 | Update physical view | 18/1/2017 | 19/1/2017 | 5 | 4