## Report
WEEKLY REPORT
WEEK:15
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Update Usecase | 2017-09-01 | 2017-09-01 | HaiTran | 5 | 4
2 | Review Usecase descriptioin | 2017-11-01 | 2017-11-01 |  | 6 | 3
3 | Update Process | 2017-12-01 | 2017-12-01 |  | 3 | 2
4 | Research Static view | 2017-12-01 | 2017-12-01 |  | 3 | 2
5 | Update usecase diagram | 14/1/2017 | 15/1/2017 |  | 2 | 1
6 | Update Function list usecase | 15/1/2017 | 15/1/2017 |  | 1 | 1
7 | Validate "Manage Banners","Manage Languages" usecase description | 15/1/2017 | 15/1/2017 |  | 1 | 1
8 | Review Requirement | 2017-10-01 | 2017-10-01 | HienNguyen | 3 | 2
9 | Update usecase description | 2017-11-01 | 2017-11-01 |  | 4 | 3
10 | Modify architecture and design process | 2017-11-01 | 2017-11-01 |  | 2 | 3
11 | Modify dynamic view | 2017-12-01 | 2017-12-01 |  | 2 | 1
12 | Research Redis engine | 15/1/2017 | 15/1/2017 |  | 1 | 1
13 | Review requirement | 2017-10-01 | 2017-10-01 | KhoiNguyen | 4 | 2
14 | Update usecase | 2017-11-01 | 2017-11-01 |  | 5 | 4
15 | Update configuration process | 2017-11-01 | 2017-11-01 |  | 3 | 1
16 | Modify Dynamic view | 2017-12-01 | 2017-12-01 |  | 3 | 2
17 | Validate SRS document | 14/1/2017 | 14/1/2017 |  | 2 | 2
18 | Validate "Manage Q&A","Manage Popups" usecase description | 15/1/2017 | 15/1/2017 |  | 2 | 3
19 | Review requirement | 2017-10-01 | 2017-10-01 | TaiNguyen | 4 | 2
20 | Update usecase | 2017-11-01 | 2017-11-01 |  | 3 | 2
21 | Update development process | 2017-11-01 | 2017-11-01 |  | 3 | 2
22 | Update measurement and control process | 2017-12-01 | 2017-12-01 |  | 2 | 2
23 | Modify static view | 2017-12-01 | 2017-12-01 |  | 2 | 3
24 | Research elastic search engine | 15/1/2017 | 15/1/2017 |  | 1 | 3
25 | Review requirement | 2017-10-01 | 2017-10-01 | MinhDoan | 4 | 2
26 | Update usecase | 2017-11-01 | 2017-11-01 |  | 3 | 2
27 | Update change management process | 2017-11-01 | 2017-11-01 |  | 3 | 4
28 | Modify Physical view | 2017-12-01 | 2017-12-01 |  | 2 | 3
29 | Validate ConOps document | 14/1/2017 | 14/1/2017 |  | 2 | 1
30 | Validate Vision and Scope document | 14/1/2017 | 14/1/2017 |  | 1 | 1
31 | Write "Manage Homepage" usecase description | 15/1/2017 | 15/1/2017 |  | 1 | 2
32 | Review requirement | 2017-10-01 | 2017-10-01 | XuanThaiHien | 3 | 2
33 | Update document structure | 2017-11-01 | 2017-11-01 |  | 2 | 2
34 | Modify Physical view | 2017-12-01 | 2017-12-01 |  | 2 | 3
35 | Validate "Manage News","Manage Account" usecase description | 15/1/2017 | 15/1/2017 |  | 3 | 4
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 21 | 14
|  |  |  | HienNguyen | 12 | 10
|  |  |  | KhoiNguyen | 19 | 14
|  |  |  | TaiNguyen | 15 | 14
|  |  |  | MinhDoan | 16 | 15
|  |  |  | XuanThaiHien | 10 | 11

## HaiTran (hidden)
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time
1 | Update Usecase | 2017-09-01 | 2017-09-01 | 5 | 4
2 | Review Usecase descriptioin | 2017-11-01 | 2017-11-01 | 6 | 3
3 | Update Process | 2017-12-01 | 2017-12-01 | 3 | 2
4 | Research Static view | 2017-12-01 | 2017-12-01 | 3 | 2
5 | Update usecase diagram | 14/1/2017 | 15/1/2017 | 2 | 1
6 | Update Function list usecase | 15/1/2017 | 15/1/2017 | 1 | 1
7 | Validate "Manage Banners","Manage Languages" usecase description | 15/1/2017 | 15/1/2017 | 1 | 1

## HienNguyen (hidden)
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time
1 | Review Requirement | 2017-10-01 | 2017-10-01 | 3 | 2
2 | Update usecase description | 2017-11-01 | 2017-11-01 | 4 | 3
3 | Modify architecture and design process | 2017-11-01 | 2017-11-01 | 2 | 3
4 | Modify dynamic view | 2017-12-01 | 2017-12-01 | 2 | 1
5 | Research Redis engine | 15/1/2017 | 15/1/2017 | 1 | 1

## KhoiNguyen (hidden)
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time
1 | Review requirement | 2017-10-01 | 2017-10-01 | 4 | 2
2 | Update usecase | 2017-11-01 | 2017-11-01 | 5 | 4
3 | Update configuration process | 2017-11-01 | 2017-11-01 | 3 | 1
4 | Modify Dynamic view | 2017-12-01 | 2017-12-01 | 3 | 2
5 | Validate SRS document | 14/1/2017 | 14/1/2017 | 2 | 2
6 | Validate "Manage Q&A","Manage Popups" usecase description | 15/1/2017 | 15/1/2017 | 2 | 3

## TaiNguyen (hidden)
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time
1 | Review requirement | 2017-10-01 | 2017-10-01 | 4 | 2
2 | Update usecase | 2017-11-01 | 2017-11-01 | 3 | 2
3 | Update development process | 2017-11-01 | 2017-11-01 | 3 | 2
4 | Update measurement and control process | 2017-12-01 | 2017-12-01 | 2 | 2
5 | Modify static view | 2017-12-01 | 2017-12-01 | 2 | 3
6 | Research elastic search engine | 15/1/2017 | 15/1/2017 | 1 | 3

## MinhDoan (hidden)
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time
1 | Review requirement | 2017-10-01 | 2017-10-01 | 4 | 2
2 | Update usecase | 2017-11-01 | 2017-11-01 | 3 | 2
3 | Update change management process | 2017-11-01 | 2017-11-01 | 3 | 4
4 | Modify Physical view | 2017-12-01 | 2017-12-01 | 2 | 3
5 | Validate ConOps document | 14/1/2017 | 14/1/2017 | 2 | 1
6 | Validate Vision and Scope document | 14/1/2017 | 14/1/2017 | 1 | 1
7 | Write "Manage Homepage" usecase description | 15/1/2017 | 15/1/2017 | 1 | 2

## XuanThaiHien (hidden)
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time
1 | Review requirement | 2017-10-01 | 2017-10-01 | 3 | 2
2 | Update document structure | 2017-11-01 | 2017-11-01 | 2 | 5
3 | Modify Physical view | 2017-12-01 | 2017-12-01 | 2 | 3
4 | Validate "Manage News","Manage Account" usecase description | 15/1/2017 | 15/1/2017 | 3 | 4