## Sheet1
|  | ID | Task | Sub Task | Level 2 Sub Task | hai | hien | khoi | minh | tai
KICK OFF |  | 1 | Develop Team rule & policy |  |  | 2 | 4 | 1 | 3 | 3
|  | 2 | Develop Team Charter |  |  | 2 | 2 | 1 | 1 | 2
|  | 4 | Develop Project Charter |  |  | 4 | 2 | 2 | 4 | 2
|  | 5 | Develop Process Decision |  |  | 5 | 3 | 4 | 3 | 3
|  | 7 | Define template
|  |  |  | Effort log, Time log template |  | 0.5 | 1 | 0.5 | 1 | 2
|  |  |  | Weekly report template |  | 1 | 0.5 | 0.5 | 1.5 | 0.5
|  |  |  | Project plan template |  | 2 | 1 | 0.5 | 2 | 0.5
|  |  |  | Configuration plan template |  | 1 | 1 | 0.5 | 2 | 1
|  |  |  | Communication plan template |  | 2 | 1 | 0.5 | 2 | 0.5
|  |  |  | Change management plan template |  | 1 | 1 | 0.5 | 1 | 0.5
|  |  |  | Measurement plan template |  | 1 | 1 | 0.5 | 1.5 | 0.5
|  |  |  | Risk Management Plan template |  | 2 | 1.5 | 0.5 | 2 | 0.5
|  |  |  | WBS template |  | 3 | 2 | 0.5 | 0.5 | 0.5
|  |  |  | List change template |  | 1 | 1 | 0.5 | 1 | 1
|  |  |  | Requirement Management plan template |  | 2 | 1 | 0.5 | 2 | 1
|  |  |  | Architecture and design plan template |  | 2 | 1 | 0.5 | 2 | 0.5
|  |  |  | Test plan template |  | 1.5 | 1.5 | 0.5 | 2.5 | 1
|  |  |  | Vision and Scope template |  | 1 | 0.5 | 0.5 | 1 | 1
|  |  |  | Concept of Operation template |  | 2 | 0.5 | 0.5 | 1.5 | 1.5
|  |  |  | Wideband Delphi template |  | 3 | 1 | 0.5 | 0.5 | 0.5
|  |  |  | SRS template |  | 2 | 1.5 | 0.5 | 1.5 | 1
|  |  |  | Detail Design template |  | 3 | 2 | 0.5 | 2.5 | 2
|  |  |  | Functional Testcase template |  | 1 | 1 | 0.5 | 1 | 1
|  |  |  | User Acceptance Testcase template |  | 2 | 1.5 | 0.5 | 1.5 | 1
|  |  |  | Test Report template |  | 1 | 1 | 0.5 | 1 | 2
PLANNING |  | 8 | Develop Work Break Down Structure |  |  | 5 | 7 | 4 | 7 | 2
|  | 9 | Develop Requirement Plan |  |  | 6 | 10 | 5 | 7 | 6
|  | 10 | Develop Implement Plan |  |  | x
|  | 11 | Develop Architecture and Design |  |  | 7 | 10 | 6 | 15 | 8
|  | 12 | Develop Configuration Plan |  |  | 7 | 10 | 6 | 10 | 4
|  | 13 | Develop Test Plan |  |  | 8 | 10 | 10 | 5 | 10
|  | 14 | Develop Risk Management |  |  | 6 | 10 | 6 | 6 | 5
|  | 15 | Develop Change Management |  |  | 8 | 10 | 6 | 6 | 5
|  | 17 | Develop Development Process |  |  | 7 | 8 | 8 | 10 | 8
|  | 18 | Develop Measurement Process |  |  | 7 | 8 | 8 | 10 | 7
|  | 19 | Develop Schedule |  |  | 9 | 7 | 6 | 10 | 5
|  | 20 | Develop Estimation |  |  | 5 | 8 | 8 | 4 | 3
|  | 21 | Develop Training Plan |  |  | 6 | 4 | 3 | 7 | 7
|  | 22 | Develop Master Plan |  |  | 7 | 6 | 4 | 5 | 4
|  | 23 | Gather Question List |  |  | 9 | 7 | 4 | 5 | 4
REQUIREMENT | ELICITATION |  |  |  |  | 5
|  | 25 | Develop Function List |  |  | 9 | 10 | 8 | 8 | 10
|  | 26 | Develop Vision and Scope
|  |  |  | Business Requirements |  | 1 | 2 | 1 | 1 | 0.5
|  |  |  | Vision of the Solution |  | 2 | 3 | 2 | 1 | 2
|  |  |  | Scope and Limitations |  | 1 | 4 | 2 | 2 | 2
|  |  |  | Business Context |  | 2 | 3 | 1 | 2 | 2
|  | 27 | Develop Concept of Operation
|  |  |  | Current System |  | 1 | 1 | 1 | 1 | 0.5
|  |  |  | Proposed System |  | 0.5 | 2 | 1 | 4 | 3
|  |  |  | Context Diargram |  | 2 | 2 | 2 | 4 | 2
|  |  |  | Environment System |  | 2 | 3 | 2 | 2 | 1
|  |  |  | Justification of Changes |  | 2 | 2 | 2 | 3 | 1
|  |  |  | Summary of impacts |  | 1 | 2 | 1 | 2 | 0.5
|  |  |  | The analysis summarizing future system |  | 1 | 1 | 1 | 0.5 | 0
|  | 28 | Develop Prototype
|  |  |  | Website |  | 20 | 25 | 22 | 15 | 24
|  |  |  | Mobile |  | 10 | 12 | 15 | 10 | 12
|  | 29 | Develop URD
Usecase Description
[5 empty] | Manage News | 10 | 24 | 20 | 25 | 8
[5 empty] | Manage Account | 8 | 18 | 15 | 10 | 5
[5 empty] | Manage Categories | 6 | 8 | 8 | 6 | 3
[5 empty] | Manage Popup | 4 | 8 | 8 | 6 | 3
| ANALYSIS |  |  |  | Manage Banners | 4 | 8 | 8 | 6 | 3
[5 empty] | Manage Q/A | 3 | 8 | 6 | 8 | 3
[5 empty] | Manage Examination | 6 | 10 | 8 | 11 | 4
[5 empty] | Manage Language | 3 | 1.5 | 3 | 0.5 | 1
[5 empty] | Manage Resource | 5 | 6 | 6 | 5 | 2
[5 empty] | Manage Homepage | 6 | 7 | 6 | 6 | 5
|  |  |  | Usecase Diagram |  | 10 | 10 | 6 | 6 | 5
|  | 30 | Develop SRS
|  |  |  | Product Functions |  | 1 | 1 | 1 | 1 | 0.5
|  |  |  | User Classes and Characteristics |  | 1 | 1 | 1 | 2 | 1
|  |  |  | Operating Environment |  | 2 | 1 | 2 | 2 | 0.5
Constraint
[5 empty] | Business Constraint | 1 | 1 | 0.5 | 1 | 0.5
| SPECIFICATION |  |  |  | Technical Constraint | 1 | 1 | 0.5 | 0.5 | 0.5
|  |  |  | Business Rules |  | 1 | 3 | 3 | 5 | 6
|  |  |  | User Interface |  | 4 | 12 | 8 | 10 | deo biet
|  |  |  | Quality Attribute Requirement |  | 5 | 10 | 6 | 5 | 4
|  | 31 | Develop Functional Testcase
|  |  |  | Manage News |  | 15 | 24 | 20 | 25 | 36
|  |  |  | Manage Account |  | 10 | 12 | 15 | 8 | 17
|  |  |  | Manage Categories |  | 8 | 8 | 10 | 5 | 11
|  |  |  | Manage Popup |  | 8 | 6 | 8 | 5 | 4
|  |  |  | Manage Banners |  | 5 | 6 | 8 | 5 | 2
|  |  |  | Manage Q/A |  | 3 | 4 | 6 | 5 | 2
| VALIDATION |  |  | Manage Examination |  | 5 | 8 | 6 | 8 | 5
|  |  |  | Manage Language |  | 3 | 1 | 2 | 1 | 1.5
|  |  |  | Manage Resource |  | 5 | 5 | 3 | 6 | 3
|  |  |  | Manage Homepage |  | 4 | 5 | 5 | 6 | 5
|  | 32 | Develop User Acceptance Testcase |  |  | 1 | 1 | 1 | 1 | 1
Manage News
Manage Account
Manage Categories
Manage Popup
Manage Banners
Manage Q/A
Manage Examination
Manage Language
Manage Resource
Manage Homepage
|  | 33 | Develop Architecture Design
|  |  |  | Physical View |  | 10 | 15 | 10 | 8 | 11
|  |  |  | Static View |  | 8 | 5 | 10 | 8 | 8
|  |  |  | Dynamic View |  | 15 | 20 | 12 | 15 | 13
|  | 34 | Develop Detail Design
Class Diagram
ARCHITECT |  |  |  |  | GUI
BUS
Entity
Sequence Diagram
IMPLEMENT | RELEASE 1 |  |  |  | Manage News
Authorization
Manage Categories
Database Design
ERD
Physical model
User Interface
Manage News
Authorization
Manage Categories
|  | 35 | Code module |  |  | 50
Manage News
View News
Post News
Approve News
Transfer News
Edit News
Filter News
Deactive News
Manage Categories
Add
Delete
Edit
Filter
View
|  |  |  | Authorization |  | 25
|  | 36 | Test
Functional Test
Manage News
Authorization
Manage Categories
Report functional test
Defect tracking
Fix bugs
Acceptance Test
Report Acceptance Test
Defect tracking
Fix bugs
|  | 37 | Develop Detail Design
Class Diagram
GUI
BUS
Entity
Sequence Diagram
Manage Student
| RELEASE 2 |  |  |  | Manage Account
Manage Q/A
Database Design
ERD
Physical model
User Interface
Manage Student
Manage Account
Manage Q/A
|  | 38 | Code module
Manage Student
View Score
Import Score
Export Profile
Edit Profile
Exam Registation
Manage Account
Login
Create
Edit
Search
Forget Password
Manage Q/A
Send Question
View Question
Answer Question
Approve Question
|  | 39 | Test
Functional Test
Manage Student
Manage Account
Manage Q/A
Report functional test
Defect tracking
Fix bugs
Acceptance Test
Report Acceptance Test
Defect tracking
Fix bugs
|  | 40 | Develop Detail Design
Class Diagram
GUI
BUS
Entity
Sequence Diagram
Manage Banners
| RELEASE 3 |  |  |  | Manage Pop_ups
Multi Language
Sale Website
Database Design
ERD
Physical model
User Interface
Manage Banners
Manage Pop_ups
Multi Language
Sale Website
|  | 41 | Code module
Manage Banners
Create
Delete
View
Edit
Control Time
Manage Pop_ups
Create
Delete
View
Show/hide
Control Time
Multi Language
Sale Website
|  | 42 | Test
Functional Test
Manage Banners
Manage Pop_ups
Multi Language
Sale Website
Report functional test
Defect tracking
Fix bugs
Acceptance Test
Report Acceptance Test
Defect tracking
Fix bugs
|  | 43 | Control and Monitor |  |  | 2
Weekly report
Team meeting
Mentor meeting
Manage Change
Manage Risk
Customer meeting
CONTROL & MONITORING |  | 44 | Deploy |  |  | 5
User guide
Installation guide
DEPLOY