## Sheet1
EFFORT LOG
WEEK: 18
No. | Task | From | To | Estimate Time | Actual Time
1 | Draw class diagram function "Manage FAQ" | 2017-07-02 | 2017-10-02 | 7 | 6
2 | Draw class diagram function "Manage Popups" | 2017-07-02 | 2017-10-02 | 7 | 6
3 | Draw sequence diagram function "Manage Categories" | 2017-07-02 | 2017-10-02 | 7 | 8
4 | Draw sequence diagram function "Manage Popups" | 2017-07-02 | 2017-10-02 | 7 | 8