## Sheet1
ID | TASK | SUB TASK | LV2 SUB TASK | LV3 SUB TASK | hai | hien | khoi | minh | tai
KICK OFF
1 | Develop Team rule & policy |  |  |  | 2 | 4 | 1 | 3 | 3
2 | Develop Team Charter |  |  |  | 2 | 2 | 1 | 1 | 2
3 | Develop Project Charter |  |  |  | 4 | 2 | 2 | 4 | 2
4 | Develop Process Decision |  |  |  | 5 | 3 | 4 | 3 | 3
PLANNING
5 | Define template
5.1 |  | Effort log. Time log template |  |  | 0.5 | 1 | 0.5 | 1 | 2
5.2 |  | Weekly report template |  |  | 1 | 0.5 | 0.5 | 1.5 | 0.5
5.3 |  | Project plan template |  |  | 2 | 1 | 0.5 | 2 | 0.5
5.4 |  | Configuration plan template |  |  | 1 | 1 | 0.5 | 2 | 1
5.5 |  | Communication plan template |  |  | 2 | 1 | 0.5 | 2 | 0.5
5.6 |  | Change management plan template |  |  | 1 | 1 | 0.5 | 1 | 0.5
5.7 |  | Measurement plan template |  |  | 1 | 1 | 0.5 | 1.5 | 0.5
5.8 |  | Risk Management Plan template |  |  | 2 | 1.5 | 0.5 | 2 | 0.5
5.9 |  | WBS template |  |  | 3 | 2 | 0.5 | 0.5 | 0.5
5.1 |  | List change template |  |  | 1 | 1 | 0.5 | 1 | 1
5.11 |  | Requirement Management plan template |  |  | 2 | 1 | 0.5 | 2 | 1
5.12 |  | Architecture and design plan template |  |  | 2 | 1 | 0.5 | 2 | 0.5
5.13 |  | Test plan template |  |  | 1.5 | 1.5 | 0.5 | 2.5 | 1
5.14 |  | Vision and Scope template |  |  | 1 | 0.5 | 0.5 | 1 | 1
5.15 |  | Concept of Operation template |  |  | 2 | 0.5 | 0.5 | 1.5 | 1.5
5.16 |  | Wideband Delphi template |  |  | 3 | 1 | 0.5 | 0.5 | 0.5
5.17 |  | SRS template |  |  | 2 | 1.5 | 0.5 | 1.5 | 1
5.18 |  | Detail Design template |  |  | 3 | 2 | 0.5 | 2.5 | 2
5.19 |  | Functional Testcase template |  |  | 1 | 1 | 0.5 | 1 | 1
5.2 |  | User Acceptance Testcase template |  |  | 2 | 1.5 | 0.5 | 1.5 | 1
5.21 |  | Test Report template |  |  | 1 | 1 | 0.5 | 1 | 2
6 | Develop Work Break Down Structure |  |  |  | 5 | 7 | 4 | 7 | 2
7 | Develop Requirement Plan |  |  |  | 6 | 10 | 5 | 7 | 6
8 | Develop Implement Plan |  |  |  | x
9 | Develop Architecture and Design |  |  |  | 7 | 10 | 6 | 15 | 8
10 | Develop Configuration Plan |  |  |  | 7 | 10 | 6 | 10 | 4
11 | Develop Test Plan |  |  |  | 8 | 10 | 10 | 5 | 10
12 | Develop Risk Management |  |  |  | 6 | 10 | 6 | 6 | 5
13 | Develop Change Management |  |  |  | 8 | 10 | 6 | 6 | 5
14 | Develop Development Process |  |  |  | 7 | 8 | 8 | 10 | 8
15 | Develop Measurement Process |  |  |  | 7 | 8 | 8 | 10 | 7
16 | Develop Schedule |  |  |  | 9 | 7 | 6 | 10 | 5
17 | Develop Estimation |  |  |  | 5 | 8 | 8 | 4 | 3
18 | Develop Training Plan |  |  |  | 6 | 4 | 3 | 7 | 7
19 | Develop Master Plan |  |  |  | 7 | 6 | 4 | 5 | 4
20 | Gather Question List |  |  |  | 9 | 7 | 4 | 5 | 4
21 | Develop Function List |  |  |  | 9 | 10 | 8 | 8 | 10
REQUIREMENT
22 | Develop Vision and Scope
22.1 |  | Business Requirements |  |  | 1 | 2 | 1 | 1 | 0.5
22.2 |  | Vision of the Solution |  |  | 2 | 3 | 2 | 1 | 2
22.3 |  | Scope and Limitations |  |  | 1 | 4 | 2 | 2 | 2
22.4 |  | Business Context |  |  | 2 | 3 | 1 | 2 | 2
23 | Develop Concept of Operation
23.1 |  | Current System |  |  | 1 | 1 | 1 | 1 | 0.5
23.2 |  | Proposed System |  |  | 0.5 | 2 | 1 | 4 | 3
23.3 |  | Context Diargram |  |  | 2 | 2 | 2 | 4 | 2
23.4 |  | Environment System |  |  | 2 | 3 | 2 | 2 | 1
23.5 |  | Justification of Changes |  |  | 2 | 2 | 2 | 3 | 1
23.6 |  | Summary of impacts |  |  | 1 | 2 | 1 | 2 | 0.5
23.7 |  | The analysis summarizing future system |  |  | 1 | 1 | 1 | 0.5 | 0
24 | Develop Prototype
24.1 |  | Website |  |  | 20 | 25 | 22 | 15 | 24
24.2 |  | Mobile |  |  | 10 | 12 | 15 | 10 | 12
25 | Develop URD
25.1 |  | Usecase Description
25.1.1 |  |  | Manage News |  | 10 | 24 | 20 | 25 | 8
25.1.2 |  |  | Manage Account |  | 8 | 18 | 15 | 10 | 5
25.1.3 |  |  | Manage Categories |  | 6 | 8 | 8 | 6 | 3
25.1.4 |  |  | Manage Popup |  | 4 | 8 | 8 | 6 | 3
25.1.5 |  |  | Manage Banners |  | 4 | 8 | 8 | 6 | 3
25.1.6 |  |  | Manage Q/A |  | 3 | 8 | 6 | 8 | 3
25.1.7 |  |  | Manage Examination |  | 6 | 10 | 8 | 11 | 4
25.1.8 |  |  | Manage Language |  | 3 | 1.5 | 3 | 0.5 | 1
25.1.9 |  |  | Manage Resource |  | 5 | 6 | 6 | 5 | 2
25.1.10 |  |  | Manage Homepage |  | 6 | 7 | 6 | 6 | 5
25.2 |  | Usecase Diagram |  |  | 10 | 10 | 6 | 6 | 5
26 | Develop SRS
26.1 |  | Product Functions |  |  | 1 | 1 | 1 | 1 | 0.5
26.2 |  | User Classes and Characteristics |  |  | 1 | 1 | 1 | 2 | 1
26.3 |  | Operating Environment |  |  | 2 | 1 | 2 | 2 | 0.5
26.4 |  | Constraint
26.4.1 |  |  | Business Constraint |  | 1 | 1 | 0.5 | 1 | 0.5
26.4.2 |  |  | Technical Constraint |  | 1 | 1 | 0.5 | 0.5 | 0.5
26.5 |  | Business Rules |  |  | 1 | 3 | 3 | 5 | 6
26.6 |  | User Interface |  |  | 4 | 12 | 8 | 10 | deo biet
26.7 |  | Quality Attribute Requirement |  |  | 5 | 10 | 6 | 5 | 4
27 | Develop Functional Testcase
27.1 |  | Manage News |  |  | 15 | 24 | 20 | 25 | 36
27.2 |  | Manage Account |  |  | 10 | 12 | 15 | 8 | 17
27.3 |  | Manage Categories |  |  | 8 | 8 | 10 | 5 | 11
27.4 |  | Manage Popup |  |  | 8 | 6 | 8 | 5 | 4
27.5 |  | Manage Banners |  |  | 5 | 6 | 8 | 5 | 2
27.6 |  | Manage Q/A |  |  | 3 | 4 | 6 | 5 | 2
27.7 |  | Manage Examination |  |  | 5 | 8 | 6 | 8 | 5
27.8 |  | Manage Language |  |  | 3 | 1 | 2 | 1 | 1.5
27.9 |  | Manage Homepage |  |  | 4 | 5 | 5 | 6 | 5
28 | Develop User Acceptance Testcase |  |  |  | 1 | 1 | 1 | 1 | 1
ARCHITECTURE AND DESIGN
29 | Develop Architecture Design
29.1 |  | Physical View |  |  | 10 | 15 | 10 | 8 | 11
29.2 |  | Static View |  |  | 8 | 5 | 10 | 8 | 8
29.3 |  | Dynamic View |  |  | 15 | 20 | 12 | 15 | 13
RELEASE 1
30 | Develop Detail Design
30.1 |  | Class Diagram
30.1.1 |  |  | GUI
30.1.2 |  |  | BUS
30.1.3 |  |  | Entity
30.2 |  | Draw Sequence Diagram
30.2.1 |  |  | Manage News Function
30.2.1.1 |  |  |  | View News
30.2.1.2 |  |  |  | Post
30.2.1.3 |  |  |  | View Draft
30.2.1.4 |  |  |  | Edit Draft
30.2.1.5 |  |  |  | Delete Draft
30.2.1.6 |  |  |  | Transfer
30.2.1.7 |  |  |  | Approve
30.2.1.8 |  |  |  | Deactive
30.2.1.9 |  |  |  | Search
30.2.1.10 |  |  |  | Sort
30.2.1.11 |  |  |  | Push
30.2.1.12 |  |  |  | Create News
30.2.1.13 |  |  |  | Share News
30.2.2 |  |  | Manage Accounts Function
30.2.2.1 |  |  |  | Log-in
30.2.2.2 |  |  |  | Log-out
30.2.2.3 |  |  |  | Create Account
30.2.2.4 |  |  |  | Edit Account
30.2.2.5 |  |  |  | Search Account
30.2.2.6 |  |  |  | Forget Password
30.2.2.7 |  |  |  | View Detail Of Account
30.2.2.8 |  |  |  | View List Account
30.2.2.9 |  |  |  | Authorize
30.2.2.10 |  |  |  | Activate Account
30.2.2.11 |  |  |  | Deactivate Account
30.2.3 |  |  | Manage Homepage Function
30.2.3.1 |  |  |  | Add
30.2.3.2 |  |  |  | Edit
30.2.3.3 |  |  |  | Delete
30.2.4 |  |  | Manage Categories Function
30.2.4.1 |  |  |  | View
30.2.4.2 |  |  |  | Add
30.2.4.3 |  |  |  | Edit
30.2.4.4 |  |  |  | Delete
30.3 |  | Design Database
30.3.1 |  |  | ERD
30.3.2 |  |  | Physical model
30.4 |  | User Interface
30.4.1 |  |  | Manage News Function
30.4.1.1 |  |  |  | View News
30.4.1.2 |  |  |  | Post
30.4.1.3 |  |  |  | View Draft
30.4.1.4 |  |  |  | Edit Draft
30.4.1.5 |  |  |  | Delete Draft
30.4.1.6 |  |  |  | Transfer
30.4.1.7 |  |  |  | Approve
30.4.1.8 |  |  |  | Deactive
30.4.1.9 |  |  |  | Search
30.4.1.10 |  |  |  | Sort
30.4.1.11 |  |  |  | Push
30.4.1.12 |  |  |  | Create News
30.4.1.13 |  |  |  | Share News
30.4.2 |  |  | Manage Accounts Function
30.4.2.1 |  |  |  | Log-in
30.4.2.2 |  |  |  | Log-out
30.4.2.3 |  |  |  | Create Account
30.4.2.4 |  |  |  | Edit Account
30.4.2.5 |  |  |  | Search Account
30.4.2.6 |  |  |  | Forget Password
30.4.2.7 |  |  |  | View Detail Of Account
30.4.2.8 |  |  |  | View List Account
30.4.2.9 |  |  |  | Authorize
30.4.2.10 |  |  |  | Activate Account
30.4.2.11 |  |  |  | Deactivate Account
30.4.3 |  |  | Manage Homepage Function
30.4.3.1 |  |  |  | Add
30.4.3.2 |  |  |  | Edit
30.4.3.3 |  |  |  | Delete
30.4.4 |  |  | Manage Categories Function
30.4.4.1 |  |  |  | View
30.4.4.2 |  |  |  | Add
30.4.4.3 |  |  |  | Edit
30.4.4.4 |  |  |  | Delete
31 | Code module |  |  |  | 50
31.1 |  | Manage News Function
31.1.1 |  |  | View News
31.1.2 |  |  | Post
31.1.3 |  |  | View Draft
31.1.4 |  |  | Edit Draft
31.1.5 |  |  | Delete Draft
31.1.6 |  |  | Transfer
31.1.7 |  |  | Approve
31.1.8 |  |  | Deactive
31.1.9 |  |  | Search
31.1.10 |  |  | Sort
31.1.11 |  |  | Push
31.1.12 |  |  | Create News
31.1.13 |  |  | Share News
31.2 |  | Manage Accounts Function
31.2.1 |  |  | Log-in
31.2.2 |  |  | Log-out
31.2.3 |  |  | Create Account
31.2.4 |  |  | Edit Account
31.2.5 |  |  | Search Account
31.2.6 |  |  | Forget Password
31.2.7 |  |  | View Detail Of Account
31.2.8 |  |  | View List Account
31.2.9 |  |  | Authorize
31.2.10 |  |  | Activate Account
31.2.11 |  |  | Deactivate Account
31.3 |  | Manage Homepage Function
31.3.1 |  |  | Add
31.3.2 |  |  | Edit
31.3.3 |  |  | Delete
31.4 |  | Manage Categories Function
31.4.1 |  |  | View
31.4.2 |  |  | Add
31.4.3 |  |  | Edit
31.4.4 |  |  | Delete
32 | Test
32.1 |  | Deploy Functional Test
32.1.1 |  |  | Manage News Function
32.1.1.1 |  |  |  | View News
32.1.1.2 |  |  |  | Post
32.1.1.3 |  |  |  | View Draft
32.1.1.4 |  |  |  | Edit Draft
32.1.1.5 |  |  |  | Delete Draft
32.1.1.6 |  |  |  | Transfer
32.1.1.7 |  |  |  | Approve
32.1.1.8 |  |  |  | Deactive
32.1.1.9 |  |  |  | Search
32.1.1.10 |  |  |  | Sort
32.1.1.11 |  |  |  | Push
32.1.1.12 |  |  |  | Create News
32.1.1.13 |  |  |  | Share News
32.1.2 |  |  | Manage Accounts Function
32.1.2.1 |  |  |  | Log-in
32.1.2.2 |  |  |  | Log-out
32.1.2.3 |  |  |  | Create Account
32.1.2.4 |  |  |  | Edit Account
32.1.2.5 |  |  |  | Search Account
32.1.2.6 |  |  |  | Forget Password
32.1.2.7 |  |  |  | View Detail Of Account
32.1.2.8 |  |  |  | View List Account
32.1.2.9 |  |  |  | Authorize
32.1.2.10 |  |  |  | Activate Account
32.1.2.11 |  |  |  | Deactivate Account
32.1.3 |  |  | Manage Homepage Function
32.1.3.1 |  |  |  | Add
32.1.3.2 |  |  |  | Edit
32.1.3.3 |  |  |  | Delete
32.1.4 |  |  | Manage Categories Function
32.1.4.1 |  |  |  | View
32.1.4.2 |  |  |  | Add
32.1.4.3 |  |  |  | Edit
32.1.4.4 |  |  |  | Delete
32.1.2 |  | Report functional test
32.1.3 |  | Defect tracking
32.1.4 |  | Fix bugs
32.1.5 |  | Acceptance Test
32.1.6 |  | Report Acceptance Test
32.1.7 |  | Defect tracking
32.1.8 |  | Fix bugs
RELEASE 2
33 | Develop Detail Design
33.1 |  | Draw Class Diagram
33.1.1 |  |  | GUI
33.1.2 |  |  | BUS
33.1.3 |  |  | Entity
33.2 |  | Draw Sequence Diagram
33.2.1 |  |  | Manage Banners Function
33.2.1.1 |  |  |  | Create
33.2.1.2 |  |  |  | View
33.2.1.3 |  |  |  | Show-Hide
33.2.1.4 |  |  |  | Edit
33.2.1.5 |  |  |  | Delete
33.2.1.6 |  |  |  | Arrange images
33.2.2 |  |  | Manage Pop-Ups Function
33.2.2.1 |  |  |  | Create
33.2.2.2 |  |  |  | View
33.2.2.3 |  |  |  | Show-Hide
33.2.2.4 |  |  |  | Edit
33.2.2.5 |  |  |  | Delete
33.2.2.6 |  |  |  | Arrange images
33.2.3 |  |  | Manage Q&A Function
33.2.3.1 |  |  |  | Send question
33.2.3.2 |  |  |  | Answer question
33.2.3.3 |  |  |  | View question
33.2.3.4 |  |  |  | Approve question
33.2.3.5 |  |  |  | Search Question
33.3 |  | Design Database
33.3.1 |  |  | ERD
33.3.2 |  |  | Physical model
33.4 |  | User Interface
33.4.1 |  |  | Manage Banners Function
33.4.1.1 |  |  |  | Create
33.4.1.2 |  |  |  | View
33.4.1.3 |  |  |  | Show-Hide
33.4.1.4 |  |  |  | Edit
33.4.1.5 |  |  |  | Delete
33.4.1.6 |  |  |  | Arrange images
33.4.2 |  |  | Manage Pop-Ups Function
33.4.2.1 |  |  |  | Create
33.4.2.2 |  |  |  | View
33.4.2.3 |  |  |  | Show-Hide
33.4.2.4 |  |  |  | Edit
33.4.2.5 |  |  |  | Delete
33.4.2.6 |  |  |  | Arrange images
33.4.3 |  |  | Manage Q&A Function
33.4.3.1 |  |  |  | Send question
33.4.3.2 |  |  |  | Answer question
33.4.3.3 |  |  |  | View question
33.4.3.4 |  |  |  | Approve question
33.4.3.5 |  |  |  | Search Question
34 | Code module |  |  |  | 50
34.1 |  | Manage Banners Function
34.1.2 |  |  | Create
34.1.3 |  |  | View
34.1.4 |  |  | Show-Hide
34.1.5 |  |  | Edit
34.1.6 |  |  | Delete
34.1.7 |  |  | Arrange images
34.2 |  | Manage Pop-Ups Function
34.2.1 |  |  | Create
34.2.2 |  |  | View
34.2.3 |  |  | Show-Hide
34.2.4 |  |  | Edit
34.2.5 |  |  | Delete
34.2.6 |  |  | Arrange images
34.3 |  | Manage Q&A Function
34.3.1 |  |  | Send question
34.3.2 |  |  | Answer question
34.3.3 |  |  | View question
34.3.4 |  |  | Approve question
34.3.5 |  |  | Search Question
35 | Test
35.1 |  | Deploy Functional Test
35.1.1 |  |  | Manage Banners Function
35.1.1.1 |  |  |  | Create
35.1.1.2 |  |  |  | View
35.1.1.3 |  |  |  | Show-Hide
35.1.1.4 |  |  |  | Edit
35.1.1.5 |  |  |  | Delete
35.1.1.6 |  |  |  | Arrange images
35.1.2 |  |  | Manage Pop-Ups Function
35.1.2.1 |  |  |  | Create
35.1.2.2 |  |  |  | View
35.1.2.3 |  |  |  | Show-Hide
35.1.2.4 |  |  |  | Edit
35.1.2.5 |  |  |  | Delete
35.1.2.6 |  |  |  | Arrange images
35.1.3 |  |  | Manage Q&A Function
35.1.3.1 |  |  |  | Send question
35.1.3.2 |  |  |  | Answer question
35.1.3.3 |  |  |  | View question
35.1.3.4 |  |  |  | Approve question
35.1.3.5 |  |  |  | Search Question
35.2 |  | Report functional test
35.3 |  | Defect tracking
35.4 |  | Fix bugs
35.5 |  | Acceptance Test
35.6 |  | Report Acceptance Test
35.7 |  | Defect tracking
35.8 |  | Fix bugs
RELEASE 3
36 | Develop Detail Design
36.1 |  | Draw Class Diagram
36.1.2 |  |  | GUI
36.1.3 |  |  | BUS
36.1.4 |  |  | Entity
36.2 |  | Draw Sequence Diagram
36.2.1 |  |  | Manage Language Function
36.2.1.1 |  |  |  | Change Languages
36.2.2 |  |  | Manage Examination Function
36.2.2.1 |  |  |  | View point
36.2.2.2 |  |  |  | View individual point
36.2.2.3 |  |  |  | Register Exam
36.2.2.4 |  |  |  | Import point
36.2.2.5 |  |  |  | Export profile
36.2.2.6 |  |  |  | Edit profile
36.2.2.7 |  |  |  | Create Exam
36.3 |  | Design Database
36.3.1 |  |  | ERD
36.3.2 |  |  | Physical model
36.4 |  | User Interface
36.4.1 |  |  | Manage Language Function
36.4.1.1 |  |  |  | Change Languages
36.4.2 |  |  | Manage Examination Function
36.4.2.1 |  |  |  | View point
36.4.2.2 |  |  |  | View individual point
36.4.2.3 |  |  |  | Register Exam
36.4.2.4 |  |  |  | Import point
36.4.2.5 |  |  |  | Export profile
36.4.2.6 |  |  |  | Edit profile
36.4.2.7 |  |  |  | Create Exam
37 | Code module |  |  |  | 50
37.1 |  | Manage Language Function
37.1.1 |  |  | Change Languages
37.2 |  | Manage Examination Function
37.2.1 |  |  | View point
37.2.2 |  |  | View individual point
37.2.3 |  |  | Register Exam
37.2.4 |  |  | Import point
37.2.5 |  |  | Export profile
37.2.6 |  |  | Edit profile
37.2.7 |  |  | Create Exam
38 | Test
38.1 |  | Deploy Functional Test
38.1.1 |  |  | Manage Language Function
38.1.1.1 |  |  |  | Change Languages
38.1.2 |  |  | Manage Examination Function
38.1.2.1 |  |  |  | View point
38.1.2.2 |  |  |  | View individual point
38.1.2.3 |  |  |  | Register Exam
38.1.2.4 |  |  |  | Import point
38.1.2.5 |  |  |  | Export profile
38.1.2.6 |  |  |  | Edit profile
38.1.2.7 |  |  |  | Create Exam
38.2 |  | Report functional test
38.3 |  | Defect tracking
38.4 |  | Fix bugs
38.5 |  | Acceptance Test
38.6 |  | Report Acceptance Test
38.7 |  | Defect tracking
38.8 |  | Fix bugs
MAINTAINING
39 | Monitor and Controlling
39.1 |  | Team meeting
39.2 |  | Mentor meeting
39.3 |  | Manage Change
39.4 |  | Manage Risk
39.5 |  | Customer meeting
40 | Deploy |  |  |  | 5
40.1 |  | User guide
40.2 |  | Installation guide