## Sheet1
WEEK | ID | TASK | TYPE | DATE ASSIGN | ESTIMATE | ACTUAL | DUE-DATE | ASSIGN TO | STATUS
1 | 1 | Develop Team rule & policy | Kick-off | 2016-04-10 | 2 | 2 | 2016-04-10 | HaiTran | Complete
1 | 2 | Develop Team rule & policy | Kick-off | 2016-04-10 | 4 | 2 | 2016-04-10 | HienNguyen | Complete
1 | 3 | Develop Team rule & policy | Kick-off | 2016-04-10 | 1 | 2 | 2016-04-10 | KhoiNguyen | Complete | Complete
1 | 4 | Develop Team rule & policy | Kick-off | 2016-04-10 | 3 | 2 | 2016-04-10 | MinhDoan | Complete | Pending
1 | 5 | Develop Team rule & policy | Kick-off | 2016-04-10 | 3 | 2 | 2016-04-10 | TaiNguyen | Complete | Not implemented
1 | 6 | Develop Team rule & policy | Kick-off | 2016-04-10 | 2 | 2 | 2016-04-10 | XuanThaiHien | Complete
1 | 7 | Develop Team Charter | Kick-off | 2016-05-10 | 4 | 3 | 2016-06-10 | HienNguyen | Complete
1 | 8 | Develop Project Charter | Kick-off | 2016-06-10 | 3 | 2 | 2016-06-10 | HienNguyen | Complete
1 | 9 | Define Process Decision | Kick-off | 2016-07-10 | 2 | 1 | 2016-07-10 | HaiTran | Complete
1 | 10 | Define Process Decision | Kick-off | 2016-07-10 | 3 | 1 | 2016-07-10 | HienNguyen | Complete
1 | 11 | Define Process Decision | Kick-off | 2016-07-10 | 2 | 2 | 2016-07-10 | KhoiNguyen | Complete
1 | 12 | Define Process Decision | Kick-off | 2016-07-10 | 4 | 3 | 2016-07-10 | MinhDoan | Complete
1 | 13 | Define Process Decision | Kick-off | 2016-07-10 | 3 | 4 | 2016-07-10 | TaiNguyen | Complete
1 | 14 | Define Process Decision | Kick-off | 2016-07-10 | 3 | 5 | 2016-07-10 | XuanThaiHien | Complete
1 | 15 | Define SWOT technology | Kick-off | 2016-07-10 | 3 | 2 | 2016-08-10 | KhoiNguyen | Complete
1 | 16 | Define SWOT Project | Kick-off | 2016-08-10 | 2 | 3 | 2016-09-10 | TaiNguyen | Complete
2 | 1 | Update Project Charter | Kick-off | 2016-11-10 | 4 | 2 | 2016-12-10 | HienNguyen | Complete
2 | 2 | Define SWOT individual | Kick-off | 13/10/2016 | 2 | 1 | 13/10/2016 | HienNguyen | Complete
2 | 3 | Define SWOT individual | Kick-off | 13/10/2016 | 1 | 1 | 13/10/2016 | HaiTran | Complete
2 | 4 | Define SWOT individual | Kick-off | 13/10/2016 | 2 | 2 | 13/10/2016 | MinhDoan | Complete
2 | 5 | Define SWOT individual | Kick-off | 13/10/2016 | 2 | 2 | 13/10/2016 | KhoiNguyen | Complete
2 | 6 | Define SWOT individual | Kick-off | 13/10/2016 | 2 | 1 | 13/10/2016 | TaiNguyen | Complete
2 | 7 | Define SWOT individual | Kick-off | 13/10/2016 | 2 | 1 | 13/10/2016 | XuanThaiHien | Complete
2 | 8 | Update Process Decision | Kick-off | 14/10/2016 | 3 | 4 | 15/10/2016 | TaiNguyen | Complete
3 | 1 | Define effort log template | Planning | 18/10/2016 | 1 | 0.5 | 18/10/2016 | HaiTran | Complete
3 | 2 | Define weekly report template | Planning | 18/10/2016 | 1 | 0.5 | 18/10/2016 | HaiTran | Complete
3 | 3 | Define project plan template | Planning | 18/10/2016 | 4 | 3 | 19/10/2016 | HienNguyen | Complete
3 | 4 | Define configuration template | Planning | 18/10/2016 | 3 | 3 | 19/10/2016 | KhoiNguyen | Complete
3 | 5 | Define communication plan template | Planning | 18/10/2016 | 2 | 2 | 19/10/2016 | HienNguyen | Complete
3 | 6 | Define change management template | Planning | 18/10/2016 | 5 | 6 | 20/10/2016 | MinhDoan | Complete
3 | 7 | Define measurement plan template | Planning | 18/10/2016 | 3 | 2.5 | 19/10/2016 | TaiNguyen | Complete
3 | 8 | Define risk management plan template | Planning | 19/10/2016 | 3 | 3 | 19/10/2016 | XuanThaiHien | Complete
3 | 9 | Define WBS template | Planning | 20/10/2016 | 2 | 3 | 20/10/2016 | HaiTran | Complete
3 | 10 | Define requirement management plan template | Planning | 20/10/2016 | 2 | 2 | 21/10/2016 | HaiTran | Complete
3 | 11 | Define achitecture and design plan template | Planning | 21/10/2016 | 3 | 2 | 21/10/2016 | HienNguyen | Complete
4 | 1 | Define test plan template | Planning | 25/10/2016 | 6 | 5 | 26/10/2016 | XuanThaiHien | Complete
4 | 2 | Define vision and scope template | Planning | 25/10/2016 | 4 | 3 | 25/10/2016 | MinhDoan | Complete
4 | 3 | Define concept of operation template | Planning | 25/10/2016 | 5 | 3 | 26/10/2016 | KhoiNguyen | Complete
4 | 4 | Define SRS template | Planning | 25/10/2016 | 4 | 4 | 26/10/2016 | MinhDoan | Complete
4 | 5 | Define detail design template | Planning | 25/10/2016 | 5 | 3 | 26/10/2016 | TaiNguyen | Complete
4 | 6 | Define function testcase template | Planning | 25/10/2016 | 2 | 2 | 25/10/2016 | HienNguyen | Complete
4 | 7 | Define user acceptance testcase template | Planning | 25/10/2016 | 4 | 5 | 26/10/2016 | HaiTran | Complete
4 | 8 | Define test report template | Planning | 27/10/2016 | 3 | 3 | 28/10/2016 | XuanThaiHien | Complete
4 | 9 | Develop Work Break Down Structure | Planning | 26/10/2016 | 4 | 4 | 28/10/2016 | TaiNguyen | Complete
4 | 10 | Develop Requirement Plan | Planning | 27/10/2016 | 4 | 6 | 29/10/2016 | HaiTran | Complete
4 | 11 | Develop Implement Plan | Planning | 27/10/2016 | 4 | 2 | 29/10/2016 | HienNguyen | Complete
4 | 12 | Develop Implement Plan | Planning | 27/10/2016 | 4 | 2 | 29/10/2016 | KhoiNguyen | Complete
4 | 13 | Develop Architecture and Design Plan | Planning | 27/10/2016 | 6 | 5 | 29/10/2016 | HienNguyen | Complete
5 | 1 | Develop Configuration Plan | Planning | 2016-01-11 | 4 | 6 | 2016-03-11 | KhoiNguyen | Complete
5 | 2 | Develop Test Plan | Planning | 2016-01-11 | 5 | 8 | 2016-04-11 | XuanThaiHien | Complete
5 | 3 | Develop Development Process | Planning | 2016-01-11 | 5 | 4 | 2016-03-11 | TaiNguyen | Complete
5 | 4 | Develop Schedule | Planning | 2016-01-11 | 3 | 6 | 2016-03-11 | HienNguyen | Complete
5 | 5 | Develop Estimation | Planning | 2016-01-11 | 4 | 5 | 2016-04-11 | HaiTran | Complete
5 | 6 | Develop Training Plan | Planning | 2016-03-11 | 3 | 3 | 2016-05-11 | TaiNguyen | Complete
5 | 7 | Develop Master Plan | Planning | 2016-02-11 | 2 | 3 | 2016-04-11 | HienNguyen | Complete
5 | 8 | Gather Question List | Planning | 2016-03-11 | 2 | 2 | 2016-04-11 | MinhDoan | Complete
6 | 1 | Modify Requirement Plan | Planning | 2016-08-11 | 3 | 2 | 2016-10-11 | HaiTran | Complete
6 | 2 | Develop Change Management Plan | Planning | 2016-08-11 | 4 | 6 | 2016-11-11 | MinhDoan | Complete
6 | 3 | Develop Risk Management Plan | Planning | 2016-08-11 | 3 | 2 | 2016-11-11 | XuanThaiHien | Complete
6 | 4 | Develop Change Management Plan | Planning | 2016-08-11 | 5 | 3 | 2016-11-11 | XuanThaiHien | Complete
6 | 5 | Develop Risk Management Plan | Planning | 2016-08-11 | 4 | 5 | 2016-11-11 | MinhDoan | Complete
6 | 6 | Modify Work Break Down Structure | Planning | 2016-08-11 | 3 | 4 | 2016-10-11 | HienNguyen | Complete
6 | 7 | Modify Configuration Plan | Planning | 2016-08-11 | 2 | 3 | 2016-10-11 | KhoiNguyen | Complete
6 | 8 | Develop Measurement plan | Planning | 2016-08-11 | 4 | 5 | 2016-11-11 | TaiNguyen | Complete
7 | 1 | Gather Requirement from customer | Requirement | 15/11/2016 | 2 | 1 | 15/11/2016 | HienNguyen | Complete
7 | 2 | Gather Requirement from customer | Requirement | 15/11/2016 | 2 | 1 | 15/11/2016 | HaiTran | Complete
7 | 3 | Gather Requirement from customer | Requirement | 15/11/2016 | 2 | 1 | 15/11/2016 | TaiNguyen | Complete
7 | 4 | Gather Requirement from customer | Requirement | 15/11/2016 | 2 | 1 | 15/11/2016 | KhoiNguyen | Complete
7 | 5 | Gather Requirement from customer | Requirement | 15/11/2016 | 2 | 1 | 15/11/2016 | MinhDoan | Complete
7 | 6 | Gather Requirement from customer | Requirement | 15/11/2016 | 2 | 1 | 15/11/2016 | XuanThaiHien | Complete
7 | 7 | Develop Business workflow "Manage Accounts" function | Requirement | 16/11/2016 | 4 | 5 | 18/11/2016 | HaiTran | Pending
7 | 8 | Develop Business workflow "Manage News" function | Requirement | 16/11/2016 | 6 | 4 | 18/11/2016 | HaiTran | Pending
7 | 9 | Develop Business workflow "Manage Banners" function | Requirement | 16/11/2016 | 3 | 2 | 18/11/2016 | TaiNguyen | Pending
7 | 10 | Develop Business workflow "Manage Pop-ups" function | Requirement | 16/11/2016 | 3 | 1 | 18/11/2016 | TaiNguyen | Pending
7 | 11 | Develop Business workflow "Manage Q&A" function | Requirement | 16/11/2016 | 5 | 6 | 18/11/2016 | KhoiNguyen | Pending
7 | 12 | Develop Business workflow "Manage Homepage" function | Requirement | 16/11/2016 | 6 | 8 | 18/11/2016 | HienNguyen | Pending
7 | 13 | Develop Business workflow "Manage Languages" function | Requirement | 16/11/2016 | 1 | 0.5 | 18/11/2016 | KhoiNguyen | Pending
7 | 14 | Develop Business workflow "Manage Categories " function | Requirement | 16/11/2016 | 6 | 5 | 18/11/2016 | MinhDoan | Pending
7 | 15 | Develop Business workflow "Manage Examination " function | Requirement | 16/11/2016 | 5 | 3 | 18/11/2016 | XuanThaiHien | Pending
8 | 1 | Define Business Requirements | Requirement | 22/11/2016 | 4 | 3 | 24/11/2016 | MinhDoan | Complete
8 | 2 | Define Vision of the soulution | Requirement | 22/11/2016 | 5 | 5 | 24/11/2016 | HienNguyen | Complete
8 | 3 | Define Scope and Limitations | Requirement | 22/11/2016 | 3 | 4 | 23/11/2016 | KhoiNguyen | Complete
8 | 4 | Define Business Context | Requirement | 22/11/2016 | 3 | 3 | 23/11/2016 | XuanThaiHien | Complete
8 | 5 | Define Current System | Requirement | 22/11/2016 | 2 | 1 | 23/11/2016 | TaiNguyen | Complete
8 | 6 | Define Proposed System | Requirement | 22/11/2016 | 4 | 6 | 24/11/2016 | HaiTran | Complete
8 | 7 | Define Context Diagram | Requirement | 22/11/2016 | 3 | 2 | 23/11/2016 | TaiNguyen | Complete
8 | 8 | Define Environment System | Requirement | 24/11/2016 | 3 | 3 | 25/11/2016 | MinhDoan | Complete
8 | 9 | Define Justification of Changes | Requirement | 24/11/2016 | 2 | 3 | 25/11/2016 | KhoiNguyen | Complete
8 | 10 | Define Summary of impacts | Requirement | 24/11/2016 | 2 | 4 | 25/11/2016 | HienNguyen | Complete
8 | 11 | Define analysis summarizing future system | Requirement | 24/11/2016 | 3 | 3 | 25/11/2016 | HaiTran | Complete
8 | 12 | Develop prototype for website | Requirement | 24/11/2016 | 6 | 7 | 26/11/2016 | TaiNguyen | Complete
9 | 1 | Write Usecase description "Manage Accounts" Function | Requirement | 29/11/2016 | 4 | 5 | 2016-01-12 | HienNguyen | Complete
9 | 2 | Write Usecase description "Manage News" Function | Requirement | 29/11/2016 | 4 | 6 | 2016-01-12 | HaiTran | Complete
9 | 3 | Write Usecase description "Manage Homepage" Function | Requirement | 29/11/2016 | 3 | 5 | 2016-01-12 | TaiNguyen | Complete
9 | 4 | Write Usecase description "Manage Q&A" Function | Requirement | 29/11/2016 | 3 | 4 | 2016-01-12 | KhoiNguyen | Complete
9 | 5 | Write Usecase description "Manage Banners" Function | Requirement | 29/11/2016 | 3 | 3 | 2016-01-12 | MinhDoan | Complete
9 | 6 | Write Usecase description "Manage Pop-ups Function | Requirement | 29/11/2016 | 2 | 2 | 2016-01-12 | MinhDoan | Complete
9 | 7 | Write Usecase description "Manage Categories" Function | Requirement | 29/11/2016 | 5 | 4 | 2016-01-12 | HaiTran | Complete
9 | 8 | Write Usecase description "Manage Languages" Function | Requirement | 29/11/2016 | 2 | 1 | 2016-01-12 | KhoiNguyen | Complete
9 | 9 | Write Usecase description "Manage Examination" Function | Requirement | 29/11/2016 | 3 | 2 | 2016-01-12 | XuanThaiHien | Complete
9 | 10 | Draw Usecase Diagram "Manage Accouts" Function | Requirement | 2016-01-12 | 3 | 2 | 2016-02-12 | HienNguyen | Complete
9 | 11 | Draw Usecase Diagram "Manage News" Function | Requirement | 2016-01-12 | 4 | 4 | 2016-02-12 | HaiTran | Complete
9 | 12 | Draw Usecase Diagram "Manage Q&A" Function | Requirement | 2016-01-12 | 2 | 2 | 2016-02-12 | TaiNguyen | Complete
9 | 13 | Draw Usecase Diagram "Manage Homepage" Function | Requirement | 2016-01-12 | 3 | 2 | 2016-02-12 | KhoiNguyen | Complete
9 | 14 | Draw Usecase Diagram "Manage Banners" Function | Requirement | 2016-01-12 | 3 | 2 | 2016-02-12 | MinhDoan | Complete
9 | 15 | Draw Usecase Diagram "Manage Pop-ups" Function | Requirement | 2016-01-12 | 2 | 2 | 2016-02-12 | MinhDoan | Complete
9 | 16 | Draw Usecase Diagram "Manage Languages" Function | Requirement | 2016-01-12 | 1 | 0.5 | 2016-02-12 | HaiTran | Complete
9 | 17 | Draw Usecase Diagram "Manage Categories" Function | Requirement | 2016-01-12 | 3 | 2 | 2016-02-12 | KhoiNguyen | Complete
9 | 18 | Draw Usecase Diagram "Manage Examination" Function | Requirement | 2016-01-12 | 3 | 4 | 2016-02-12 | XuanThaiHien | Complete
10 | 1 | Define Product Functions | Requirement | 2016-06-12 | 2 | 3 | 2016-07-12 | MinhDoan
10 | 2 | Define user classes and characteristics | Requirement | 2016-06-12 | 3 | 3 | 2016-07-12 | HienNguyen
10 | 3 | Define Operating environment | Requirement | 2016-06-12 | 2 | 1 | 2016-07-12 | TaiNguyen
10 | 4 | Define Business constraint | Requirement | 2016-06-12 | 1 | 1 | 2016-07-12 | KhoiNguyen
10 | 5 | Research about technical constraint | Requirement | 2016-06-12 | 3 | 3 | 2016-07-12 | TaiNguyen
10 | 6 | Define Business rules | Requirement | 2016-06-12 | 2 | 1 | 2016-07-12 | XuanThaiHien
10 | 7 | Develop UI "Manage Accounts" Function | Requirement | 2016-07-12 | 5 | 5 | 2016-09-12 | HaiTran
10 | 8 | Develop UI "Manage News" Function | Requirement | 2016-07-12 | 4 | 6 | 2016-09-12 | TaiNguyen
10 | 9 | Develop UI "Manage Q&A" Function | Requirement | 2016-07-12 | 4 | 3 | 2016-09-12 | HienNguyen
10 | 10 | Develop UI "Manage Homepage" Function | Requirement | 2016-07-12 | 5 | 7 | 2016-09-12 | KhoiNguyen
10 | 11 | Develop UI "Manage Banners" Function | Requirement | 2016-07-12 | 2 | 2 | 2016-09-12 | MinhDoan
10 | 12 | Develop UI "Manage Pop-ups" Function | Requirement | 2016-07-12 | 2 | 1 | 2016-09-12 | MinhDoan
10 | 13 | Develop UI "Manage Languages" Function | Requirement | 2016-07-12 | 2 | 1 | 2016-09-12 | KhoiNguyen
10 | 14 | Develop UI "Manage Categories" Function | Requirement | 2016-07-12 | 3 | 4 | 2016-09-12 | HaiTran
10 | 15 | Develop UI "Manage Examination" Function | Requirement | 2016-07-12 | 3 | 2 | 2016-09-12 | XuanThaiHien
10 | 16 | Define Quality Attribute | Requirement | 2016-06-12 | 4 | 3 | 2016-07-12 | HaiTran
14 | 1 | Review usecase description | Requirement | 2017-02-01 | 4 | 3 | 2017-03-01 | HaiTran | Complete
14 | 2 | Draw static view detailed | Architect | 2017-03-01 | 2 | 1 | 2017-04-01 | HaiTran | Pending
14 | 3 | Update requirement | Requirement | 2017-04-01 | 2 | 3 | 2017-06-01 | HaiTran | Complete
14 | 4 | Update usecase | Requirement | 2017-06-01 | 3 | 3 | 2017-06-01 | HaiTran | Complete
14 | 5 | Update dynamic view lv 0 | Architect | 2017-02-01 | 4 | 2 | 2017-03-01 | HienNguyen | Pending
14 | 6 | Research pattern 3 layers in dynamic view | Architect | 2017-03-01 | 3 | 2 | 2017-04-01 | HienNguyen | Complete
14 | 7 | Update usecase | Requirement | 2017-04-01 | 5 | 3 | 2017-06-01 | HienNguyen | Complete
14 | 8 | Research pattern 3 layers in dynamic view | Architect | 2017-02-01 | 2 | 1 | 2017-03-01 | KhoiNguyen | Complete
14 | 9 | Update dynamic view lv 0 | Architect | 2017-04-01 | 2 | 4 | 2017-04-01 | KhoiNguyen | Pending
14 | 10 | Update document structure | Planning | 2017-05-01 | 3 | 3 | 2017-06-01 | KhoiNguyen | Complete
14 | 11 | Draw static view | Architect | 2017-01-01 | 4 | 3 | 2017-03-01 | TaiNguyen | Complete
14 | 12 | Update Static view | Architect | 2017-03-01 | 2 | 3 | 2017-04-01 | TaiNguyen | Pending
14 | 13 | Update usecase | Requirement | 2017-04-01 | 2 | 2 | 2017-06-01 | TaiNguyen | Complete
14 | 14 | Draw physical view | Architect | 2017-02-01 | 2 | 2.5 | 2017-03-01 | MinhDoan | Pending
14 | 15 | Fix physical view | Architect | 2017-04-01 | 2 | 1 | 2017-04-01 | MinhDoan | Pending
14 | 16 | Research tactics for quality attributes | Architect | 2017-05-01 | 3 | 4 | 2017-06-01 | MinhDoan | Complete
14 | 17 | Update usecase | Requirement | 2017-06-01 | 2 | 1 | 2017-06-01 | MinhDoan | Complete
14 | 18 | Research tactics for physical view | Architect | 2017-02-01 | 1 | 2 | 2017-03-01 | XuanThaiHien | Pending
14 | 19 | Tactics performance, usability for physical view | Architect | 2017-03-01 | 5 | 2 | 2017-04-01 | XuanThaiHien | Complete
14 | 20 | Draw physical view draft | Architect | 2017-02-01 | 4 | 2 | 2017-03-01 | XuanThaiHien | Pending
14 | 21 | Apply tactics performance, usability for physical view | Architect | 2017-03-01 | 1 | 2 | 2017-04-01 | XuanThaiHien | Pending
15 | 1 | Update Usecase | Requirement | 2017-09-01 | 5 | 4 | 2017-10-01 | HaiTran | Complete
15 | 2 | Review Usecase descriptioin | Requirement | 2017-11-01 | 6 | 3 | 2017-11-01 | HaiTran | Complete
15 | 3 | Update Process Requirement Development | Planning | 2017-12-01 | 3 | 2 | 2017-12-01 | HaiTran | Complete
15 | 4 | Research Static view | Architect | 2017-12-01 | 3 | 2 | 2017-12-01 | HaiTran | Complete
15 | 5 | Update usecase diagram | Requirement | 14/1/2017 | 2 | 1 | 15/1/2017 | HaiTran | Complete
15 | 6 | Update Function list usecase | Requirement | 15/1/2017 | 1 | 1 | 15/1/2017 | HaiTran | Complete
15 | 7 | Validate "Manage Banners","Manage Languages" usecase description | Requirement | 15/1/2017 | 1 | 1 | 15/1/2017 | HaiTran | Complete
15 | 8 | Review Requirement | Requirement | 2017-10-01 | 3 | 2 | 2017-11-01 | HienNguyen | Complete
15 | 9 | Update usecase description | Requirement | 2017-11-01 | 4 | 3 | 2017-11-01 | HienNguyen | Complete
15 | 10 | Modify architecture and design process | Architect | 2017-11-01 | 2 | 3 | 2017-11-01 | HienNguyen | Complete
15 | 11 | Modify dynamic view | Architect | 2017-12-01 | 2 | 1 | 2017-12-01 | HienNguyen | Complete
15 | 12 | Research Redis engine | Architect | 15/1/2017 | 1 | 1 | 15/1/2017 | HienNguyen | Complete
15 | 13 | Review requirement | Requirement | 2017-10-01 | 4 | 2 | 2017-10-01 | KhoiNguyen | Complete
15 | 14 | Update usecase | Requirement | 2017-11-01 | 5 | 4 | 2017-12-01 | KhoiNguyen | Complete
15 | 15 | Update configuration process | Planning | 2017-11-01 | 3 | 1 | 2017-11-01 | KhoiNguyen | Complete
15 | 16 | Modify Dynamic view | Architect | 2017-12-01 | 3 | 2 | 2017-12-01 | KhoiNguyen | Pending
15 | 17 | Validate SRS document | Requirement | 14/1/2017 | 2 | 2 | 14/1/2017 | KhoiNguyen | Complete
15 | 18 | Validate "Manage Q&A","Manage Popups" usecase description | Requirement | 15/1/2017 | 2 | 3 | 15/1/2017 | KhoiNguyen | Complete
15 | 19 | Review requirement | Requirement | 2017-10-01 | 4 | 2 | 2017-10-01 | TaiNguyen | Complete
15 | 20 | Update usecase | Requirement | 2017-11-01 | 3 | 2 | 2017-11-01 | TaiNguyen | Complete
15 | 21 | Update development process | Planning | 2017-11-01 | 3 | 2 | 2017-11-01 | TaiNguyen | Complete
15 | 22 | Update measurement and control process | Planning | 2017-12-01 | 2 | 2 | 2017-12-01 | TaiNguyen | Complete
15 | 23 | Modify static view | Architect | 2017-12-01 | 2 | 3 | 2017-12-01 | TaiNguyen | Pending
15 | 24 | Research elastic search engine | Architect | 15/1/2017 | 1 | 3 | 15/1/2017 | TaiNguyen | Complete
15 | 25 | Review requirement | Requirement | 2017-10-01 | 4 | 2 | 2017-10-01 | MinhDoan | Complete
15 | 26 | Update usecase | Requirement | 2017-11-01 | 3 | 2 | 2017-11-01 | MinhDoan | Complete
15 | 27 | Update change management process | Planning | 2017-11-01 | 3 | 4 | 2017-11-01 | MinhDoan | Complete
15 | 28 | Modify Physical view | Architect | 2017-12-01 | 2 | 3 | 2017-12-01 | MinhDoan | Pending
15 | 29 | Validate ConOps document | Requirement | 14/1/2017 | 2 | 1 | 14/1/2017 | MinhDoan | Complete
15 | 30 | Validate Vision and Scope document | Requirement | 14/1/2017 | 1 | 1 | 15/1/2017 | MinhDoan | Complete
15 | 31 | Write "Manage Homepage" usecase description | Requirement | 15/1/2017 | 1 | 2 | 15/1/2017 | MinhDoan | Complete
15 | 32 | Review requirement | Requirement | 2017-10-01 | 3 | 2 | 2017-10-01 | XuanThaiHien | Complete
15 | 33 | Update document structure | Planning | 2017-11-01 | 2 | 2 | 2017-11-01 | XuanThaiHien | Complete
15 | 34 | Modify Physical view | Architect | 2017-12-01 | 2 | 3 | 2017-12-01 | XuanThaiHien | Pending
15 | 35 | Validate "Manage News","Manage Account" usecase description | Requirement | 15/1/2017 | 3 | 4 | 15/1/2017 | XuanThaiHien | Complete
16 | 1 | Demo connect redis engine | Architect | 16/1/2017 | 6 | 4 | 18/1/2017 | HienNguyen | Complete
16 | 2 | Demo index data into mongo db | Architect | 16/1/2017 | 4 | 3 | 18/1/2017 | TaiNguyen | Pending
16 | 3 | Demo connect relastic search with mongo db | Architect | 16/1/2017 | 5 | 4 | 18/1/2017 | TaiNguyen | Pending
16 | 4 | Demo function "Create Account" using angular 2, mongodb | Coding | 18/1/2017 |  |  |  | XuanThaiHien | Not implemented
16 | 5 | Demo function "Create Account" using angular 2, mongodb | Coding | 18/1/2017 | 4 | 6 | 20/1/2017 | KhoiNguyen | Pending
16 | 7 | Update schedule | Planning | 16/1/2017 | 3 | 2 | 18/1/2017 | HaiTran | Complete
16 | 8 | Update static view | Architect | 18/1/2017 | 4 | 4 | 19/1/2017 | HaiTran | Pending
16 | 9 | Update physical view | Architect | 18/1/2017 | 5 | 4 | 19/1/2017 | HienNguyen | Complete
16 | 10 | Update physical view | Architect | 18/1/2017 | 5 | 5 | 19/1/2017 | HaiTran | Complete
17 | 1 | Modify Physical view | Architect | 23/1/2017 |  |  | 24/1/2017 | HienNguyen
17 | 2 | Modify Static view | Architect | 23/1/2017 |  |  | 24/1/2017 | HaiTran
17 | 3 | Modify Dynamic view | Architect | 23/1/2017 |  |  | 24/1/2017 | KhoiNguyen
17 | 4 | Code Function "Login" | Coding | 23/1/2017 |  |  | 24/1/2017 | TaiNguyen
17 | 5 | Code Function "Login" | Coding | 23/1/2017 |  |  | 24/1/2017 | MinhDoan
17 | 6 | Code Function "Login" | Coding | 23/1/2017 |  |  | 24/1/2017 | XuanThaiHien | Not implemented
17 | 7 | Code Function "Login" | Coding | 23/1/2017 |  |  | 24/1/2017 | HienNguyen
17 | 8 | Code Function "Login" | Coding | 23/1/2017 |  |  | 24/1/2017 | HaiTran
17 | 9 | Code Function "Login" | Coding | 23/1/2017 |  |  | 24/1/2017 | KhoiNguyen
17 | 10 | Modify Database design | Detailed Design | 23/1/2017 |  |  | 24/1/2017 | TaiNguyen