## Sheet1
WEEK | ID | TASK | PHASE | DATE ASSIGN | ESTIMATE | ACTUAL | DUE-DATE | ASSIGN TO | STATUS
1 | 1 | Team Meeting | Kick-off | 2016-03-10 | 1 | 1 | 2016-03-10 | HaiTran | Complete
1 | 2 | Team Meeting | Kick-off | 2016-03-10 | 1 | 1 | 2016-03-10 | KhoiNguyen | Complete
1 | 3 | Team Meeting | Kick-off | 2016-03-10 | 1 | 1 | 2016-03-10 | TaiNguyen | Complete | W1 | 87 | Complete
1 | 4 | Team Meeting | Kick-off | 2016-03-10 | 1 | 1 | 2016-03-10 | HienNguyen | Complete | W2 | 85 | Pending
1 | 5 | Team Meeting | Kick-off | 2016-03-10 | 1 | 1 | 2016-03-10 | XuanThaiHien | Complete | W3 | 122 | Not implemented
1 | 6 | Team Meeting | Kick-off | 2016-03-10 | 1 | 1 | 2016-03-10 | MinhDoan | Complete | W4 | 113
1 | 7 | Develop Team rule & policy | Kick-off | 2016-03-10 | 2 | 2 | 2016-04-10 | HaiTran | Complete | W5 | 202
1 | 8 | Develop Team rule & policy | Kick-off | 2016-03-10 | 4 | 2 | 2016-04-10 | HienNguyen | Complete | W6 | 123
1 | 9 | Develop Team rule & policy | Kick-off | 2016-03-10 | 1 | 2 | 2016-04-10 | KhoiNguyen | Complete | W7 | 127
1 | 10 | Develop Team rule & policy | Kick-off | 2016-03-10 | 3 | 2 | 2016-04-10 | MinhDoan | Complete | W8 | 135
1 | 11 | Develop Team rule & policy | Kick-off | 2016-03-10 | 3 | 2 | 2016-04-10 | TaiNguyen | Complete | W9 | 175
1 | 12 | Develop Team rule & policy | Kick-off | 2016-03-10 | 2 | 2 | 2016-04-10 | XuanThaiHien | Complete | W10 | 180
1 | 13 | Review Team rule & policy | Kick-off | 2016-05-10 | 3 | 4 | 2016-05-10 | HaiTran | Complete | W11 | 164
1 | 14 | Review Team rule & policy | Kick-off | 2016-05-10 | 3 | 4 | 2016-05-10 | HienNguyen | Complete | W12 | 171
1 | 15 | Review Team rule & policy | Kick-off | 2016-05-10 | 3 | 4 | 2016-05-10 | KhoiNguyen | Complete | W13 | 203
1 | 16 | Review Team rule & policy | Kick-off | 2016-05-10 | 3 | 4 | 2016-05-10 | MinhDoan | Complete | W14 | 181.5
1 | 17 | Review Team rule & policy | Kick-off | 2016-05-10 | 3 | 4 | 2016-05-10 | TaiNguyen | Complete | W15 | 90
1 | 18 | Review Team rule & policy | Kick-off | 2016-05-10 | 3 | 4 | 2016-05-10 | XuanThaiHien | Complete | W16 | 219
1 | 19 | Mentor Meeting | Kick-off | 2016-06-10 | 2 | 3 | 2016-06-10 | HaiTran | Complete | W17 | 201
1 | 20 | Mentor Meeting | Kick-off | 2016-06-10 | 2 | 3 | 2016-06-10 | HienNguyen | Complete | W18 | Holiday
1 | 21 | Mentor Meeting | Kick-off | 2016-06-10 | 2 | 3 | 2016-06-10 | KhoiNguyen | Complete | W19 | 212
1 | 22 | Mentor Meeting | Kick-off | 2016-06-10 | 2 | 3 | 2016-06-10 | MinhDoan | Complete | W20 | 189
1 | 23 | Mentor Meeting | Kick-off | 2016-06-10 | 2 | 3 | 2016-06-10 | TaiNguyen | Complete
1 | 24 | Mentor Meeting | Kick-off | 2016-06-10 | 2 | 3 | 2016-06-10 | XuanThaiHien | Complete
1 | 25 | Develop Team Charter | Kick-off | 2016-06-10 | 4 | 3 | 2016-07-10 | HienNguyen | Complete
1 | 26 | Develop Project Charter | Kick-off | 2016-06-10 | 3 | 2 | 2016-07-10 | HienNguyen | Complete
1 | 27 | Define Process Decision | Kick-off | 2016-07-10 | 2 | 3 | 2016-08-10 | HaiTran | Complete
1 | 28 | Define Process Decision | Kick-off | 2016-07-10 | 3 | 4 | 2016-08-10 | HienNguyen | Complete
1 | 29 | Define Process Decision | Kick-off | 2016-07-10 | 2 | 5 | 2016-08-10 | KhoiNguyen | Complete
1 | 30 | Define Process Decision | Kick-off | 2016-07-10 | 4 | 3 | 2016-08-10 | MinhDoan | Complete
1 | 31 | Define Process Decision | Kick-off | 2016-07-10 | 3 | 5 | 2016-08-10 | TaiNguyen | Complete
1 | 32 | Define Process Decision | Kick-off | 2016-07-10 | 3 | 2 | 2016-08-10 | XuanThaiHien | Complete
2 | 1 | Team Meeting | Kick-off | 2016-10-10 | 1 | 2 | 2016-10-10 | HaiTran | Complete
2 | 2 | Team Meeting | Kick-off | 2016-10-10 | 1 | 2 | 2016-10-10 | HienNguyen | Complete
2 | 3 | Team Meeting | Kick-off | 2016-10-10 | 1 | 2 | 2016-10-10 | KhoiNguyen | Complete
2 | 4 | Team Meeting | Kick-off | 2016-10-10 | 1 | 2 | 2016-10-10 | MinhDoan | Complete
2 | 5 | Team Meeting | Kick-off | 2016-10-10 | 1 | 2 | 2016-10-10 | TaiNguyen | Complete
2 | 6 | Team Meeting | Kick-off | 2016-10-10 | 1 | 2 | 2016-10-10 | XuanThaiHien | Complete
2 | 7 | Review Process Decision | Kick-off | 2016-11-10 | 2 | 5 | 2016-11-10 | HaiTran | Complete
2 | 8 | Review Process Decision | Kick-off | 2016-11-10 | 3 | 5 | 2016-11-10 | HienNguyen | Complete
2 | 9 | Review Process Decision | Kick-off | 2016-11-10 | 3 | 5 | 2016-11-10 | KhoiNguyen | Complete
2 | 10 | Review Process Decision | Kick-off | 2016-11-10 | 2 | 5 | 2016-11-10 | MinhDoan | Complete
2 | 11 | Review Process Decision | Kick-off | 2016-11-10 | 3 | 5 | 2016-11-10 | TaiNguyen | Complete
2 | 12 | Review Process Decision | Kick-off | 2016-11-10 | 3 | 5 | 2016-11-10 | XuanThaiHien | Complete
2 | 13 | Mentor Meeting | Kick-off | 2016-12-10 | 1 | 2 | 2016-12-10 | HaiTran | Complete
2 | 14 | Mentor Meeting | Kick-off | 2016-12-10 | 1 | 2 | 2016-12-10 | HienNguyen | Complete
2 | 15 | Mentor Meeting | Kick-off | 2016-12-10 | 1 | 2 | 2016-12-10 | KhoiNguyen | Complete
2 | 16 | Mentor Meeting | Kick-off | 2016-12-10 | 1 | 2 | 2016-12-10 | MinhDoan | Complete
2 | 17 | Mentor Meeting | Kick-off | 2016-12-10 | 1 | 2 | 2016-12-10 | TaiNguyen | Complete
2 | 18 | Mentor Meeting | Kick-off | 2016-12-10 | 1 | 2 | 2016-12-10 | XuanThaiHien | Complete
2 | 19 | Define SWOT technology | Kick-off | 2016-12-10 | 3 | 2 | 13/10/2016 | KhoiNguyen | Complete
2 | 20 | Define SWOT Project | Kick-off | 2016-12-10 | 2 | 3 | 13/10/2016 | TaiNguyen | Complete
2 | 21 | Review SWOT technology | Kick-off | 13/10/2016 | 1 | 3 | 13/10/2016 | TaiNguyen | Complete
2 | 22 | Review SWOT Project | Kick-off | 13/10/2016 | 2 | 3 | 13/10/2016 | HaiTran | Complete
2 | 23 | Review SWOT technology | Kick-off | 13/10/2016 | 2 | 3 | 13/10/2016 | KhoiNguyen | Complete
2 | 24 | Review SWOT Project | Kick-off | 13/10/2016 | 1 | 3 | 13/10/2016 | TaiNguyen | Complete
2 | 25 | Update Project Charter | Kick-off | 13/10/2016 | 4 | 2 | 14/12/2016 | HienNguyen | Complete
2 | 26 | Define SWOT individual | Kick-off | 13/10/2016 | 2 | 1 | 14/10/2016 | HienNguyen | Complete
2 | 27 | Define SWOT individual | Kick-off | 13/10/2016 | 1 | 1 | 14/10/2016 | HaiTran | Complete
2 | 28 | Define SWOT individual | Kick-off | 13/10/2016 | 2 | 2 | 14/10/2016 | MinhDoan | Complete
2 | 29 | Define SWOT individual | Kick-off | 13/10/2016 | 2 | 2 | 14/10/2016 | KhoiNguyen | Complete
2 | 30 | Define SWOT individual | Kick-off | 13/10/2016 | 2 | 1 | 14/10/2016 | TaiNguyen | Complete
2 | 31 | Define SWOT individual | Kick-off | 13/10/2016 | 2 | 1 | 14/10/2016 | XuanThaiHien | Complete
2 | 32 | Update Process Decision | Kick-off | 14/10/2016 | 3 | 4 | 15/10/2016 | TaiNguyen | Complete
3 | 1 | Mentor Meeting | Planning | 17/10/2016 | 2 | 5 | 17/10/2016 | HaiTran | Complete
3 | 2 | Mentor Meeting | Planning | 17/10/2016 | 2 | 5 | 17/10/2016 | MinhDoan | Complete
3 | 3 | Mentor Meeting | Planning | 17/10/2016 | 2 | 5 | 17/10/2016 | KhoiNguyen | Complete
3 | 4 | Mentor Meeting | Planning | 17/10/2016 | 2 | 5 | 17/10/2016 | TaiNguyen | Complete
3 | 5 | Mentor Meeting | Planning | 17/10/2016 | 2 | 5 | 17/10/2016 | XuanThaiHien | Complete
3 | 6 | Mentor Meeting | Planning | 17/10/2016 | 2 | 5 | 17/10/2016 | TaiNguyen | Complete
3 | 7 | Team Meeting | Planning | 18/10/2016 | 2 | 2 | 18/10/2016 | HaiTran | Complete
3 | 8 | Team Meeting | Planning | 18/10/2016 | 2 | 2 | 18/10/2016 | MinhDoan | Complete
3 | 9 | Team Meeting | Planning | 18/10/2016 | 2 | 2 | 18/10/2016 | KhoiNguyen | Complete
3 | 10 | Team Meeting | Planning | 18/10/2016 | 2 | 2 | 18/10/2016 | TaiNguyen | Complete
3 | 11 | Team Meeting | Planning | 18/10/2016 | 2 | 2 | 18/10/2016 | XuanThaiHien | Complete
3 | 12 | Team Meeting | Planning | 18/10/2016 | 2 | 2 | 18/10/2016 | TaiNguyen | Complete
3 | 13 | Define effort log template | Planning | 18/10/2016 | 1 | 2 | 20/10/2016 | HaiTran | Complete
3 | 14 | Define weekly report template | Planning | 18/10/2016 | 1 | 2 | 20/10/2016 | HaiTran | Complete
3 | 3 | Define project plan template | Planning | 18/10/2016 | 4 | 6 | 20/10/2016 | HienNguyen | Complete
3 | 4 | Define configuration template | Planning | 18/10/2016 | 3 | 6 | 20/10/2016 | KhoiNguyen | Complete
3 | 5 | Define communication plan template | Planning | 18/10/2016 | 2 | 3 | 20/10/2016 | HienNguyen | Complete
3 | 6 | Define change management template | Planning | 18/10/2016 | 5 | 8 | 20/10/2016 | MinhDoan | Complete
3 | 7 | Define measurement plan template | Planning | 18/10/2016 | 3 | 5 | 20/10/2016 | TaiNguyen | Complete
3 | 8 | Define risk management plan template | Planning | 19/10/2016 | 3 | 4 | 20/10/2016 | XuanThaiHien | Complete
3 | 9 | Define WBS template | Planning | 19/10/2016 | 4 | 4 | 20/10/2016 | HaiTran | Complete
3 | 10 | Define requirement management plan template | Planning | 19/10/2016 | 3 | 5 | 20/10/2016 | HaiTran | Complete
3 | 11 | Define achitecture and design plan template | Planning | 19/10/2016 | 3 | 3 | 20/10/2016 | HienNguyen | Complete
3 | 12 | Review Project Plan Template | Planning | 20/10/2016 | 3 | 4 | 21/10/2016 | HaiTran | Complete
3 | 13 | Review Configuration Template | Planning | 20/10/2016 | 4 | 4 | 21/10/2016 | TaiNguyen | Complete
3 | 14 | Review Communication Plan Template | Planning | 20/10/2016 | 3 | 1 | 21/10/2016 | KhoiNguyen | Complete
3 | 15 | Review Change Management Template | Planning | 20/10/2016 | 5 | 5 | 21/10/2016 | HienNguyen | Complete
3 | 16 | Review Measurement Plan Template | Planning | 20/10/2016 | 2 | 4 | 21/10/2016 | MinhDoan | Complete
3 | 17 | Review Risk Management Plan Template | Planning | 20/10/2016 | 3 | 4 | 21/10/2016 | TaiNguyen | Complete
3 | 18 | Review Requirement Management Plan Template | Planning | 20/10/2016 | 3 | 3 | 21/10/2016 | XuanThaiHien | Complete
3 | 19 | Review Architecture and Design Plan Template | Planning | 20/10/2016 | 6 | 5 | 21/10/2016 | HaiTran | Complete
3 | 20 | Update Configuration Plan Tempate | Planning | 22/10/2016 | 2 | 2 | 22/10/2016 | KhoiNguyen | Complete
4 | 1 | Team Meeting | Planning | 24/10/2016 | 3 | 3 | 24/10/2016 | HaiTran | Complete
4 | 2 | Team Meeting | Planning | 24/10/2016 | 3 | 3 | 24/10/2016 | MinhDoan | Complete
4 | 3 | Team Meeting | Planning | 24/10/2016 | 3 | 3 | 24/10/2016 | KhoiNguyen | Complete
4 | 4 | Team Meeting | Planning | 24/10/2016 | 3 | 3 | 24/10/2016 | TaiNguyen | Complete
4 | 5 | Team Meeting | Planning | 24/10/2016 | 3 | 3 | 24/10/2016 | XuanThaiHien | Complete
4 | 6 | Team Meeting | Planning | 24/10/2016 | 3 | 3 | 24/10/2016 | TaiNguyen | Complete
4 | 7 | Define test plan template | Planning | 25/10/2016 | 6 | 8 | 27/10/2016 | XuanThaiHien | Complete
4 | 8 | Define vision and scope template | Planning | 25/10/2016 | 3 | 4 | 27/10/2016 | MinhDoan | Complete
4 | 9 | Define concept of operation template | Planning | 25/10/2016 | 3 | 5 | 27/10/2016 | KhoiNguyen | Complete
4 | 10 | Define SRS template | Planning | 25/10/2016 | 4 | 4 | 27/10/2016 | MinhDoan | Complete
4 | 11 | Define detail design template | Planning | 25/10/2016 | 3 | 5 | 27/10/2016 | TaiNguyen | Complete
4 | 12 | Define function testcase template | Planning | 25/10/2016 | 2 | 4 | 27/10/2016 | HienNguyen | Complete
4 | 13 | Define user acceptance testcase template | Planning | 25/10/2016 | 4 | 5 | 27/10/2016 | HaiTran | Complete
4 | 14 | Define test report template | Planning | 25/10/2016 | 3 | 4 | 27/10/2016 | XuanThaiHien | Complete
4 | 15 | Review Test Plan Template | Planning | 28/10/2016 | 3 | 4 | 28/10/2016 | MinhDoan | Complete
4 | 16 | Review Vision and Scope Template | Planning | 28/10/2016 | 2 | 3 | 28/10/2016 | HaiTran | Complete
4 | 17 | Review Concept of Operation Template | Planning | 28/10/2016 | 4 | 3 | 28/10/2016 | MinhDoan | Complete
4 | 18 | Review SRS Template | Planning | 28/10/2016 | 3 | 3 | 28/10/2016 | TaiNguyen | Complete
4 | 19 | Update Vision and Scope Template | Planning | 28/10/2016 | 1 | 2 | 29/10/2016 | MinhDoan | Complete
4 | 20 | Update Concept of Operation Template | Planning | 28/10/2016 | 3 | 1 | 29/10/2016 | KhoiNguyen | Complete
4 | 21 | Update SRS Template | Planning | 28/10/2016 | 2 | 2 | 29/10/2016 | HienNguyen | Complete
4 | 22 | Develop Work Break Down Structure | Planning | 28/10/2016 | 8 | 6 | 29/10/2016 | TaiNguyen | Complete
4 | 23 | Develop Requirement Plan | Planning | 28/10/2016 | 10 | 9 | 29/10/2016 | HaiTran | Complete
4 | 24 | Develop Implement Plan | Planning | 28/10/2016 | 9 | 7 | 29/10/2016 | HienNguyen | Complete
4 | 25 | Develop Implement Plan | Planning | 28/10/2016 | 8 | 5 | 29/10/2016 | KhoiNguyen | Complete
4 | 26 | Develop Architecture and Design Plan | Planning | 28/10/2016 | 14 | 11 | 29/10/2016 | HienNguyen | Complete
5 | 1 | Team Meeting | Planning | 31/10/2016 | 3 | 3 | 31/10/2016 | HaiTran | Complete
5 | 2 | Team Meeting | Planning | 31/10/2016 | 2 | 3 | 31/10/2016 | HienNguyen | Complete
5 | 3 | Team Meeting | Planning | 31/10/2016 | 3 | 3 | 31/10/2016 | TaiNguyen | Complete
5 | 4 | Team Meeting | Planning | 31/10/2016 | 1 | 3 | 31/10/2016 | MinhDoan | Complete
5 | 5 | Team Meeting | Planning | 31/10/2016 | 2 | 3 | 31/10/2016 | KhoiNguyen | Complete
5 | 6 | Team Meeting | Planning | 31/10/2016 | 2 | 3 | 31/10/2016 | XuanThaiHien | Complete
5 | 7 | Review Requirement Plan | Planning | 2016-01-11 | 5 | 2 | 2016-01-11 | TaiNguyen | Complete
5 | 8 | Review Requirement Plan | Planning | 2016-01-11 | 3 | 2 | 2016-01-11 | HaiTran | Complete
5 | 9 | Review Requirement Plan | Planning | 2016-01-11 | 5 | 2 | 2016-01-11 | XuanThaiHien | Complete
5 | 10 | Review Requirement Plan | Planning | 2016-01-11 | 4 | 2 | 2016-01-11 | MinhDoan | Complete
5 | 11 | Review Requirement Plan | Planning | 2016-01-11 | 3 | 2 | 2016-01-11 | KhoiNguyen | Complete
5 | 12 | Review Requirement Plan | Planning | 2016-01-11 | 4 | 2 | 2016-01-11 | HienNguyen | Complete
5 | 13 | Review Implement Plan | Planning | 2016-01-11 | 2 | 1 | 2016-01-11 | HaiTran | Complete
5 | 14 | Review Implement Plan | Planning | 2016-01-11 | 1 | 1 | 2016-01-11 | HienNguyen | Complete
5 | 15 | Review Implement Plan | Planning | 2016-01-11 | 2 | 1 | 2016-01-11 | TaiNguyen | Complete
5 | 16 | Review Implement Plan | Planning | 2016-01-11 | 2 | 1 | 2016-01-11 | MinhDoan | Complete
5 | 17 | Review Implement Plan | Planning | 2016-01-11 | 1 | 1 | 2016-01-11 | KhoiNguyen | Complete
5 | 18 | Review Implement Plan | Planning | 2016-01-11 | 2 | 1 | 2016-01-11 | XuanThaiHien | Complete
5 | 19 | Review Architecture and Design Plan | Planning | 2016-01-11 | 5 | 7 | 2016-01-11 | MinhDoan | Complete
5 | 20 | Review Architecture and Design Plan | Planning | 2016-01-11 | 5 | 7 | 2016-01-11 | HaiTran | Complete
5 | 21 | Review Architecture and Design Plan | Planning | 2016-01-11 | 6 | 7 | 2016-01-11 | TaiNguyen | Complete
5 | 22 | Review Architecture and Design Plan | Planning | 2016-01-11 | 5 | 7 | 2016-01-11 | KhoiNguyen | Complete
5 | 23 | Review Architecture and Design Plan | Planning | 2016-01-11 | 7 | 7 | 2016-01-11 | HienNguyen | Complete
5 | 24 | Review Architecture and Design Plan | Planning | 2016-01-11 | 6 | 7 | 2016-01-11 | XuanThaiHien | Complete
5 | 25 | Update Requirement Plan | Planning | 2016-02-11 | 4 | 5 | 2016-02-11 | HaiTran | Complete
5 | 26 | Update Implement Plan | Planning | 2016-02-11 | 3 | 2 | 2016-02-11 | KhoiNguyen | Complete
5 | 27 | Update Architecture and Design Plan | Planning | 2016-02-11 | 4 | 6 | 2016-02-11 | HaiTran | Complete
5 | 28 | Develop Configuration Plan | Planning | 2016-03-11 | 8 | 11 | 2016-05-11 | KhoiNguyen | Complete
5 | 29 | Develop Test Plan | Planning | 2016-03-11 | 9 | 12 | 2016-05-11 | XuanThaiHien | Complete
5 | 30 | Develop Software Development Process | Planning | 2016-03-11 | 6 | 9 | 2016-05-11 | TaiNguyen | Complete
5 | 31 | Develop Schedule | Planning | 2016-03-11 | 8 | 6 | 2016-05-11 | HienNguyen | Complete
5 | 32 | Develop Estimation | Planning | 2016-03-11 | 6 | 8 | 2016-04-11 | HaiTran | Complete
5 | 33 | Develop Training Plan | Planning | 2016-03-11 | 3 | 4 | 2016-05-11 | TaiNguyen | Complete
5 | 34 | Develop Master Plan | Planning | 2016-03-11 | 2 | 3 | 2016-04-11 | HienNguyen | Complete
5 | 35 | Gather Question List | Planning | 2016-03-11 | 2 | 2 | 2016-04-11 | MinhDoan | Complete
5 | 36 | Review Configuration Plan | Planning | 2016-04-11 | 3 | 5 | 2016-05-11 | HienNguyen | Complete
5 | 37 | Review Test Plan | Planning | 2016-04-11 | 4 | 3 | 2016-05-11 | MinhDoan | Complete
5 | 38 | Review Software Development Process | Planning | 2016-04-11 | 4 | 4 | 2016-05-11 | HaiTran | Complete
5 | 39 | Review Software Development Process | Planning | 2016-04-11 | 3 | 4 | 2016-05-11 | HienNguyen | Complete
5 | 40 | Review Software Development Process | Planning | 2016-04-11 | 5 | 4 | 2016-05-11 | KhoiNguyen | Complete
5 | 41 | Review Software Development Process | Planning | 2016-04-11 | 4 | 4 | 2016-05-11 | TaiNguyen | Complete
5 | 42 | Review Software Development Process | Planning | 2016-04-11 | 3 | 4 | 2016-05-11 | XuanThaiHien | Complete
5 | 43 | Review Software Development Process | Planning | 2016-04-11 | 3 | 4 | 2016-05-11 | MinhDoan | Complete
5 | 44 | Review Schedule | Planning | 2016-04-11 | 3 | 2 | 2016-05-11 | HaiTran | Complete
5 | 45 | Review Schedule | Planning | 2016-04-11 | 1 | 2 | 2016-05-11 | HienNguyen | Complete
5 | 46 | Review Schedule | Planning | 2016-04-11 | 2 | 2 | 2016-05-11 | KhoiNguyen | Complete
5 | 47 | Review Schedule | Planning | 2016-04-11 | 2 | 2 | 2016-05-11 | TaiNguyen | Complete
5 | 48 | Review Schedule | Planning | 2016-04-11 | 1 | 2 | 2016-05-11 | XuanThaiHien | Complete
5 | 49 | Review Schedule | Planning | 2016-04-11 | 1 | 2 | 2016-05-11 | MinhDoan | Complete
5 | 50 | Review Training Plan | Planning | 2016-04-11 | 2 | 2 | 2016-05-11 | HaiTran | Complete
5 | 51 | Review Training Plan | Planning | 2016-04-11 | 1 | 2 | 2016-05-11 | MinhDoan | Complete
5 | 52 | Review Training Plan | Planning | 2016-04-11 | 1 | 2 | 2016-05-11 | KhoiNguyen | Complete
5 | 53 | Review Training Plan | Planning | 2016-04-11 | 1 | 2 | 2016-05-11 | TaiNguyen | Complete
5 | 54 | Review Training Plan | Planning | 2016-04-11 | 2 | 2 | 2016-05-11 | XuanThaiHien | Complete
5 | 55 | Review Training Plan | Planning | 2016-04-11 | 1 | 2 | 2016-05-11 | HienNguyen | Complete
6 | 1 | Team Meeting | Planning | 2016-07-11 | 2 | 2 | 2016-07-11 | HaiTran | Complete
6 | 2 | Team Meeting | Planning | 2016-07-11 | 3 | 2 | 2016-07-11 | MinhDoan | Complete
6 | 3 | Team Meeting | Planning | 2016-07-11 | 1 | 2 | 2016-07-11 | KhoiNguyen | Complete
6 | 4 | Team Meeting | Planning | 2016-07-11 | 3 | 2 | 2016-07-11 | TaiNguyen | Complete
6 | 5 | Team Meeting | Planning | 2016-07-11 | 2 | 2 | 2016-07-11 | XuanThaiHien | Complete
6 | 6 | Team Meeting | Planning | 2016-07-11 | 3 | 2 | 2016-07-11 | HienNguyen | Complete
6 | 7 | Mentor Meeting | Planning | 2016-08-11 | 2 | 3 | 2016-08-11 | HaiTran | Complete
6 | 8 | Mentor Meeting | Planning | 2016-08-11 | 3 | 3 | 2016-08-11 | MinhDoan | Complete
6 | 9 | Mentor Meeting | Planning | 2016-08-11 | 2 | 3 | 2016-08-11 | KhoiNguyen | Complete
6 | 10 | Mentor Meeting | Planning | 2016-08-11 | 3 | 3 | 2016-08-11 | TaiNguyen | Complete
6 | 11 | Mentor Meeting | Planning | 2016-08-11 | 3 | 3 | 2016-08-11 | XuanThaiHien | Complete
6 | 12 | Mentor Meeting | Planning | 2016-08-11 | 2 | 3 | 2016-08-11 | HienNguyen | Complete
6 | 13 | Training Technical | Planning | 2016-08-11 |  | 2 | 2016-08-11 | HaiTran | Complete
6 | 14 | Training Technical | Planning | 2016-08-11 |  | 2 | 2016-08-11 | MinhDoan | Complete
6 | 15 | Training Technical | Planning | 2016-08-11 |  | 2 | 2016-08-11 | KhoiNguyen | Complete
6 | 16 | Training Technical | Planning | 2016-08-11 |  | 2 | 2016-08-11 | TaiNguyen | Complete
6 | 17 | Training Technical | Planning | 2016-08-11 |  | 2 | 2016-08-11 | XuanThaiHien | Complete
6 | 18 | Training Technical | Planning | 2016-08-11 |  | 2 | 2016-08-11 | HienNguyen | Complete
6 | 19 | Update Software Development Process | Planning | 2016-08-11 | 3 | 2 | 2016-08-11 | HaiTran | Complete
6 | 20 | Update Schedule | Planning | 2016-08-11 | 3 | 2 | 2016-08-11 | HienNguyen | Complete
6 | 21 | Update Training Plan | Planning | 2016-08-11 | 2 | 1 | 2016-08-11 | TaiNguyen | Complete
6 | 22 | Develop Change Management Plan | Planning | 2016-08-11 | 10 | 14 | 2016-11-11 | MinhDoan | Complete
6 | 23 | Develop Risk Management Plan | Planning | 2016-08-11 | 16 | 15 | 2016-11-11 | XuanThaiHien | Complete
6 | 24 | Develop Measurement plan | Planning | 2016-08-11 | 4 | 5 | 2016-11-11 | TaiNguyen | Complete
6 | 25 | Review Change Management Plan | Planning | 2016-12-11 | 3 | 3 | 2016-12-11 | HaiTran | Complete
6 | 26 | Review Change Management Plan | Planning | 2016-12-11 | 2 | 3 | 2016-12-11 | MinhDoan | Complete
6 | 27 | Review Change Management Plan | Planning | 2016-12-11 | 3 | 3 | 2016-12-11 | KhoiNguyen | Complete
6 | 28 | Review Change Management Plan | Planning | 2016-12-11 | 4 | 3 | 2016-12-11 | TaiNguyen | Complete
6 | 29 | Review Change Management Plan | Planning | 2016-12-11 | 4 | 3 | 2016-12-11 | XuanThaiHien | Complete
6 | 30 | Review Change Management Plan | Planning | 2016-12-11 | 3 | 3 | 2016-12-11 | HienNguyen | Complete
6 | 31 | Review Risk Management Plan | Planning | 2016-12-11 | 3 | 2 | 2016-12-11 | HaiTran | Complete
6 | 32 | Review Risk Management Plan | Planning | 2016-12-11 | 3 | 2 | 2016-12-11 | MinhDoan | Complete
6 | 33 | Review Risk Management Plan | Planning | 2016-12-11 | 4 | 2 | 2016-12-11 | KhoiNguyen | Complete
6 | 34 | Review Risk Management Plan | Planning | 2016-12-11 | 2 | 2 | 2016-12-11 | TaiNguyen | Complete
6 | 35 | Review Risk Management Plan | Planning | 2016-12-11 | 3 | 2 | 2016-12-11 | XuanThaiHien | Complete
6 | 36 | Review Risk Management Plan | Planning | 2016-12-11 | 2 | 2 | 2016-12-11 | HienNguyen | Complete
6 | 37 | Review Measurement Plan | Planning | 2016-12-11 | 1 | 2 | 2016-12-11 | HaiTran | Complete
6 | 38 | Review Measurement Plan | Planning | 2016-12-11 | 2 | 2 | 2016-12-11 | MinhDoan | Complete
6 | 39 | Review Measurement Plan | Planning | 2016-12-11 | 2 | 2 | 2016-12-11 | KhoiNguyen | Complete
6 | 40 | Review Measurement Plan | Planning | 2016-12-11 | 3 | 2 | 2016-12-11 | TaiNguyen | Complete
6 | 41 | Review Measurement Plan | Planning | 2016-12-11 | 2 | 2 | 2016-12-11 | XuanThaiHien | Complete
6 | 42 | Review Measurement Plan | Planning | 2016-12-11 | 3 | 2 | 2016-12-11 | HienNguyen | Complete
7 | 1 | Team Meeting | Planning | 14/11/2016 |  | 3 | 14/11/2016 | HaiTran | Complete
7 | 2 | Team Meeting | Planning | 14/11/2016 |  | 3 | 14/11/2016 | MinhDoan | Complete
7 | 3 | Team Meeting | Planning | 14/11/2016 |  | 3 | 14/11/2016 | KhoiNguyen | Complete
7 | 4 | Team Meeting | Planning | 14/11/2016 |  | 3 | 14/11/2016 | TaiNguyen | Complete
7 | 5 | Team Meeting | Planning | 14/11/2016 |  | 3 | 14/11/2016 | XuanThaiHien | Complete
7 | 6 | Team Meeting | Planning | 14/11/2016 |  | 3 | 14/11/2016 | HienNguyen | Complete
7 | 7 | Training Technical | Planning | 15/11/2016 | 2 | 2 | 15/11/2016 | HaiTran | Complete
7 | 8 | Training Technical | Planning | 15/11/2016 | 2 | 2 | 15/11/2016 | MinhDoan | Complete
7 | 9 | Training Technical | Planning | 15/11/2016 | 2 | 2 | 15/11/2016 | KhoiNguyen | Complete
7 | 10 | Training Technical | Planning | 15/11/2016 | 2 | 2 | 15/11/2016 | TaiNguyen | Complete
7 | 11 | Training Technical | Planning | 15/11/2016 | 2 | 2 | 15/11/2016 | XuanThaiHien | Complete
7 | 12 | Training Technical | Planning | 15/11/2016 | 2 | 2 | 15/11/2016 | HienNguyen | Complete
7 | 13 | Update Change Management Plan | Planning | 16/11/2016 | 7 | 5 | 17/11/2016 | XuanThaiHien | Complete
7 | 14 | Update Change Management Plan | Planning | 16/11/2016 | 8 | 7 | 17/11/2016 | MinhDoan | Complete
7 | 15 | Update Risk Management Plan | Planning | 16/11/2016 | 6 | 8 | 17/11/2016 | HienNguyen | Complete
7 | 16 | Update Risk Management Plan | Planning | 16/11/2016 | 5 | 6 | 17/11/2016 | KhoiNguyen | Complete
7 | 17 | Update Measurement Plan | Planning | 16/11/2016 | 5 | 4 | 17/11/2016 | HaiTran | Complete
7 | 18 | Update Measurement Plan | Planning | 16/11/2016 | 6 | 4 | 17/11/2016 | TaiNguyen | Complete
7 | 19 | Presenstation | Planning | 17/11/2016 | 2 | 3 | 17/11/2016 | HaiTran | Complete
7 | 20 | Presenstation | Planning | 17/11/2016 | 2 | 3 | 17/11/2016 | HienNguyen | Complete
7 | 21 | Presenstation | Planning | 17/11/2016 | 2 | 3 | 17/11/2016 | KhoiNguyen | Complete
7 | 22 | Presenstation | Planning | 17/11/2016 | 2 | 3 | 17/11/2016 | MinhDoan | Complete
7 | 23 | Presenstation | Planning | 17/11/2016 | 2 | 3 | 17/11/2016 | TaiNguyen | Complete
7 | 24 | Presenstation | Planning | 17/11/2016 | 2 | 3 | 17/11/2016 | XuanThaiHien | Complete
7 | 25 | Modify Requirement Plan | Planning | 18/11/2016 | 4 | 5 | 19/11/2016 | HaiTran | Complete
7 | 26 | Modify Architecture and design plan | Planning | 18/11/2016 | 3 | 6 | 19/11/2016 | HienNguyen | Complete
7 | 27 | Modify Risk Management plan | Planning | 18/11/2016 | 4 | 6 | 19/11/2016 | MinhDoan | Complete
7 | 28 | Modify Change Management plan | Planning | 18/11/2016 | 3 | 5 | 19/11/2016 | TaiNguyen | Complete
7 | 29 | Modify Configuration Plan | Planning | 18/11/2016 | 5 | 7 | 19/11/2016 | KhoiNguyen | Complete
7 | 30 | Modify Test plan | Planning | 18/11/2016 | 5 | 3 | 19/11/2016 | XuanThaiHien | Complete
7 | 31 | Update document structure | Planning | 18/11/2016 | 3 | 3 | 19/11/2016 | KhoiNguyen | Complete
7 | 32 | Update configuration process | Planning | 18/11/2016 | 3 | 1 | 19/11/2016 | KhoiNguyen | Complete
7 | 33 | Update development process | Planning | 18/11/2016 | 3 | 2 | 19/11/2016 | TaiNguyen | Complete
7 | 34 | Update measurement and control process | Planning | 18/11/2016 | 2 | 2 | 19/11/2016 | TaiNguyen | Complete
7 | 35 | Update change management process | Planning | 18/11/2016 | 2 | 1 | 19/11/2016 | XuanThaiHien | Complete
7 | 36 | Update document structure | Planning | 18/11/2016 | 2 | 2 | 19/11/2016 | HaiTran | Complete
7 | 37 | Update schedule | Planning | 18/11/2016 | 3 | 2 | 19/11/2016 | HaiTran | Complete
8 | 1 | Team Meeting | Requirement | 21/11/2016 | 2 | 3 | 21/11/2016 | HaiTran | Complete
8 | 2 | Team Meeting | Requirement | 21/11/2016 | 2 | 3 | 21/11/2016 | HienNguyen | Complete
8 | 3 | Team Meeting | Requirement | 21/11/2016 | 2 | 3 | 21/11/2016 | TaiNguyen | Complete
8 | 4 | Team Meeting | Requirement | 21/11/2016 | 2 | 3 | 21/11/2016 | MinhDoan | Complete
8 | 5 | Team Meeting | Requirement | 21/11/2016 | 2 | 3 | 21/11/2016 | XuanThaiHien | Complete
8 | 6 | Team Meeting | Requirement | 21/11/2016 | 2 | 3 | 21/11/2016 | KhoiNguyen | Complete
8 | 7 | Mentor Meeting | Requirement | 21/11/2016 | 3 | 3 | 21/11/2016 | HaiTran | Complete
8 | 8 | Mentor Meeting | Requirement | 21/11/2016 | 3 | 3 | 21/11/2016 | HienNguyen | Complete
8 | 9 | Mentor Meeting | Requirement | 21/11/2016 | 3 | 3 | 21/11/2016 | TaiNguyen | Complete
8 | 10 | Mentor Meeting | Requirement | 21/11/2016 | 3 | 3 | 21/11/2016 | MinhDoan | Complete
8 | 11 | Mentor Meeting | Requirement | 21/11/2016 | 3 | 3 | 21/11/2016 | XuanThaiHien | Complete
8 | 12 | Mentor Meeting | Requirement | 21/11/2016 | 3 | 3 | 21/11/2016 | KhoiNguyen | Complete
8 | 13 | Training Technical | Requirement | 22/11/2016 | 2 | 2 | 22/11/2016 | HaiTran | Complete
8 | 14 | Training Technical | Requirement | 22/11/2016 | 2 | 2 | 22/11/2016 | HienNguyen | Complete
8 | 15 | Training Technical | Requirement | 22/11/2016 | 2 | 2 | 22/11/2016 | TaiNguyen | Complete
8 | 16 | Training Technical | Requirement | 22/11/2016 | 2 | 2 | 22/11/2016 | MinhDoan | Complete
8 | 17 | Training Technical | Requirement | 22/11/2016 | 2 | 2 | 22/11/2016 | XuanThaiHien | Complete
8 | 18 | Training Technical | Requirement | 22/11/2016 | 2 | 2 | 22/11/2016 | KhoiNguyen | Complete
8 | 19 | Customer Meeting | Requirement | 22/11/2016 | 3 | 2 | 22/11/2016 | HaiTran | Complete
8 | 20 | Customer Meeting | Requirement | 22/11/2016 | 3 | 2 | 22/11/2016 | HienNguyen | Complete
8 | 21 | Customer Meeting | Requirement | 22/11/2016 | 3 | 2 | 22/11/2016 | TaiNguyen | Complete
8 | 22 | Customer Meeting | Requirement | 22/11/2016 | 3 | 2 | 22/11/2016 | MinhDoan | Complete
8 | 23 | Customer Meeting | Requirement | 22/11/2016 | 3 | 2 | 22/11/2016 | XuanThaiHien | Complete
8 | 24 | Customer Meeting | Requirement | 22/11/2016 | 3 | 2 | 22/11/2016 | KhoiNguyen | Complete
8 | 25 | Analyze Requirement | Requirement | 22/11/2016 | 8 | 7 | 23/11/2016 | HienNguyen | Complete
8 | 26 | Analyze Requirement | Requirement | 22/11/2016 | 6 | 6 | 23/11/2016 | HaiTran | Complete
8 | 27 | Analyze Requirement | Requirement | 22/11/2016 | 9 | 7 | 23/11/2016 | MinhDoan | Complete
8 | 28 | Analyze Requirement | Requirement | 22/11/2016 | 8 | 6 | 23/11/2016 | KhoiNguyen | Complete
8 | 29 | Analyze Requirement | Requirement | 22/11/2016 | 7 | 7 | 23/11/2016 | TaiNguyen | Complete
8 | 30 | Analyze Requirement | Requirement | 22/11/2016 | 5 | 7 | 23/11/2016 | XuanThaiHien | Complete
8 | 31 | Develop Business workflow "Manage Accounts" function | Requirement | 22/11/2016 | 4 | 5 | 23/11/2016 | HaiTran | Pending
8 | 32 | Develop Business workflow "Manage News" function | Requirement | 24/11/2016 | 6 | 4 | 25/11/2016 | HaiTran | Pending
8 | 33 | Develop Business workflow "Manage Banners" function | Requirement | 24/11/2016 | 3 | 2 | 25/11/2016 | TaiNguyen | Pending
8 | 34 | Develop Business workflow "Manage Pop-ups" function | Requirement | 24/11/2016 | 3 | 1 | 25/11/2016 | TaiNguyen | Pending
8 | 35 | Develop Business workflow "Manage FAQ" function | Requirement | 24/11/2016 | 5 | 6 | 25/11/2016 | KhoiNguyen | Pending
8 | 36 | Develop Business workflow "Manage Homepage" function | Requirement | 24/11/2016 | 6 | 8 | 26/11/2016 | HienNguyen | Pending
8 | 37 | Develop Business workflow "Manage Languages" function | Requirement | 24/11/2016 | 1 | 1 | 26/11/2016 | KhoiNguyen | Pending
8 | 38 | Develop Business workflow "Manage Categories " function | Requirement | 24/11/2016 | 6 | 5 | 26/11/2016 | MinhDoan | Pending
8 | 39 | Develop Business workflow "Manage Examination " function | Requirement | 24/11/2016 | 5 | 3 | 26/11/2016 | XuanThaiHien | Pending
9 | 1 | Team Meeting | Requirement | 28/11/2016 |  | 3 | 28/11/2016 | HaiTran | Complete
9 | 2 | Team Meeting | Requirement | 28/11/2016 |  | 3 | 28/11/2016 | HienNguyen | Complete
9 | 3 | Team Meeting | Requirement | 28/11/2016 |  | 3 | 28/11/2016 | MinhDoan | Complete
9 | 4 | Team Meeting | Requirement | 28/11/2016 |  | 3 | 28/11/2016 | TaiNguyen | Complete
9 | 5 | Team Meeting | Requirement | 28/11/2016 |  | 3 | 28/11/2016 | KhoiNguyen | Complete
9 | 6 | Team Meeting | Requirement | 28/11/2016 |  | 3 | 28/11/2016 | XuanThaiHien | Complete
9 | 7 | Review Business Workflow "Manage Account"function | Requirement | 28/11/2016 | 4 | 5 | 28/11/2016 | HienNguyen | Complete
9 | 8 | Review Business Workflow "Manage Account"function | Requirement | 28/11/2016 | 3 | 5 | 28/11/2016 | HaiTran | Complete
9 | 9 | Review Business Workflow "Manage News" function | Requirement | 28/11/2016 | 4 | 4 | 28/11/2016 | MinhDoan | Complete
9 | 10 | Review Business Workflow "Manage News" function | Requirement | 28/11/2016 | 3 | 4 | 28/11/2016 | KhoiNguyen | Complete
9 | 11 | Review Business Workflow "Manage Banners" function | Requirement | 28/11/2016 | 3 | 3 | 28/11/2016 | TaiNguyen | Complete
9 | 12 | Review Business Workflow "Manage Banners" function | Requirement | 28/11/2016 | 2 | 3 | 28/11/2016 | XuanThaiHien | Complete
9 | 13 | Review Business Workflow "Manage Pop-ups" function | Requirement | 29/11/2016 | 3 | 2 | 29/11/2016 | MinhDoan | Complete
9 | 14 | Review Business Workflow "Manage Pop-ups" function | Requirement | 29/11/2016 | 2 | 2 | 29/11/2016 | XuanThaiHien | Complete
9 | 15 | Review Business Workflow "Manage FAQ" function | Requirement | 29/11/2016 | 4 | 2 | 29/11/2016 | KhoiNguyen | Complete
9 | 16 | Review Business Workflow "Manage FAQ" function | Requirement | 29/11/2016 | 3 | 2 | 29/11/2016 | HienNguyen | Complete
9 | 17 | Review Business Workflow "Manage Homepage" function | Requirement | 29/11/2016 | 3 | 5 | 29/11/2016 | TaiNguyen | Complete
9 | 18 | Review Business Workflow "Manage Homepage" function | Requirement | 29/11/2016 | 2 | 5 | 29/11/2016 | HaiTran | Complete
9 | 19 | Review Business Workflow "Manage Languages" function | Requirement | 29/11/2016 | 1 | 1 | 29/11/2016 | KhoiNguyen | Complete
9 | 20 | Review Business Workflow "Manage Languages" function | Requirement | 29/11/2016 | 1 | 1 | 29/11/2016 | HaiTran | Complete
9 | 21 | Review Business Workflow "Manage Categories " function | Requirement | 29/11/2016 | 3 | 4 | 29/11/2016 | TaiNguyen | Complete
9 | 22 | Review Business Workflow "Manage Categories " function | Requirement | 29/11/2016 | 4 | 4 | 29/11/2016 | HienNguyen | Complete
9 | 23 | Review Business Workflow "Manage Examination " function | Requirement | 29/11/2016 | 2 | 3 | 29/11/2016 | XuanThaiHien | Complete
9 | 24 | Review Business Workflow "Manage Examination " function | Requirement | 29/11/2016 | 3 | 3 | 29/11/2016 | MinhDoan | Complete
9 | 25 | Training Technical | Requirement | 29/11/2016 | 2 | 2 | 29/11/2016 | HaiTran | Complete
9 | 26 | Training Technical | Requirement | 29/11/2016 | 2 | 2 | 29/11/2016 | HienNguyen | Complete
9 | 27 | Training Technical | Requirement | 29/11/2016 | 2 | 2 | 29/11/2016 | KhoiNguyen | Complete
9 | 28 | Training Technical | Requirement | 29/11/2016 | 2 | 2 | 29/11/2016 | MinhDoan | Complete
9 | 29 | Training Technical | Requirement | 29/11/2016 | 2 | 2 | 29/11/2016 | TaiNguyen | Complete
9 | 30 | Training Technical | Requirement | 29/11/2016 | 2 | 2 | 29/11/2016 | XuanThaiHien | Complete
9 | 31 | Update Business workflow "Manage Accounts" function | Requirement | 30/11/2016 | 5 | 4 | 2016-01-12 | HaiTran | Complete
9 | 32 | Update Business workflow "Manage News" function | Requirement | 30/11/2016 | 5 | 7 | 2016-01-12 | HaiTran | Complete
9 | 33 | Update Business workflow "Manage Banners" function | Requirement | 30/11/2016 | 3 | 4 | 2016-01-12 | TaiNguyen | Complete
9 | 34 | Update Business workflow "Manage Pop-ups" function | Requirement | 30/11/2016 | 3 | 2 | 2016-01-12 | TaiNguyen | Complete
9 | 35 | Update Business workflow "Manage FAQ" function | Requirement | 30/11/2016 | 4 | 5 | 2016-01-12 | KhoiNguyen | Complete
9 | 36 | Update Business workflow "Manage Homepage" function | Requirement | 30/11/2016 | 3 | 5 | 2016-01-12 | HienNguyen | Complete
9 | 37 | Update Business workflow "Manage Categories " function | Requirement | 30/11/2016 | 3 | 3 | 2016-01-12 | MinhDoan | Complete
9 | 38 | Update Business workflow "Manage Examination " function | Requirement | 30/11/2016 | 2 | 3 | 2016-01-12 | XuanThaiHien | Complete
9 | 39 | Define Business Requirements | Requirement | 2016-01-12 | 4 | 6 | 2016-01-12 | MinhDoan | Complete
9 | 40 | Define Vision of the soulution | Requirement | 2016-01-12 | 5 | 5 | 2016-01-12 | HienNguyen | Complete
9 | 41 | Define Scope and Limitations | Requirement | 2016-01-12 | 3 | 6 | 2016-01-12 | KhoiNguyen | Complete
9 | 42 | Define Business Context | Requirement | 2016-01-12 | 2 | 3 | 2016-01-12 | XuanThaiHien | Complete
9 | 43 | Define Current System | Requirement | 2016-01-12 | 2 | 1 | 2016-01-12 | TaiNguyen | Complete
9 | 44 | Define Proposed System | Requirement | 2016-01-12 | 4 | 2 | 2016-01-12 | HaiTran | Complete
9 | 45 | Define Context Diagram | Requirement | 2016-02-12 | 3 | 5 | 2016-03-12 | TaiNguyen | Complete
9 | 46 | Define Environment System | Requirement | 2016-02-12 | 4 | 3 | 2016-03-12 | MinhDoan | Complete
9 | 47 | Define Justification of Changes | Requirement | 2016-02-12 | 2 | 5 | 2016-03-12 | KhoiNguyen | Complete
9 | 48 | Define Summary of impacts | Requirement | 2016-02-12 | 2 | 4 | 2016-03-12 | HienNguyen | Complete
9 | 49 | Define analysis summarizing future system | Requirement | 2016-02-12 | 3 | 5 | 2016-03-12 | HaiTran | Complete
9 | 50 | Develop prototype for website | Requirement | 2016-02-12 | 6 | 9 | 2016-03-12 | TaiNguyen | Complete
10 | 1 | Team Meeting | Requirement | 2016-05-12 | 2 | 2 | 2016-05-12 | HienNguyen | Complete
10 | 2 | Team Meeting | Requirement | 2016-05-12 | 2 | 2 | 2016-05-12 | HaiTran | Complete
10 | 3 | Team Meeting | Requirement | 2016-05-12 | 2 | 2 | 2016-05-12 | KhoiNguyen | Complete
10 | 4 | Team Meeting | Requirement | 2016-05-12 | 2 | 2 | 2016-05-12 | TaiNguyen | Complete
10 | 5 | Team Meeting | Requirement | 2016-05-12 | 2 | 2 | 2016-05-12 | MinhDoan | Complete
10 | 6 | Team Meeting | Requirement | 2016-05-12 | 2 | 2 | 2016-05-12 | XuanThaiHien | Complete
10 | 7 | Review Business Requirements | Requirement | 2016-05-12 | 3 | 4 | 2016-05-12 | MinhDoan | Complete
10 | 8 | Review Business Requirements | Requirement | 2016-05-12 | 2 | 4 | 2016-05-12 | KhoiNguyen | Complete
10 | 9 | Review Vision of the soulution | Requirement | 2016-05-12 | 3 | 2 | 2016-05-12 | HaiTran | Complete
10 | 10 | Review Vision of the soulution | Requirement | 2016-05-12 | 2 | 2 | 2016-05-12 | HienNguyen | Complete
10 | 11 | Review Scope and Limitations | Requirement | 2016-05-12 | 2 | 2 | 2016-05-12 | XuanThaiHien | Complete
10 | 12 | Review Scope and Limitations | Requirement | 2016-05-12 | 2 | 2 | 2016-05-12 | MinhDoan | Complete
10 | 13 | Review Business Context | Requirement | 2016-05-12 | 3 | 5 | 2016-05-12 | TaiNguyen | Complete
10 | 14 | Review Business Context | Requirement | 2016-05-12 | 4 | 5 | 2016-05-12 | MinhDoan | Complete
10 | 15 | Review Proposed System | Requirement | 2016-06-12 | 4 | 6 | 2016-06-12 | HienNguyen | Complete
10 | 16 | Review Proposed System | Requirement | 2016-06-12 | 5 | 6 | 2016-06-12 | TaiNguyen | Complete
10 | 17 | Review Context Diagram | Requirement | 2016-06-12 | 6 | 5 | 2016-06-12 | KhoiNguyen | Complete
10 | 18 | Review Context Diagram | Requirement | 2016-06-12 | 5 | 5 | 2016-06-12 | HienNguyen | Complete
10 | 19 | Review prototype for website | Requirement | 2016-06-12 | 6 | 6 | 2016-06-12 | HaiTran | Complete
10 | 20 | Review prototype for website | Requirement | 2016-06-12 | 5 | 6 | 2016-06-12 | TaiNguyen | Complete
10 | 21 | Collect into Concept of Operation document | Requirement | 2016-06-12 | 1 | 1 | 2016-06-12 | MinhDoan | Complete
10 | 22 | Training Technical | Requirement | 2016-06-12 | 2 | 2 | 2016-06-12 | HienNguyen | Complete
10 | 23 | Training Technical | Requirement | 2016-06-12 | 2 | 2 | 2016-06-12 | HaiTran | Complete
10 | 24 | Training Technical | Requirement | 2016-06-12 | 2 | 2 | 2016-06-12 | TaiNguyen | Complete
10 | 25 | Training Technical | Requirement | 2016-06-12 | 2 | 2 | 2016-06-12 | KhoiNguyen | Complete
10 | 26 | Training Technical | Requirement | 2016-06-12 | 2 | 2 | 2016-06-12 | MinhDoan | Complete
10 | 27 | Training Technical | Requirement | 2016-06-12 | 2 | 2 | 2016-06-12 | XuanThaiHien | Complete
10 | 28 | Customer Meeting | Requirement | 2016-07-12 | 2 | 3 | 2016-07-12 | HienNguyen | Complete
10 | 29 | Customer Meeting | Requirement | 2016-07-12 | 2 | 3 | 2016-07-12 | HaiTran | Complete
10 | 30 | Customer Meeting | Requirement | 2016-07-12 | 2 | 3 | 2016-07-12 | TaiNguyen | Complete
10 | 31 | Customer Meeting | Requirement | 2016-07-12 | 2 | 3 | 2016-07-12 | KhoiNguyen | Complete
10 | 32 | Customer Meeting | Requirement | 2016-07-12 | 2 | 3 | 2016-07-12 | MinhDoan | Complete
10 | 33 | Customer Meeting | Requirement | 2016-07-12 | 2 | 3 | 2016-07-12 | XuanThaiHien | Complete
10 | 34 | Write Usecase description "Manage Accounts" Function | Requirement | 2016-07-12 | 7 | 8 | 2016-08-12 | HienNguyen | Complete
10 | 35 | Write Usecase description "Manage News" Function | Requirement | 2016-07-12 | 8 | 10 | 2016-08-12 | HaiTran | Complete
10 | 36 | Write Usecase description "Manage Homepage" Function | Requirement | 2016-07-12 | 5 | 5 | 2016-08-12 | TaiNguyen | Complete
10 | 37 | Write Usecase description "Manage Q&A" Function | Requirement | 2016-07-12 | 3 | 5 | 2016-08-12 | KhoiNguyen | Complete
10 | 38 | Write Usecase description "Manage Banners" Function | Requirement | 2016-07-12 | 4 | 4 | 2016-08-12 | MinhDoan | Complete
10 | 39 | Write Usecase description "Manage Pop-ups Function | Requirement | 2016-07-12 | 3 | 4 | 2016-08-12 | MinhDoan | Complete
10 | 40 | Write Usecase description "Manage Categories" Function | Requirement | 2016-07-12 | 5 | 5 | 2016-08-12 | HaiTran | Complete
10 | 41 | Write Usecase description "Manage Languages" Function | Requirement | 2016-07-12 | 2 | 2 | 2016-08-12 | KhoiNguyen | Complete
10 | 42 | Write Usecase description "Manage Examination" Function | Requirement | 2016-07-12 | 3 | 3 | 2016-08-12 | XuanThaiHien | Complete
10 | 43 | Draw Usecase Diagram "Manage Accouts" Function | Requirement | 2016-08-12 | 5 | 5 | 2016-09-12 | HienNguyen | Complete
10 | 44 | Draw Usecase Diagram "Manage News" Function | Requirement | 2016-08-12 | 4 | 4 | 2016-09-12 | HaiTran | Complete
10 | 45 | Draw Usecase Diagram "Manage Q&A" Function | Requirement | 2016-08-12 | 4 | 4 | 2016-09-12 | TaiNguyen | Complete
10 | 46 | Draw Usecase Diagram "Manage Homepage" Function | Requirement | 2016-08-12 | 4 | 3 | 2016-09-12 | KhoiNguyen | Complete
10 | 47 | Draw Usecase Diagram "Manage Banners" Function | Requirement | 2016-08-12 | 3 | 3 | 2016-09-12 | MinhDoan | Complete
10 | 48 | Draw Usecase Diagram "Manage Pop-ups" Function | Requirement | 2016-08-12 | 2 | 3 | 2016-09-12 | MinhDoan | Complete
10 | 49 | Draw Usecase Diagram "Manage Languages" Function | Requirement | 2016-08-12 | 1 | 1 | 2016-09-12 | HaiTran | Complete
10 | 50 | Draw Usecase Diagram "Manage Categories" Function | Requirement | 2016-08-12 | 3 | 4 | 2016-09-12 | KhoiNguyen | Complete
10 | 51 | Draw Usecase Diagram "Manage Examination" Function | Requirement | 2016-08-12 | 3 | 4 | 2016-09-12 | XuanThaiHien | Complete
11 | 1 | Team Meeting | Requirement | 2016-12-12 | 2 | 2 | 2016-12-12 | MinhDoan | Complete
11 | 2 | Team Meeting | Requirement | 2016-12-12 | 2 | 2 | 2016-12-12 | HaiTran | Complete
11 | 3 | Team Meeting | Requirement | 2016-12-12 | 2 | 2 | 2016-12-12 | HienNguyen | Complete
11 | 4 | Team Meeting | Requirement | 2016-12-12 | 2 | 2 | 2016-12-12 | TaiNguyen | Complete
11 | 5 | Team Meeting | Requirement | 2016-12-12 | 2 | 2 | 2016-12-12 | KhoiNguyen | Complete
11 | 6 | Team Meeting | Requirement | 2016-12-12 | 2 | 2 | 2016-12-12 | XuanThaiHien | Complete
11 | 7 | Review Usecase description "Manage Accounts" Function | Requirement | 2016-12-12 | 5 | 4 | 2016-12-12 | HaiTran | Complete
11 | 8 | Review Usecase description "Manage Accounts" Function | Requirement | 2016-12-12 | 4 | 4 | 2016-12-12 | HienNguyen | Complete
11 | 9 | Review Usecase description "Manage News" Function | Requirement | 2016-12-12 | 6 | 4 | 2016-12-12 | KhoiNguyen | Complete
11 | 10 | Review Usecase description "Manage News" Function | Requirement | 2016-12-12 | 4 | 5 | 2016-12-12 | TaiNguyen | Complete
11 | 11 | Review Usecase description "Manage Homepage" Function | Requirement | 2016-12-12 | 3 | 4 | 2016-12-12 | MinhDoan | Complete
11 | 12 | Review Usecase description "Manage Homepage" Function | Requirement | 2016-12-12 | 3 | 2 | 2016-12-12 | XuanThaiHien | Pending
11 | 13 | Review Usecase description "Manage Q&A" Function | Requirement | 13/12/2016 | 4 | 3 | 13/12/2016 | TaiNguyen | Complete
11 | 14 | Review Usecase description "Manage Q&A" Function | Requirement | 13/12/2016 | 3 | 3 | 13/12/2016 | MinhDoan | Complete
11 | 15 | Review Usecase description "Manage Banners" Function | Requirement | 13/12/2016 | 2 | 3 | 13/12/2016 | HaiTran | Complete
11 | 16 | Review Usecase description "Manage Banners" Function | Requirement | 13/12/2016 | 3 | 2 | 13/12/2016 | KhoiNguyen | Complete
11 | 17 | Review Usecase description "Manage Pop-ups Function | Requirement | 13/12/2016 | 2 | 2 | 13/12/2016 | XuanThaiHien | Complete
11 | 18 | Review Usecase description "Manage Pop-ups Function | Requirement | 13/12/2016 | 3 | 2 | 13/12/2016 | HienNguyen | Complete
11 | 19 | Review Usecase description "Manage Categories" Function | Requirement | 13/12/2016 | 4 | 5 | 13/12/2016 | TaiNguyen | Complete
11 | 20 | Review Usecase description "Manage Categories" Function | Requirement | 13/12/2016 | 5 | 3 | 13/12/2016 | HaiTran | Complete
11 | 21 | Review Usecase description "Manage Languages" Function | Requirement | 13/12/2016 | 2 | 1 | 13/12/2016 | KhoiNguyen | Complete
11 | 22 | Review Usecase description "Manage Languages" Function | Requirement | 13/12/2016 | 1 | 1 | 13/12/2016 | MinhDoan | Complete
11 | 23 | Review Usecase description "Manage Examination" Function | Requirement | 13/12/2016 | 3 | 4 | 13/12/2016 | HienNguyen | Complete
11 | 24 | Training Technical | Requirement | 13/12/2016 | 2 | 2 | 13/12/2016 | HaiTran | Complete
11 | 25 | Training Technical | Requirement | 13/12/2016 | 2 | 2 | 13/12/2016 | HienNguyen | Complete
11 | 26 | Training Technical | Requirement | 13/12/2016 | 2 | 2 | 13/12/2016 | MinhDoan | Complete
11 | 27 | Training Technical | Requirement | 13/12/2016 | 2 | 2 | 13/12/2016 | TaiNguyen | Complete
11 | 28 | Training Technical | Requirement | 13/12/2016 | 2 | 2 | 13/12/2016 | KhoiNguyen | Complete
11 | 29 | Review Usecase Diagram "Manage Accouts" Function | Requirement | 14/12/2016 | 4 | 5 | 14/12/2016 | HienNguyen | Complete
11 | 30 | Review Usecase Diagram "Manage News" Function | Requirement | 14/12/2016 | 6 | 5 | 14/12/2016 | TaiNguyen | Complete
11 | 31 | Review Usecase Diagram "Manage Q&A" Function | Requirement | 14/12/2016 | 3 | 2 | 14/12/2016 | MinhDoan | Complete
11 | 32 | Review Usecase Diagram "Manage Homepage" Function | Requirement | 14/12/2016 | 4 | 2 | 14/12/2016 | HaiTran | Complete
11 | 33 | Review Usecase Diagram "Manage Banners" Function | Requirement | 14/12/2016 | 2 | 3 | 14/12/2016 | KhoiNguyen | Complete
11 | 34 | Review Usecase Diagram "Manage Pop-ups" Function | Requirement | 14/12/2016 | 3 | 3 | 14/12/2016 | KhoiNguyen | Complete
11 | 35 | Review Usecase Diagram "Manage Languages" Function | Requirement | 14/12/2016 | 2 | 1 | 14/12/2016 | XuanThaiHien | Pending
11 | 36 | Review Usecase Diagram "Manage Categories" Function | Requirement | 14/12/2016 | 3 | 3 | 14/12/2016 | HaiTran | Complete
11 | 37 | Review Usecase Diagram "Manage Examination" Function | Requirement | 14/12/2016 | 2 | 3 | 14/12/2016 | MinhDoan | Complete
11 | 38 | Collect into Usecase Specification document | Requirement | 14/12/2016 | 1 | 1 | 14/12/2016 | MinhDoan | Complete
11 | 39 | Define Product Functions | Requirement | 15/12/2016 | 1 | 1 | 15/12/2016 | MinhDoan | Complete
11 | 40 | Define user classes and characteristics | Requirement | 15/12/2016 | 3 | 3 | 15/12/2016 | HienNguyen | Complete
11 | 41 | Define Operating environment | Requirement | 15/12/2016 | 2 | 1 | 15/12/2016 | TaiNguyen | Complete
11 | 42 | Define Business constraint | Requirement | 15/12/2016 | 1 | 2 | 15/12/2016 | KhoiNguyen | Complete
11 | 43 | Define Business rules | Requirement | 15/12/2016 | 2 | 1 | 15/12/2016 | XuanThaiHien | Complete
11 | 44 | Define Quality Attribute | Requirement | 15/12/2016 | 4 | 3 | 15/12/2016 | HaiTran | Complete
11 | 45 | Develop UI "Manage Accounts" Function | Requirement | 16/12/2016 | 5 | 6 | 17/12/2016 | HaiTran | Pending
11 | 46 | Develop UI "Manage News" Function | Requirement | 16/12/2016 | 6 | 8 | 17/12/2016 | TaiNguyen | Pending
11 | 47 | Develop UI "Manage Q&A" Function | Requirement | 16/12/2016 | 4 | 6 | 17/12/2016 | HienNguyen | Pending
11 | 48 | Develop UI "Manage Homepage" Function | Requirement | 16/12/2016 | 5 | 7 | 17/12/2016 | KhoiNguyen | Pending
11 | 49 | Develop UI "Manage Banners" Function | Requirement | 16/12/2016 | 3 | 5 | 17/12/2016 | MinhDoan | Pending
11 | 50 | Develop UI "Manage Pop-ups" Function | Requirement | 16/12/2016 | 3 | 5 | 17/12/2016 | MinhDoan | Pending
11 | 51 | Develop UI "Manage Languages" Function | Requirement | 16/12/2016 | 2 | 1 | 17/12/2016 | KhoiNguyen | Pending
11 | 52 | Develop UI "Manage Categories" Function | Requirement | 16/12/2016 | 5 | 8 | 17/12/2016 | HaiTran | Pending
11 | 53 | Develop UI "Manage Examination" Function | Requirement | 16/12/2016 | 3 | 5 | 17/12/2016 | XuanThaiHien | Pending
12 | 1 | Team Meeting | Requirement | 19/12/2016 | 2 | 2 | 19/12/2016 | HaiTran | Complete
12 | 2 | Team Meeting | Requirement | 19/12/2016 | 2 | 2 | 19/12/2016 | HienNguyen | Complete
12 | 3 | Team Meeting | Requirement | 19/12/2016 | 2 | 2 | 19/12/2016 | TaiNguyen | Complete
12 | 4 | Team Meeting | Requirement | 19/12/2016 | 2 | 2 | 19/12/2016 | MinhDoan | Complete
12 | 5 | Team Meeting | Requirement | 19/12/2016 | 2 | 2 | 19/12/2016 | KhoiNguyen | Complete
12 | 6 | Update Usecase description "Manage Accounts" Function | Requirement | 19/12/2016 | 3 | 4 | 19/12/2016 | HienNguyen | Complete
12 | 7 | Update Usecase description "Manage News" Function | Requirement | 19/12/2016 | 4 | 4 | 19/12/2016 | HaiTran | Complete
12 | 8 | Update Usecase description "Manage Homepage" Function | Requirement | 19/12/2016 | 2 | 3 | 19/12/2016 | TaiNguyen | Complete
12 | 9 | Update Usecase description "Manage Q&A" Function | Requirement | 19/12/2016 | 2 | 3 | 19/12/2016 | KhoiNguyen | Complete
12 | 10 | Update Usecase description "Manage Banners" Function | Requirement | 19/12/2016 | 2 | 3 | 19/12/2016 | MinhDoan | Complete
12 | 11 | Update Usecase description "Manage Pop-ups Function | Requirement | 19/12/2016 | 2 | 3 | 19/12/2016 | MinhDoan | Complete
12 | 12 | Update Usecase description "Manage Categories" Function | Requirement | 19/12/2016 | 3 | 4 | 19/12/2016 | HaiTran | Complete
12 | 13 | Update Usecase description "Manage Languages" Function | Requirement | 19/12/2016 | 2 | 1 | 19/12/2016 | KhoiNguyen | Complete
12 | 14 | Update Usecase description "Manage Examination" Function | Requirement | 19/12/2016 | 2 | 3 | 19/12/2016 | XuanThaiHien | Pending
12 | 15 | Update Usecase Diagram "Manage Accouts" Function | Requirement | 20/12/2016 | 2 | 3 | 20/12/2016 | HienNguyen | Complete
12 | 16 | Update Usecase Diagram "Manage News" Function | Requirement | 20/12/2016 | 2 | 2 | 20/12/2016 | HaiTran | Complete
12 | 17 | Update Usecase Diagram "Manage Q&A" Function | Requirement | 20/12/2016 | 3 | 2 | 20/12/2016 | TaiNguyen | Complete
12 | 18 | Update Usecase Diagram "Manage Homepage" Function | Requirement | 20/12/2016 | 2 | 2 | 20/12/2016 | KhoiNguyen | Complete
12 | 19 | Update Usecase Diagram "Manage Banners" Function | Requirement | 20/12/2016 | 2 | 3 | 20/12/2016 | MinhDoan | Complete
12 | 20 | Update Usecase Diagram "Manage Pop-ups" Function | Requirement | 20/12/2016 | 3 | 2 | 20/12/2016 | MinhDoan | Complete
12 | 21 | Update Usecase Diagram "Manage Languages" Function | Requirement | 20/12/2016 | 1 | 2 | 20/12/2016 | HaiTran | Complete
12 | 22 | Update Usecase Diagram "Manage Categories" Function | Requirement | 20/12/2016 | 3 | 3 | 20/12/2016 | KhoiNguyen | Complete
12 | 23 | Update Usecase Diagram "Manage Examination" Function | Requirement | 20/12/2016 | 3 | 2 | 20/12/2016 | XuanThaiHien | Pending
12 | 24 | Training Technical | Requirement | 20/12/2016 | 2 | 2 | 20/12/2016 | HaiTran | Complete
12 | 25 | Training Technical | Requirement | 20/12/2016 | 2 | 2 | 20/12/2016 | HienNguyen | Complete
12 | 26 | Training Technical | Requirement | 20/12/2016 | 2 | 2 | 20/12/2016 | MinhDoan | Complete
12 | 27 | Training Technical | Requirement | 20/12/2016 | 2 | 2 | 20/12/2016 | TaiNguyen | Complete
12 | 28 | Training Technical | Requirement | 20/12/2016 | 2 | 2 | 20/12/2016 | KhoiNguyen | Complete
12 | 29 | Customer Meeting | Requirement | 21/12/2016 | 3 | 2 | 21/12/2016 | HienNguyen | Complete
12 | 30 | Customer Meeting | Requirement | 21/12/2016 | 3 | 2 | 21/12/2016 | HaiTran | Complete
12 | 31 | Customer Meeting | Requirement | 21/12/2016 | 3 | 2 | 21/12/2016 | TaiNguyen | Complete
12 | 32 | Customer Meeting | Requirement | 21/12/2016 | 3 | 2 | 21/12/2016 | KhoiNguyen | Complete
12 | 33 | Customer Meeting | Requirement | 21/12/2016 | 3 | 2 | 21/12/2016 | MinhDoan | Complete
12 | 34 | Develop "Manage News" Functional Testcase | Requirement | 21/12/2016 | 7 | 8 | 23/12/2016 | HaiTran | Complete
12 | 35 | Develop "Manage Account" Functional Testcase | Requirement | 21/12/2016 | 6 | 6 | 23/12/2016 | HienNguyen | Complete
12 | 36 | Develop "Manage Homepage" Functional Testcase | Requirement | 21/12/2016 | 5 | 6 | 23/12/2016 | TaiNguyen | Complete
12 | 37 | Develop "Manage Categories" Functional Testcase | Requirement | 21/12/2016 | 6 | 7 | 23/12/2016 | KhoiNguyen | Complete
12 | 38 | Develop "Manage Banners" Functional Testcase | Requirement | 21/12/2016 | 6 | 5 | 23/12/2016 | MinhDoan | Complete
12 | 39 | Develop "Manage Pop-ups" Functional Testcase | Requirement | 21/12/2016 | 6 | 7 | 23/12/2016 | MinhDoan | Complete
12 | 40 | Develop "Manage Examination" Functional Testcase | Requirement | 21/12/2016 | 4 | 4 | 23/12/2016 | XuanThaiHien | Complete
12 | 41 | Develop "Manage Q&A" Functional Testcase | Requirement | 21/12/2016 | 5 | 6 | 24/12/2016 | XuanThaiHien | Complete
12 | 42 | Develop "Manage Languages" Functional Testcase | Requirement | 21/12/2016 | 3 | 2 | 24/12/2016 | KhoiNguyen | Complete
12 | 43 | Develop "Manage Account" User Acceptance Testcase | Requirement | 21/12/2016 | 7 | 6 | 24/12/2016 | HaiTran | Complete
12 | 44 | Develop "Manage News" User Acceptance Testcase | Requirement | 21/12/2016 | 7 | 5 | 24/12/2016 | HienNguyen | Complete
12 | 45 | Develop "Manage Homepage" User Acceptance Testcase | Requirement | 21/12/2016 | 6 | 5 | 24/12/2016 | TaiNguyen | Complete
12 | 46 | Develop "Manage Banners" User Acceptance Testcase | Requirement | 21/12/2016 | 3 | 4 | 24/12/2016 | MinhDoan | Complete
12 | 47 | Develop "Manage Pop-ups" User Acceptance Testcase | Requirement | 21/12/2016 | 3 | 4 | 24/12/2016 | MinhDoan | Complete
12 | 48 | Develop "Manage Categories" User Acceptance Testcase | Requirement | 21/12/2016 | 6 | 6 | 24/12/2016 | KhoiNguyen | Complete
12 | 49 | Develop "Manage Examination" User Acceptance Testcase | Requirement | 21/12/2016 | 6 | 4 | 24/12/2016 | XuanThaiHien | Complete
12 | 50 | Develop "Manage Q&A" User Acceptance Testcase | Requirement | 21/12/2016 | 3 | 5 | 24/12/2016 | KhoiNguyen | Complete
12 | 51 | Develop "Manage Languages" User Acceptance Testcase | Requirement | 21/12/2016 | 2 | 2 | 24/12/2016 | HaiTran | Complete
13 | 1 | Team Meeting | Architect | 26/12/2016 | 2 | 2 | 26/12/2016 | HaiTran | Complete
13 | 2 | Team Meeting | Architect | 26/12/2016 | 2 | 2 | 26/12/2016 | HienNguyen | Complete
13 | 3 | Team Meeting | Architect | 26/12/2016 | 2 | 2 | 26/12/2016 | MinhDoan | Complete
13 | 4 | Team Meeting | Architect | 26/12/2016 | 2 | 2 | 26/12/2016 | TaiNguyen | Complete
13 | 5 | Team Meeting | Architect | 26/12/2016 | 2 | 2 | 26/12/2016 | KhoiNguyen | Complete
13 | 6 | Review "Manage News" Functional Testcase | Architect | 26/12/2016 | 4 | 5 | 26/12/2016 | HaiTran | Complete
13 | 7 | Review "Manage News" Functional Testcase | Architect | 26/12/2016 | 3 | 6 | 26/12/2016 | HienNguyen | Complete
13 | 8 | Review "Manage Account" Functional Testcase | Architect | 26/12/2016 | 5 | 7 | 26/12/2016 | TaiNguyen | Complete
13 | 9 | Review "Manage Account" Functional Testcase | Architect | 26/12/2016 | 4 | 5 | 26/12/2016 | MinhDoan | Complete
13 | 10 | Review "Manage Homepage" Functional Testcase | Architect | 26/12/2016 | 4 | 3 | 26/12/2016 | KhoiNguyen | Complete
13 | 11 | Review "Manage Homepage" Functional Testcase | Architect | 26/12/2016 | 2 | 2 | 26/12/2016 | XuanThaiHien | Complete
13 | 12 | Review "Manage Categories" Functional Testcase | Architect | 27/12/2016 | 3 | 3 | 27/12/2016 | KhoiNguyen | Complete
13 | 13 | Review "Manage Categories" Functional Testcase | Architect | 27/12/2016 | 3 | 4 | 27/12/2016 | HienNguyen | Complete
13 | 14 | Review "Manage Banners" Functional Testcase | Architect | 27/12/2016 | 2 | 2 | 27/12/2016 | MinhDoan | Complete
13 | 15 | Review "Manage Banners" Functional Testcase | Architect | 27/12/2016 | 3 | 2 | 27/12/2016 | XuanThaiHien | Complete
13 | 16 | Review "Manage Pop-ups" Functional Testcase | Architect | 27/12/2016 | 2 | 2 | 27/12/2016 | HaiTran | Complete
13 | 17 | Review "Manage Pop-ups" Functional Testcase | Architect | 27/12/2016 | 2 | 1 | 27/12/2016 | TaiNguyen | Complete
13 | 18 | Review "Manage Examination" Functional Testcase | Architect | 27/12/2016 | 2 | 2 | 27/12/2016 | TaiNguyen | Complete
13 | 19 | Review "Manage Examination" Functional Testcase | Architect | 27/12/2016 | 1 | 2 | 27/12/2016 | MinhDoan | Complete
13 | 20 | Training Technical | Architect | 27/12/2016 | 2 | 2 | 27/12/2016 | HaiTran | Complete
13 | 21 | Training Technical | Architect | 27/12/2016 | 2 | 2 | 27/12/2016 | HienNguyen | Complete
13 | 22 | Training Technical | Architect | 27/12/2016 | 2 | 2 | 27/12/2016 | KhoiNguyen | Complete
13 | 23 | Training Technical | Architect | 27/12/2016 | 2 | 2 | 27/12/2016 | MinhDoan | Complete
13 | 24 | Training Technical | Architect | 27/12/2016 | 2 | 2 | 27/12/2016 | TaiNguyen | Complete
13 | 25 | Review "Manage Q&A" Functional Testcase | Architect | 28/12/2016 | 2 | 3 | 28/12/2016 | MinhDoan | Complete
13 | 26 | Review "Manage Q&A" Functional Testcase | Architect | 28/12/2016 | 3 | 2 | 28/12/2016 | KhoiNguyen | Complete
13 | 27 | Review "Manage Languages" Functional Testcase | Architect | 28/12/2016 | 1 | 2 | 28/12/2016 | HienNguyen | Complete
13 | 28 | Review "Manage Languages" Functional Testcase | Architect | 28/12/2016 | 1 | 1 | 28/12/2016 | XuanThaiHien | Complete
13 | 29 | Review "Manage Account" User Acceptance Testcase | Architect | 28/12/2016 | 5 | 6 | 28/12/2016 | HaiTran | Complete
13 | 30 | Review "Manage Account" User Acceptance Testcase | Architect | 28/12/2016 | 4 | 6 | 28/12/2016 | TaiNguyen | Complete
13 | 31 | Review "Manage News" User Acceptance Testcase | Architect | 28/12/2016 | 4 | 6 | 28/12/2016 | HienNguyen | Complete
13 | 32 | Review "Manage News" User Acceptance Testcase | Architect | 28/12/2016 | 5 | 6 | 28/12/2016 | KhoiNguyen | Complete
13 | 33 | Review "Manage Homepage" User Acceptance Testcase | Architect | 28/12/2016 | 3 | 4 | 28/12/2016 | MinhDoan | Complete
13 | 34 | Review "Manage Homepage" User Acceptance Testcase | Architect | 28/12/2016 | 2 | 3 | 28/12/2016 | TaiNguyen | Complete
13 | 35 | Review "Manage Banners" User Acceptance Testcase | Architect | 28/12/2016 | 2 | 1 | 28/12/2016 | XuanThaiHien | Complete
13 | 36 | Review "Manage Banners" User Acceptance Testcase | Architect | 28/12/2016 | 2 | 3 | 28/12/2016 | HaiTran | Complete
13 | 37 | Review "Manage Pop-ups" User Acceptance Testcase | Architect | 29/12/2016 | 2 | 1 | 29/12/2016 | XuanThaiHien | Complete
13 | 38 | Review "Manage Pop-ups" User Acceptance Testcase | Architect | 29/12/2016 | 2 | 3 | 29/12/2016 | MinhDoan | Complete
13 | 39 | Review "Manage Categories" User Acceptance Testcase | Architect | 29/12/2016 | 4 | 6 | 29/12/2016 | TaiNguyen | Complete
13 | 40 | Review "Manage Categories" User Acceptance Testcase | Architect | 29/12/2016 | 5 | 6 | 29/12/2016 | HienNguyen | Complete
13 | 41 | Review "Manage Examination" User Acceptance Testcase | Architect | 29/12/2016 | 3 | 4 | 29/12/2016 | KhoiNguyen | Complete
13 | 42 | Review "Manage Examination" User Acceptance Testcase | Architect | 29/12/2016 | 2 | 3 | 29/12/2016 | HaiTran | Complete
13 | 43 | Review "Manage Q&A" User Acceptance Testcase | Architect | 29/12/2016 | 2 | 3 | 29/12/2016 | HaiTran | Complete
13 | 44 | Review "Manage Q&A" User Acceptance Testcase | Architect | 29/12/2016 | 2 | 2 | 29/12/2016 | TaiNguyen | Complete
13 | 45 | Review "Manage Languages" User Acceptance Testcase | Architect | 29/12/2016 | 1 | 1 | 29/12/2016 | MinhDoan | Complete
13 | 46 | Review "Manage Languages" User Acceptance Testcase | Architect | 29/12/2016 | 1 | 1 | 29/12/2016 | HienNguyen | Complete
13 | 47 | Update "Manage News" Functional Testcase | Architect | 29/12/2016 | 3 | 3 | 29/12/2016 | HaiTran | Complete
13 | 48 | Update "Manage Account" Functional Testcase | Architect | 29/12/2016 | 2 | 3 | 29/12/2016 | HienNguyen | Complete
13 | 49 | Update "Manage Homepage" Functional Testcase | Architect | 29/12/2016 | 2 | 2 | 29/12/2016 | TaiNguyen | Complete
13 | 50 | Update "Manage Categories" Functional Testcase | Architect | 29/12/2016 | 3 | 2 | 29/12/2016 | KhoiNguyen | Complete
13 | 51 | Update "Manage Banners" Functional Testcase | Architect | 29/12/2016 | 2 | 2 | 29/12/2016 | MinhDoan | Complete
13 | 52 | Update "Manage Pop-ups" Functional Testcase | Architect | 29/12/2016 | 2 | 3 | 29/12/2016 | MinhDoan | Complete
13 | 53 | Update "Manage Examination" Functional Testcase | Architect | 29/12/2016 | 3 | 3 | 29/12/2016 | XuanThaiHien | Complete
13 | 54 | Update "Manage Q&A" Functional Testcase | Architect | 29/12/2016 | 3 | 2 | 29/12/2016 | XuanThaiHien | Complete
13 | 55 | Update "Manage Languages" Functional Testcase | Architect | 29/12/2016 | 2 | 1 | 29/12/2016 | KhoiNguyen | Complete
13 | 56 | Collect Testcase | Architect | 29/12/2016 | 1 | 2 | 29/12/2016 | KhoiNguyen | Complete
13 | 57 | Research Physical view | Architect | 30/12/2016 | 3 | 5 | 31/12/2016 | HienNguyen | Complete
13 | 58 | Research Static view | Architect | 30/12/2016 | 4 | 5 | 31/12/2016 | TaiNguyen | Complete
13 | 59 | Research Dynamic view | Architect | 30/12/2016 | 6 | 4 | 31/12/2016 | MinhDoan | Complete
13 | 60 | Research Physical view | Architect | 30/12/2016 | 4 | 3 | 31/12/2016 | KhoiNguyen | Complete
13 | 61 | Research Static view | Architect | 30/12/2016 | 5 | 4 | 31/12/2016 | HaiTran | Complete
13 | 62 | Research Dynamic view | Architect | 30/12/2016 | 3 | 4 | 31/12/2016 | XuanThaiHien | Complete
13 | 63 | Draw Physical view draft | Architect | 30/12/2016 | 3 | 4 | 31/12/2016 | HienNguyen | Complete
13 | 64 | Draw Static view draft | Architect | 30/12/2016 | 4 | 3 | 31/12/2016 | TaiNguyen | Complete
13 | 65 | Draw Dynamic view draft | Architect | 30/12/2016 | 5 | 4 | 31/12/2016 | MinhDoan | Complete
13 | 66 | Writting rationel | Architect | 30/12/2016 | 3 | 1 | 31/12/2016 | HaiTran | Complete
13 | 67 | Draw Physical view draft | Architect | 30/12/2016 | 3 | 4 | 31/12/2016 | KhoiNguyen | Complete
14 | 1 | Team Meeting | Architect | 2017-02-01 | 2 | 2 | 2017-02-01 | HaiTran | Complete
14 | 2 | Team Meeting | Architect | 2017-02-01 | 2 | 2 | 2017-02-01 | HienNguyen | Complete
14 | 3 | Team Meeting | Architect | 2017-02-01 | 2 | 2 | 2017-02-01 | KhoiNguyen | Complete
14 | 4 | Team Meeting | Architect | 2017-02-01 | 2 | 2 | 2017-02-01 | TaiNguyen | Complete
14 | 5 | Team Meeting | Architect | 2017-02-01 | 2 | 2 | 2017-02-01 | MinhDoan | Complete
14 | 6 | Team Meeting | Architect | 2017-02-01 | 2 | 2 | 2017-02-01 | XuanThaiHien | Complete
14 | 7 | Draw Physical View | Architect | 2017-02-01 | 4 | 7 | 2017-02-01 | HienNguyen | Pending
14 | 8 | Draw Static View Level 1 | Architect | 2017-02-01 | 5 | 6 | 2017-02-01 | HaiTran | Pending
14 | 9 | Draw Static View Level 2 | Architect | 2017-02-01 | 6 | 5 | 2017-02-01 | KhoiNguyen | Pending
14 | 10 | Draw Static View Level 2 | Architect | 2017-02-01 | 4 | 3 | 2017-02-01 | HaiTran | Pending
14 | 11 | Draw Dynamic View Level 1 | Architect | 2017-02-01 | 7 | 9 | 2017-02-01 | TaiNguyen | Pending
14 | 12 | Draw Dynamic View Level 2 | Architect | 2017-02-01 | 6 | 8 | 2017-02-01 | MinhDoan | Pending
14 | 13 | Mentor Meeting | Architect | 2017-03-01 | 3 | 2 | 2017-03-01 | HaiTran | Complete
14 | 14 | Mentor Meeting | Architect | 2017-03-01 | 3 | 2 | 2017-03-01 | HienNguyen | Complete
14 | 15 | Mentor Meeting | Architect | 2017-03-01 | 3 | 2 | 2017-03-01 | KhoiNguyen | Complete
14 | 16 | Mentor Meeting | Architect | 2017-03-01 | 3 | 2 | 2017-03-01 | TaiNguyen | Complete
14 | 17 | Mentor Meeting | Architect | 2017-03-01 | 3 | 2 | 2017-03-01 | MinhDoan | Complete
14 | 18 | Mentor Meeting | Architect | 2017-03-01 | 3 | 2 | 2017-03-01 | XuanThaiHien | Complete
14 | 19 | Training Technical | Architect | 2017-03-01 | 2 | 2 | 2017-03-01 | HaiTran | Complete
14 | 20 | Training Technical | Architect | 2017-03-01 | 2 | 2 | 2017-03-01 | HienNguyen | Complete
14 | 21 | Training Technical | Architect | 2017-03-01 | 2 | 2 | 2017-03-01 | KhoiNguyen | Complete
14 | 22 | Training Technical | Architect | 2017-03-01 | 2 | 2 | 2017-03-01 | TaiNguyen | Complete
14 | 23 | Training Technical | Architect | 2017-03-01 | 2 | 2 | 2017-03-01 | MinhDoan | Complete
14 | 24 | Draw Physical View | Architect | 2017-03-01 | 3 | 3 | 2017-03-01 | HienNguyen
14 | 25 | Draw Static View Level 1 | Architect | 2017-03-01 | 4 | 3 | 2017-03-01 | HaiTran
14 | 26 | Draw Static View Level 2 | Architect | 2017-03-01 | 5 | 4 | 2017-03-01 | KhoiNguyen
14 | 27 | Draw Static View Level 2 | Architect | 2017-03-01 | 4 | 4 | 2017-03-01 | HaiTran
14 | 28 | Draw Dynamic View Level 1 | Architect | 2017-03-01 | 3 | 4 | 2017-03-01 | TaiNguyen
14 | 29 | Draw Dynamic View Level 2 | Architect | 2017-03-01 | 5 | 3 | 2017-03-01 | MinhDoan
14 | 30 | Review Physical View | Architect | 2017-04-01 | 2 | 2 | 2017-04-01 | HaiTran
14 | 31 | Review Physical View | Architect | 2017-04-01 | 2 | 2 | 2017-04-01 | HienNguyen
14 | 32 | Review Physical View | Architect | 2017-04-01 | 2 | 2 | 2017-04-01 | MinhDoan
14 | 33 | Review Physical View | Architect | 2017-04-01 | 2 | 2 | 2017-04-01 | TaiNguyen
14 | 34 | Review Physical View | Architect | 2017-04-01 | 2 | 2 | 2017-04-01 | KhoiNguyen
14 | 35 | Review Physical View | Architect | 2017-04-01 | 2 | 2 | 2017-04-01 | XuanThaiHien
14 | 36 | Review Static View | Architect | 2017-04-01 | 3 | 2 | 2017-04-01 | HaiTran
14 | 37 | Review Static View | Architect | 2017-04-01 | 2 | 2 | 2017-04-01 | HienNguyen
14 | 38 | Review Static View | Architect | 2017-04-01 | 3 | 2 | 2017-04-01 | MinhDoan
14 | 39 | Review Static View | Architect | 2017-04-01 | 4 | 2 | 2017-04-01 | TaiNguyen
14 | 40 | Review Static View | Architect | 2017-04-01 | 2 | 2 | 2017-04-01 | KhoiNguyen
14 | 41 | Review Static View | Architect | 2017-04-01 | 2 | 2 | 2017-04-01 | XuanThaiHien
14 | 42 | Review Dynamic | Architect | 2017-04-01 | 2 | 3 | 2017-05-01 | HaiTran
14 | 43 | Review Dynamic | Architect | 2017-04-01 | 3 | 3 | 2017-05-01 | HienNguyen
14 | 44 | Review Dynamic | Architect | 2017-04-01 | 2 | 3 | 2017-05-01 | MinhDoan
14 | 45 | Review Dynamic | Architect | 2017-04-01 | 2 | 3 | 2017-05-01 | TaiNguyen
14 | 46 | Review Dynamic | Architect | 2017-04-01 | 3 | 3 | 2017-05-01 | KhoiNguyen
14 | 47 | Review Dynamic | Architect | 2017-04-01 | 2 | 3 | 2017-05-01 | XuanThaiHien
14 | 48 | Mentor Meeting | Architect | 2017-05-01 | 2 | 4 | 2017-05-01 | HaiTran
14 | 49 | Mentor Meeting | Architect | 2017-05-01 | 2 | 4 | 2017-05-01 | HienNguyen
14 | 50 | Mentor Meeting | Architect | 2017-05-01 | 2 | 4 | 2017-05-01 | MinhDoan
14 | 51 | Mentor Meeting | Architect | 2017-05-01 | 2 | 4 | 2017-05-01 | TaiNguyen
14 | 52 | Mentor Meeting | Architect | 2017-05-01 | 2 | 4 | 2017-05-01 | KhoiNguyen
14 | 53 | Mentor Meeting | Architect | 2017-05-01 | 2 | 4 | 2017-05-01 | XuanThaiHien
14 | 54 | Research pattern 3 layers in dynamic view | Architect | 2017-06-01 | 3 | 2 | 2017-07-01 | HienNguyen | Complete
14 | 55 | Research pattern 3 layers in dynamic view | Architect | 2017-06-01 | 2 | 1 | 2017-07-01 | KhoiNguyen | Complete
14 | 56 | Update Dynamic View | Architect | 2017-06-01 | 2 | 4 | 2017-07-01 | KhoiNguyen | Pending
14 | 57 | Update Static View | Architect | 2017-06-01 | 2 | 3 | 2017-07-01 | TaiNguyen | Pending
14 | 58 | Research tactics for physical view | Architect | 2017-06-01 | 1 | 2 | 2017-07-01 | MinhDoan | Complete
14 | 59 | Research tactics for quality attributes | Architect | 2017-06-01 | 3 | 4 | 2017-07-01 | MinhDoan | Pending
14 | 60 | Apply tactics performance, usability for physical view | Architect | 2017-06-01 | 1 | 2 | 2017-07-01 | XuanThaiHien | Pending
14 | 61 | Tactics performance, usability for physical view | Architect | 2017-06-01 | 5 | 2 | 2017-07-01 | XuanThaiHien | Pending
14 | 62 | Update Physical View | Architect | 2017-06-01 | 2 | 2.5 | 2017-07-01 | TaiNguyen | Complete
15 | 1 | Team Meeting | Architect | 2017-09-01 | 2 | 2 | 2017-09-01 | HaiTran | Complete
15 | 2 | Team Meeting | Architect | 2017-09-01 | 2 | 2 | 2017-09-01 | HienNguyen | Complete
15 | 3 | Team Meeting | Architect | 2017-09-01 | 2 | 2 | 2017-09-01 | KhoiNguyen | Complete
15 | 4 | Team Meeting | Architect | 2017-09-01 | 2 | 2 | 2017-09-01 | MinhDoan | Complete
15 | 5 | Team Meeting | Architect | 2017-09-01 | 2 | 2 | 2017-09-01 | TaiNguyen | Complete
15 | 6 | Update Physical View | Architect | 2017-09-01 | 3 | 4 | 2017-09-01 | HienNguyen | Complete
15 | 7 | Update Static View | Architect | 2017-09-01 | 6 | 5 | 2017-09-01 | HaiTran | Complete
15 | 8 | Update Dynamic View | Architect | 2017-09-01 | 4 | 6 | 2017-09-01 | KhoiNguyen | Complete
15 | 9 | Customer Meeting | Architect | 2017-10-01 | 2 | 2 | 2017-10-01 | HaiTran | Complete
15 | 10 | Customer Meeting | Architect | 2017-10-01 | 2 | 2 | 2017-10-01 | HienNguyen | Complete
15 | 11 | Customer Meeting | Architect | 2017-10-01 | 2 | 2 | 2017-10-01 | KhoiNguyen | Complete
15 | 12 | Customer Meeting | Architect | 2017-10-01 | 2 | 2 | 2017-10-01 | MinhDoan | Complete
15 | 13 | Customer Meeting | Architect | 2017-10-01 | 2 | 2 | 2017-10-01 | TaiNguyen | Complete
15 | 14 | Training Technical | Architect | 2017-10-01 | 2 | 2 | 2017-10-01 | HaiTran | Complete
15 | 15 | Training Technical | Architect | 2017-10-01 | 2 | 2 | 2017-10-01 | HienNguyen | Complete
15 | 16 | Training Technical | Architect | 2017-10-01 | 2 | 2 | 2017-10-01 | KhoiNguyen | Complete
15 | 17 | Training Technical | Architect | 2017-10-01 | 2 | 2 | 2017-10-01 | MinhDoan | Complete
15 | 18 | Training Technical | Architect | 2017-10-01 | 2 | 2 | 2017-10-01 | TaiNguyen | Complete
15 | 19 | Research Redis Technology | Architect | 2017-11-01 | 3 | 4 | 2017-11-01 | HienNguyen | Complete
15 | 20 | Research Elastic Technology | Architect | 2017-11-01 | 3 | 3 | 2017-11-01 | TaiNguyen | Complete
15 | 21 | Research MongoDB | Architect | 2017-11-01 | 3 | 2 | 2017-11-01 | HaiTran | Complete
15 | 22 | Update Physical View | Architect | 2017-11-01 | 3 | 4 | 2017-11-01 | KhoiNguyen | Complete
15 | 23 | Update Static View | Architect | 2017-11-01 | 3 | 3 | 2017-11-01 | TaiNguyen | Complete
15 | 24 | Update Dynamic View | Architect | 2017-11-01 | 4 | 5 | 2017-11-01 | HaiTran | Complete
15 | 25 | Mentor Meeting | Architect | 2017-12-01 | 2 | 4 | 2017-12-01 | HaiTran | Complete
15 | 26 | Mentor Meeting | Architect | 2017-12-01 | 2 | 4 | 2017-12-01 | HienNguyen | Complete
15 | 27 | Mentor Meeting | Architect | 2017-12-01 | 2 | 4 | 2017-12-01 | KhoiNguyen | Complete
15 | 28 | Mentor Meeting | Architect | 2017-12-01 | 2 | 4 | 2017-12-01 | MinhDoan | Complete
15 | 29 | Mentor Meeting | Architect | 2017-12-01 | 2 | 4 | 2017-12-01 | TaiNguyen | Complete
15 | 30 | Mentor Meeting | Architect | 2017-12-01 | 2 | 4 | 2017-12-01 | XuanThaiHien | Complete
16 | 1 | Team Meeting | Detailed Design | 16/1/2017 | 2 | 2 | 16/1/2017 | HaiTran | Complete
16 | 2 | Team Meeting | Detailed Design | 16/1/2017 | 2 | 2 | 16/1/2017 | HienNguyen | Complete
16 | 3 | Team Meeting | Detailed Design | 16/1/2017 | 2 | 2 | 16/1/2017 | MinhDoan | Complete
16 | 4 | Team Meeting | Detailed Design | 16/1/2017 | 2 | 2 | 16/1/2017 | TaiNguyen | Complete
16 | 5 | Team Meeting | Detailed Design | 16/1/2017 | 2 | 2 | 16/1/2017 | KhoiNguyen | Complete
16 | 6 | Design Database | Detailed Design | 16/1/2017 | 2 | 3 | 16/1/2017 | HaiTran | Complete
16 | 7 | Design Database | Detailed Design | 16/1/2017 | 3 | 3 | 16/1/2017 | TaiNguyen | Complete
16 | 8 | Draw class diagram function "Manage Account" | Detailed Design | 16/1/2017 | 5 | 6 | 16/1/2017 | TaiNguyen | Complete
16 | 9 | Draw class diagram function "Manage News" | Detailed Design | 16/1/2017 | 4 | 5 | 16/1/2017 | HienNguyen | Complete
16 | 10 | Draw class diagram function "Manage FAQ" | Detailed Design | 16/1/2017 | 7 | 6 | 16/1/2017 | MinhDoan | Complete
16 | 11 | Draw class diagram function "Manage Homepage" | Detailed Design | 16/1/2017 | 6 | 5 | 16/1/2017 | KhoiNguyen | Complete
16 | 12 | Draw class diagram function "Manage Categories" | Detailed Design | 16/1/2017 | 5 | 7 | 16/1/2017 | TaiNguyen | Complete
16 | 13 | Draw class diagram function "Manage Banners" | Detailed Design | 16/1/2017 | 3 | 3 | 16/1/2017 | HienNguyen | Complete
16 | 14 | Training Technical | Detailed Design | 17/1/2017 | 2 | 2 | 17/1/2017 | HaiTran | Complete
16 | 15 | Training Technical | Detailed Design | 17/1/2017 | 2 | 2 | 17/1/2017 | HienNguyen | Complete
16 | 16 | Training Technical | Detailed Design | 17/1/2017 | 2 | 2 | 17/1/2017 | MinhDoan | Complete
16 | 17 | Training Technical | Detailed Design | 17/1/2017 | 2 | 2 | 17/1/2017 | TaiNguyen | Complete
16 | 18 | Training Technical | Detailed Design | 17/1/2017 | 2 | 2 | 17/1/2017 | KhoiNguyen | Complete
16 | 19 | Draw class diagram function "Manage Popups" | Detailed Design | 17/1/2017 | 7 | 6 | 17/1/2017 | MinhDoan | Complete
16 | 20 | Draw class diagram function "Manage Languages" | Detailed Design | 17/1/2017 | 2 | 1 | 17/1/2017 | TaiNguyen | Complete
16 | 21 | Draw class diagram function "Manage Examination" | Detailed Design | 17/1/2017 | 4 | 6 | 17/1/2017 | XuanThaiHien | Not implemented
16 | 22 | Draw sequence diagram function "Manage Account" | Detailed Design | 17/1/2017 | 5 | 7 | 17/1/2017 | HaiTran | Complete
16 | 23 | Draw sequence diagram function "Manage News" | Detailed Design | 17/1/2017 | 5 | 6 | 17/1/2017 | KhoiNguyen | Complete
16 | 24 | Draw sequence diagram function "Manage Categories" | Detailed Design | 18/1/2017 | 7 | 8 | 18/1/2017 | MinhDoan | Complete
16 | 25 | Draw sequence diagram function "Manage Banners" | Detailed Design | 18/1/2017 | 2 | 4 | 18/1/2017 | HienNguyen | Complete
16 | 26 | Draw sequence diagram function "Manage Popups" | Detailed Design | 18/1/2017 | 7 | 8 | 18/1/2017 | MinhDoan | Complete
16 | 27 | Draw sequence diagram function "Manage Homepage" | Detailed Design | 18/1/2017 | 4 | 5 | 18/1/2017 | HaiTran | Complete
16 | 28 | Draw sequence diagram function "Manage Examination" | Detailed Design | 18/1/2017 | 3 | 4 | 18/1/2017 | HienNguyen | Complete
16 | 29 | Draw sequence diagram function "Manage Language" | Detailed Design | 18/1/2017 | 2 | 1 | 18/1/2017 | XuanThaiHien | Complete
16 | 30 | Draw sequence diagram function "Manage FAQ" | Detailed Design | 18/1/2017 | 2 | 3 | 18/1/2017 | XuanThaiHien | Complete
16 | 31 | Mentor Meeting | Detailed Design | 19/1/2017 | 2 | 3 | 19/1/2017 | TaiNguyen | Complete
16 | 32 | Mentor Meeting | Detailed Design | 19/1/2017 | 2 | 3 | 19/1/2017 | XuanThaiHien | Complete
16 | 33 | Mentor Meeting | Detailed Design | 19/1/2017 | 2 | 3 | 19/1/2017 | HaiTran | Complete
16 | 34 | Mentor Meeting | Detailed Design | 19/1/2017 | 2 | 3 | 19/1/2017 | KhoiNguyen | Complete
16 | 35 | Mentor Meeting | Detailed Design | 19/1/2017 | 2 | 3 | 19/1/2017 | MinhDoan | Complete
16 | 36 | Mentor Meeting | Detailed Design | 19/1/2017 | 2 | 3 | 19/1/2017 | HienNguyen | Complete
16 | 37 | Review class diagram function "Manage Account" | Detailed Design | 19/1/2017 | 3 | 2 | 19/1/2017 | HienNguyen | Complete
16 | 38 | Review class diagram function "Manage Account" | Detailed Design | 19/1/2017 | 2 | 2 | 19/1/2017 | TaiNguyen | Complete
16 | 39 | Review class diagram function "Manage News" | Detailed Design | 19/1/2017 | 3 | 2 | 19/1/2017 | HaiTran | Complete
16 | 40 | Review class diagram function "Manage News" | Detailed Design | 19/1/2017 | 2 | 2 | 19/1/2017 | KhoiNguyen | Complete
16 | 41 | Review class diagram function "Manage FAQ" | Detailed Design | 19/1/2017 | 2 | 1 | 19/1/2017 | MinhDoan | Complete
16 | 42 | Review class diagram function "Manage FAQ" | Detailed Design | 19/1/2017 | 1 | 1 | 19/1/2017 | XuanThaiHien | Complete
16 | 43 | Review class diagram function "Manage Homepage" | Detailed Design | 19/1/2017 | 2 | 2 | 19/1/2017 | MinhDoan | Complete
16 | 44 | Review class diagram function "Manage Categories" | Detailed Design | 19/1/2017 | 2 | 3 | 19/1/2017 | TaiNguyen | Complete
16 | 45 | Review class diagram function "Manage Categories" | Detailed Design | 19/1/2017 | 3 | 3 | 19/1/2017 | HienNguyen | Complete
16 | 46 | Review class diagram function "Manage Banners" | Detailed Design | 19/1/2017 | 2 | 2 | 19/1/2017 | HaiTran | Complete
16 | 47 | Review class diagram function "Manage Popups" | Detailed Design | 20/1/2017 | 2 | 2 | 20/1/2017 | HaiTran | Complete
16 | 48 | Review class diagram function "Manage Languages" | Detailed Design | 20/1/2017 | 1 | 1 | 20/1/2017 | XuanThaiHien | Complete
16 | 49 | Review class diagram function "Manage Examination" | Detailed Design | 20/1/2017 | 2 | 3 | 20/1/2017 | MinhDoan | Complete
16 | 50 | Review sequence diagram function "Manage Account" | Detailed Design | 20/1/2017 | 4 | 5 | 20/1/2017 | TaiNguyen | Complete
16 | 51 | Review sequence diagram function "Manage Account" | Detailed Design | 20/1/2017 | 3 | 4 | 20/1/2017 | HienNguyen | Complete
16 | 52 | Review sequence diagram function "Manage News" | Detailed Design | 20/1/2017 | 4 | 4 | 20/1/2017 | TaiNguyen | Complete
16 | 53 | Review sequence diagram function "Manage News" | Detailed Design | 20/1/2017 | 3 | 4 | 20/1/2017 | HaiTran | Complete
16 | 54 | Review sequence diagram function "Manage Categories" | Detailed Design | 20/1/2017 | 2 | 3 | 20/1/2017 | MinhDoan | Complete
16 | 55 | Review sequence diagram function "Manage Categories" | Detailed Design | 20/1/2017 | 2 | 2 | 20/1/2017 | KhoiNguyen | Complete
16 | 56 | Review sequence diagram function "Manage Banners" | Detailed Design | 20/1/2017 | 2 | 2 | 20/1/2017 | TaiNguyen | Complete
16 | 57 | Review sequence diagram function "Manage Popups" | Detailed Design | 20/1/2017 | 2 | 2 | 20/1/2017 | HienNguyen | Complete
16 | 58 | Review sequence diagram function "Manage Homepage" | Detailed Design | 20/1/2017 | 3 | 2 | 20/1/2017 | MinhDoan | Complete
16 | 59 | Review sequence diagram function "Manage Examination" | Detailed Design | 20/1/2017 | 3 | 3 | 20/1/2017 | XuanThaiHien | Complete
16 | 60 | Review sequence diagram function "Manage Language" | Detailed Design | 20/1/2017 | 2 | 1 | 20/1/2017 | KhoiNguyen | Complete
16 | 61 | Review sequence diagram function "Manage FAQ" | Detailed Design | 20/1/2017 | 2 | 2 | 20/1/2017 | XuanThaiHien | Complete
16 | 62 | Review class diagram function "Manage Account" | Detailed Design | 21/1/2017 | 5 | 5 | 21/1/2017 | TaiNguyen | Complete
16 | 63 | Update sequence diagram function "Manage Account" | Detailed Design | 21/1/2017 | 4 | 6 | 21/1/2017 | HienNguyen | Complete
16 | 64 | Update sequence diagram function "Manage News" | Detailed Design | 21/1/2017 | 5 | 7 | 21/1/2017 | HaiTran | Complete
16 | 65 | Update sequence diagram function "Manage Categories" | Detailed Design | 21/1/2017 | 4 | 4 | 21/1/2017 | KhoiNguyen | Complete
16 | 66 | Collect diagram into document | Detailed Design | 21/1/2017 | 2 | 2 | 21/1/2017 | MinhDoan | Complete
17 | 1 | Team Meeting | Implement | 23/1/2017 | 2 | 2 | 23/1/2017 | HaiTran | Complete
17 | 2 | Team Meeting | Implement | 23/1/2017 | 2 | 2 | 23/1/2017 | TaiNguyen | Complete
17 | 3 | Team Meeting | Implement | 23/1/2017 | 2 | 2 | 23/1/2017 | HienNguyen | Complete
17 | 4 | Team Meeting | Implement | 23/1/2017 | 2 | 2 | 23/1/2017 | MinhDoan | Complete
17 | 5 | Team Meeting | Implement | 23/1/2017 | 2 | 2 | 23/1/2017 | KhoiNguyen | Complete
17 | 6 | Mentor Meeting | Implement | 23/1/2017 | 3 | 4 | 23/1/2017 | HaiTran | Complete
17 | 7 | Mentor Meeting | Implement | 23/1/2017 | 3 | 4 | 23/1/2017 | TaiNguyen | Complete
17 | 8 | Mentor Meeting | Implement | 23/1/2017 | 3 | 4 | 23/1/2017 | HienNguyen | Complete
17 | 9 | Mentor Meeting | Implement | 23/1/2017 | 3 | 4 | 23/1/2017 | MinhDoan | Complete
17 | 10 | Mentor Meeting | Implement | 23/1/2017 | 3 | 4 | 23/1/2017 | KhoiNguyen | Complete
17 | 11 | Training Technical | Implement | 24/1/2017 | 2 | 2 | 24/1/2017 | HaiTran | Complete
17 | 12 | Training Technical | Implement | 24/1/2017 | 2 | 2 | 24/1/2017 | TaiNguyen | Complete
17 | 13 | Training Technical | Implement | 24/1/2017 | 2 | 2 | 24/1/2017 | HienNguyen | Complete
17 | 14 | Training Technical | Implement | 24/1/2017 | 2 | 2 | 24/1/2017 | MinhDoan | Complete
17 | 15 | Training Technical | Implement | 24/1/2017 | 2 | 2 | 24/1/2017 | KhoiNguyen | Complete
17 | 16 | Create "Account" table | Implement | 24/1/2017 | 4 | 3 | 24/1/2017 | TaiNguyen | Complete
17 | 17 | Create "News" table | Implement | 24/1/2017 | 3 | 3 | 24/1/2017 | HienNguyen | Complete
17 | 18 | Create "Categories" table | Implement | 24/1/2017 | 3 | 3 | 24/1/2017 | HaiTran | Complete
17 | 19 | Create "Banners" table | Implement | 24/1/2017 | 4 | 2 | 24/1/2017 | KhoiNguyen | Complete
17 | 20 | Create "Popups" table | Implement | 24/1/2017 | 4 | 2 | 24/1/2017 | KhoiNguyen | Complete
17 | 21 | Create "Examination" table | Implement | 24/1/2017 | 3 | 3 | 24/1/2017 | MinhDoan | Complete
17 | 22 | Create "FAQ" table | Implement | 24/1/2017 | 3 | 3 | 24/1/2017 | MinhDoan | Complete
17 | 23 | Create "Homepage" table | Implement | 24/1/2017 | 3 | 3 | 24/1/2017 | HaiTran | Complete
17 | 24 | Create "Language" table | Implement | 24/1/2017 | 2 | 1 | 24/1/2017 | HienNguyen | Complete
17 | 25 | Implement Create Account Function | Implement | 24/1/2017 | 3 | 4 | 24/1/2017 | HaiTran | Complete
17 | 26 | Implement Create Account Function | Implement | 24/1/2017 | 4 | 4 | 24/1/2017 | HienNguyen | Complete
17 | 27 | Implement Create Account Function | Implement | 24/1/2017 | 5 | 4 | 24/1/2017 | KhoiNguyen | Complete
17 | 28 | Implement Create Account Function | Implement | 24/1/2017 | 4 | 3 | 24/1/2017 | TaiNguyen | Complete
17 | 29 | Implement Create Account Function | Implement | 24/1/2017 | 3 |  | 24/1/2017 | MinhDoan | Not implemented
17 | 30 | Implement Create Account Function | Implement | 24/1/2017 | 4 |  | 24/1/2017 | XuanThaiHien | Not implemented
17 | 31 | Implement server | Implement | 25/1/2017 | 20 | 22 | 27/1/2017 | HaiTran | Complete
17 | 32 | Implement server | Implement | 25/1/2017 | 24 | 16 | 27/1/2017 | KhoiNguyen | Complete
17 | 33 | Implement connection from Redis to MongoDB | Implement | 25/1/2017 | 15 | 16 | 26/1/2017 | HienNguyen | Complete
17 | 34 | Implement connection from ElasticSearch to MongoDB | Implement | 25/1/2017 | 22 | 25 | 27/1/2016 | TaiNguyen | Complete
17 | 35 | Implement connection to MongoDB | Implement | 25/1/2017 | 14 | 16 | 27/1/2016 | MinhDoan | Complete
17 | 36 | Implement Login Function | Implement | 27/1/2017 | 7 | 8 | 28/1/2017 | HaiTran | Complete
17 | 37 | Implement Login Function | Implement | 27/1/2017 | 6 | 6 | 28/1/2017 | HienNguyen | Complete
17 | 38 | Implement Login Function | Implement | 27/1/2017 | 6 | 7 | 28/1/2017 | TaiNguyen | Complete
17 | 39 | Implement Login Function | Implement | 27/1/2017 | 7 | 7 | 28/1/2017 | KhoiNguyen | Complete
17 | 40 | Implement Login Function | Implement | 27/1/2017 | 6 |  | 28/1/2017 | MinhDoan | Not implemented
17 | 41 | Implement Login Function | Implement | 27/1/2017 | 7 |  | 28/1/2017 | XuanThaiHien | Not implemented
18 | TET HOLIDAY
19 | 1 | Team Meeting | Implement | 2017-06-02 | 2 | 2 | 2017-06-02 | HaiTran | Complete
19 | 2 | Team Meeting | Implement | 2017-06-02 | 2 | 2 | 2017-06-02 | MinhDoan | Complete
19 | 3 | Team Meeting | Implement | 2017-06-02 | 2 | 2 | 2017-06-02 | KhoiNguyen | Complete
19 | 4 | Team Meeting | Implement | 2017-06-02 | 2 | 2 | 2017-06-02 | TaiNguyen | Complete
19 | 5 | Team Meeting | Implement | 2017-06-02 | 2 | 2 | 2017-06-02 | HienNguyen | Complete
19 | 6 | Mentor Meeting | Implement | 2017-06-02 | 2 | 4 | 2017-06-02 | HaiTran | Complete
19 | 7 | Mentor Meeting | Implement | 2017-06-02 | 2 | 4 | 2017-06-02 | MinhDoan | Complete
19 | 8 | Mentor Meeting | Implement | 2017-06-02 | 2 | 4 | 2017-06-02 | KhoiNguyen | Complete
19 | 9 | Mentor Meeting | Implement | 2017-06-02 | 2 | 4 | 2017-06-02 | TaiNguyen | Complete
19 | 10 | Mentor Meeting | Implement | 2017-06-02 | 2 | 4 | 2017-06-02 | HienNguyen | Complete
19 | 11 | Mentor Meeting | Implement | 2017-06-02 | 2 | 4 | 2017-06-02 | XuanThaiHien | Complete
19 | 12 | Training Technical | Implement | 2017-07-02 | 2 | 2 | 2017-07-02 | HaiTran | Complete
19 | 13 | Training Technical | Implement | 2017-07-02 | 2 | 2 | 2017-07-02 | MinhDoan | Complete
19 | 14 | Training Technical | Implement | 2017-07-02 | 2 | 2 | 2017-07-02 | KhoiNguyen | Complete
19 | 15 | Training Technical | Implement | 2017-07-02 | 2 | 2 | 2017-07-02 | TaiNguyen | Complete
19 | 16 | Training Technical | Implement | 2017-07-02 | 2 | 2 | 2017-07-02 | HienNguyen | Complete
19 | 17 | Training Technical | Implement | 2017-07-02 | 2 | 2 | 2017-07-02 | XuanThaiHien | Complete
19 | 18 | Implement "Show Detail Account" function | Implement | 2017-07-02 | 14 | 15 | 2017-08-02 | MinhDoan | Complete
19 | 19 | Implement "View List Account" function | Implement | 2017-07-02 | 10 | 12 | 2017-08-02 | KhoiNguyen | Complete
19 | 20 | Implement "Edit Account" function | Implement | 2017-07-02 | 16 | 16 | 2017-08-02 | HienNguyen | Complete
19 | 21 | Implement "Activate Account" function | Implement | 2017-07-02 | 17 | 16 | 2017-08-02 | TaiNguyen | Complete
19 | 22 | Implement"Deactivate Account" function | Implement | 2017-07-02 | 16 | 15 | 2017-08-02 | HaiTran | Complete
19 | 23 | Demo "Login" function | Implement | 2017-09-02 | 2 | 1 | 2017-09-02 | HienNguyen | Complete
19 | 24 | Demo "Login" function | Implement | 2017-09-02 | 2 | 1 | 2017-09-02 | HaiTran | Complete
19 | 25 | Demo "Login" function | Implement | 2017-09-02 | 2 | 1 | 2017-09-02 | MinhDoan | Complete
19 | 26 | Demo "Login" function | Implement | 2017-09-02 | 2 | 1 | 2017-09-02 | TaiNguyen | Complete
19 | 27 | Demo "Login" function | Implement | 2017-09-02 | 2 | 1 | 2017-09-02 | KhoiNguyen | Complete
19 | 28 | Demo "Create Account" function | Implement | 2017-09-02 | 1 | 1 | 2017-09-02 | HienNguyen | Complete
19 | 29 | Demo "Create Account" function | Implement | 2017-09-02 | 1 | 1 | 2017-09-02 | MinhDoan | Complete
19 | 30 | Demo "Create Account" function | Implement | 2017-09-02 | 1 | 1 | 2017-09-02 | KhoiNguyen | Complete
19 | 31 | Demo "Create Account" function | Implement | 2017-09-02 | 1 | 1 | 2017-09-02 | HaiTran | Complete
19 | 32 | Demo "Create Account" function | Implement | 2017-09-02 | 1 | 1 | 2017-09-02 | TaiNguyen | Complete
19 | 33 | Demo " Show Account" function | Implement | 2017-09-02 | 1 | 1 | 2017-09-02 | KhoiNguyen | Complete
19 | 34 | Demo " Show Account" function | Implement | 2017-09-02 | 1 | 1 | 2017-09-02 | HaiTran | Complete
19 | 35 | Demo " Show Account" function | Implement | 2017-09-02 | 1 | 1 | 2017-09-02 | HienNguyen | Complete
19 | 36 | Demo " Show Account" function | Implement | 2017-09-02 | 1 | 1 | 2017-09-02 | TaiNguyen | Complete
19 | 37 | Demo " Show Account" function | Implement | 2017-09-02 | 1 | 1 | 2017-09-02 | MinhDoan | Complete
19 | 38 | Demo "Edit Account" function | Implement | 2017-09-02 | 2 | 2 | 2017-09-02 | HaiTran | Complete
19 | 39 | Demo "Edit Account" function | Implement | 2017-09-02 | 2 | 2 | 2017-09-02 | HienNguyen | Complete
19 | 40 | Demo "Edit Account" function | Implement | 2017-09-02 | 2 | 2 | 2017-09-02 | TaiNguyen | Complete
19 | 41 | Demo "Edit Account" function | Implement | 2017-09-02 | 2 | 2 | 2017-09-02 | MinhDoan | Complete
19 | 42 | Demo "Edit Account" function | Implement | 2017-09-02 | 2 | 2 | 2017-09-02 | KhoiNguyen | Complete
19 | 43 | Implement "Create draft" function | Implement | 2017-10-01 | 15 | 16 | 2017-11-01 | HaiTran | Pending
19 | 44 | Implement "View News" function | Implement | 2017-10-01 | 14 | 14 | 2017-11-01 | HienNguyen | Pending
19 | 45 | Implement "Transfer News" function | Implement | 2017-10-01 | 18 | 20 | 2017-11-01 | TaiNguyen | Pending
19 | 46 | Implement"Edit News" function | Implement | 2017-10-01 | 15 | 17 | 2017-11-01 | KhoiNguyen | Pending
20 | 1 | Team Meeting | Implement | 13/2/2017 | 2 | 2 | 13/2/2017 | HienNguyen | Complete
20 | 2 | Team Meeting | Implement | 13/2/2017 | 2 | 2 | 13/2/2017 | HaiTran | Complete
20 | 3 | Team Meeting | Implement | 13/2/2017 | 2 | 2 | 13/2/2017 | MinhDoan | Complete
20 | 4 | Team Meeting | Implement | 13/2/2017 | 2 | 2 | 13/2/2017 | KhoiNguyen | Complete
20 | 5 | Team Meeting | Implement | 13/2/2017 | 2 | 2 | 13/2/2017 | TaiNguyen | Complete
20 | 6 | Implement "Create draft" function | Implement | 13/2/2017 | 12 | 14 | 14/2/2017 | HaiTran | Complete
20 | 7 | Implement "Transfer News" function | Implement | 13/2/2017 | 15 | 16 | 14/2/2017 | TaiNguyen | Complete
20 | 8 | Implement"Edit News" function | Implement | 13/2/2017 | 14 | 16 | 14/2/2017 | KhoiNguyen | Complete
20 | 9 | Demo "View News" function | Implement | 13/2/2017 | 2 | 2 | 13/2/2017 | HienNguyen | Complete
20 | 10 | Demo "View News" function | Implement | 13/2/2017 | 2 | 2 | 13/2/2017 | HaiTran | Complete
20 | 11 | Demo "View News" function | Implement | 13/2/2017 | 2 | 2 | 13/2/2017 | MinhDoan | Complete
20 | 12 | Demo "View News" function | Implement | 13/2/2017 | 2 | 2 | 13/2/2017 | KhoiNguyen | Complete
20 | 13 | Demo "View News" function | Implement | 13/2/2017 | 2 | 2 | 13/2/2017 | TaiNguyen | Complete
20 | 14 | Training Technical | Implement | 14/2/2017 | 2 | 2 | 14/2/2017 | HaiTran | Complete
20 | 15 | Training Technical | Implement | 14/2/2017 | 2 | 2 | 14/2/2017 | TaiNguyen | Complete
20 | 16 | Training Technical | Implement | 14/2/2017 | 2 | 2 | 14/2/2017 | MinhDoan | Complete
20 | 17 | Training Technical | Implement | 14/2/2017 | 2 | 2 | 14/2/2017 | KhoiNguyen | Complete
20 | 18 | Training Technical | Implement | 14/2/2017 | 2 | 2 | 14/2/2017 | HienNguyen | Complete
20 | 19 | Demo "Create Draft" function | Implement | 14/2/2017 | 1 | 2 | 14/2/2017 | HaiTran | Complete
20 | 20 | Demo "Create Draft" function | Implement | 14/2/2017 | 1 | 2 | 14/2/2017 | MinhDoan | Complete
20 | 21 | Demo "Create Draft" function | Implement | 14/2/2017 | 1 | 2 | 14/2/2017 | TaiNguyen | Complete
20 | 22 | Demo "Create Draft" function | Implement | 14/2/2017 | 1 | 2 | 14/2/2017 | KhoiNguyen | Complete
20 | 23 | Demo "Create Draft" function | Implement | 14/2/2017 | 1 | 2 | 14/2/2017 | HienNguyen | Complete
20 | 24 | Demo "Edit News" function | Implement | 14/2/2017 | 1 | 3 | 14/2/2017 | KhoiNguyen | Complete
20 | 25 | Demo "Edit News" function | Implement | 14/2/2017 | 1 | 3 | 14/2/2017 | HaiTran | Complete
20 | 26 | Demo "Edit News" function | Implement | 14/2/2017 | 1 | 3 | 14/2/2017 | HienNguyen | Complete
20 | 27 | Demo "Edit News" function | Implement | 14/2/2017 | 1 | 3 | 14/2/2017 | TaiNguyen | Complete
20 | 28 | Demo "Edit News" function | Implement | 14/2/2017 | 1 | 3 | 14/2/2017 | MinhDoan | Complete
20 | 29 | Mentor Meeting | Implement | 15/2/2017 | 2 | 4 | 15/2/2017 | HaiTran | Complete
20 | 30 | Mentor Meeting | Implement | 15/2/2017 | 2 | 4 | 15/2/2017 | HienNguyen | Complete
20 | 31 | Mentor Meeting | Implement | 15/2/2017 | 2 | 4 | 15/2/2017 | KhoiNguyen | Complete
20 | 32 | Mentor Meeting | Implement | 15/2/2017 | 2 | 4 | 15/2/2017 | MinhDoan | Complete
20 | 33 | Mentor Meeting | Implement | 15/2/2017 | 2 | 4 | 15/2/2017 | TaiNguyen | Complete
20 | 34 | Implement "Approve News" function | Implement | 16/2/2017 | 14 | 17 | 18/2/2017 | TaiNguyen | Pending
20 | 35 | Implement "Deactivate News" function | Implement | 16/2/2017 | 16 | 18 | 18/2/2017 | HienNguyen | Pending
20 | 36 | Implement "Sort News" function | Implement | 16/2/2017 | 16 | 17 | 18/2/2017 | HaiTran | Pending
20 | 37 | Implement "Search News" function | Implement | 16/2/2017 | 17 | 16 | 18/2/2017 | KhoiNguyen | Pending
21 | 1 | Team Meeting | Implement | 20/2/2017 | 2 | 2 | 20/2/2017 | HienNguyen | Complete
21 | 2 | Team Meeting | Implement | 20/2/2017 | 2 | 2 | 20/2/2017 | HaiTran | Complete
21 | 3 | Team Meeting | Implement | 20/2/2017 | 2 | 2 | 20/2/2017 | KhoiNguyen | Complete
21 | 4 | Team Meeting | Implement | 20/2/2017 | 2 | 2 | 20/2/2017 | TaiNguyen | Complete
21 | 5 | Team Meeting | Implement | 20/2/2017 | 2 | 2 | 20/2/2017 | MinhDoan | Complete
21 | 6 | Team Meeting | Implement | 20/2/2017 | 2 | 2 | 20/2/2017 | XuanThaiHien | Complete
21 | 7 | Implement "Create draft" function on server | Implement | 20/2/2017 | 8 | 6 | 22/2/2017 | HienNguyen | Complete
21 | 8 | Implement "Create draft" function on server | Implement | 20/2/2017 | 8 | 6 | 22/2/2017 | KhoiNguyen | Complete
21 | 9 | Implement "Create draft" function on frontend | Implement | 20/2/2017 | 15 | 16 | 22/2/2017 | TaiNguyen | Complete
21 | 10 | Implement "Create draft" function on frontend | Implement | 20/2/2017 | 14 | 14 | 22/2/2017 | MinhDoan | Complete
21 | 11 | Implement "View News" function on server | Implement | 20/2/2017 | 16 | 16 | 22/2/2017 | HienNguyen | Complete
21 | 12 | Implement "View News" function on server | Implement | 20/2/2017 | 14 | 16 | 22/2/2017 | HaiTran | Complete
21 | 13 | Implement "View News" function on frontend for user | Implement | 20/2/2017 | 20 | 18 | 22/2/2017 | HaiTran | Complete
21 | 14 | Implement "View News" function on frontend for admin | Implement | 20/2/2017 | 18 | 15 | 22/2/2017 | TaiNguyen | Complete
21 | 15 | Training Technical | Implement | 23/2/2017 | 2 | 2 | 23/2/2017 | HaiTran | Complete
21 | 16 | Training Technical | Implement | 23/2/2017 | 2 | 2 | 23/2/2017 | HienNguyen | Complete
21 | 17 | Training Technical | Implement | 23/2/2017 | 2 | 2 | 23/2/2017 | TaiNguyen | Complete
21 | 18 | Training Technical | Implement | 23/2/2017 | 2 | 2 | 23/2/2017 | MinhDoan | Complete
21 | 19 | Training Technical | Implement | 23/2/2017 | 2 | 2 | 23/2/2017 | KhoiNguyen | Complete
21 | 20 | Implement "Transfer News" function on server | Implement | 23/2/2017 | 6 | 7 | 24/2/2017 | HienNguyen | Complete
21 | 21 | Implement "Transfer News" function on frontend | Implement | 23/2/2017 | 8 | 7 | 24/2/2017 | TaiNguyen | Complete
21 | 22 | Implement "Transfer News" function on frontend | Implement | 23/2/2017 | 6 | 6 | 24/2/2017 | HaiTran | Complete
21 | 23 | Implement "Edit News" function on server | Implement | 23/2/2017 | 10 | 11 | 24/2/2017 | HienNguyen | Complete
21 | 24 | Implement "Edit News" function on server | Implement | 23/2/2017 | 5 | 7 | 24/2/2017 | KhoiNguyen | Complete
21 | 25 | Implement "Edit News"function on frontend | Implement | 23/2/2017 | 6 | 6 | 24/2/2017 | TaiNguyen | Complete
21 | 26 | Implement "Edit News"function on frontend | Implement | 23/2/2017 | 4 | 5 | 24/2/2017 | HaiTran | Complete
21 | 27 | Import data into database for function "Manage News" | Implement | 23/2/2017 | 3 | 4 | 24/2/2017 | MinhDoan | Complete
21 | 28 | Mentor Meeting | Implement | 24/2/2017 | 2 | 3 | 24/2/2017 | HaiTran | Complete
21 | 29 | Mentor Meeting | Implement | 24/2/2017 | 2 | 3 | 24/2/2017 | HienNguyen | Complete
21 | 30 | Mentor Meeting | Implement | 24/2/2017 | 2 | 3 | 24/2/2017 | TaiNguyen | Complete
21 | 31 | Mentor Meeting | Implement | 24/2/2017 | 2 | 3 | 24/2/2017 | MinhDoan | Complete
21 | 32 | Mentor Meeting | Implement | 24/2/2017 | 2 | 3 | 24/2/2017 | KhoiNguyen | Complete
21 | 33 | Mentor Meeting | Implement | 24/2/2017 | 2 | 3 | 24/2/2017 | XuanThaiHien | Complete
21 | 34 | Presentation EOMP2 | Implement | 25/2/2017 | 2 | 2 | 25/2/2017 | HaiTran | Complete
21 | 35 | Presentation EOMP2 | Implement | 25/2/2017 | 2 | 2 | 25/2/2017 | MinhDoan | Complete
21 | 36 | Presentation EOMP2 | Implement | 25/2/2017 | 2 | 2 | 25/2/2017 | HienNguyen | Complete
21 | 37 | Presentation EOMP2 | Implement | 25/2/2017 | 2 | 2 | 25/2/2017 | XuanThaiHien | Complete
21 | 38 | Presentation EOMP2 | Implement | 25/2/2017 | 2 | 2 | 25/2/2017 | KhoiNguyen | Complete
21 | 39 | Presentation EOMP2 | Implement | 25/2/2017 | 2 | 2 | 25/2/2017 | TaiNguyen | Complete
21 | 40 | Team Meeting | Implement | 25/2/2017 | 1 | 1 | 25/2/2017 | HaiTran | Complete
21 | 41 | Team Meeting | Implement | 25/2/2017 | 1 | 1 | 25/2/2017 | MinhDoan | Complete
21 | 42 | Team Meeting | Implement | 25/2/2017 | 1 | 1 | 25/2/2017 | HienNguyen | Complete
21 | 43 | Team Meeting | Implement | 25/2/2017 | 1 | 1 | 25/2/2017 | XuanThaiHien | Complete
21 | 44 | Team Meeting | Implement | 25/2/2017 | 1 | 1 | 25/2/2017 | KhoiNguyen | Complete
21 | 45 | Team Meeting | Implement | 25/2/2017 | 1 | 1 | 25/2/2017 | TaiNguyen | Complete
22 | 1 | Team Meeting | Implement | 27/2/2017 | 2 | 2 | 27/2/2017 | HienNguyen | Complete
22 | 2 | Team Meeting | Implement | 27/2/2017 | 2 | 2 | 27/2/2017 | HaiTran | Complete
22 | 3 | Team Meeting | Implement | 27/2/2017 | 2 | 2 | 27/2/2017 | TaiNguyen | Complete
22 | 4 | Team Meeting | Implement | 27/2/2017 | 2 | 2 | 27/2/2017 | KhoiNguyen | Complete
22 | 5 | Team Meeting | Implement | 27/2/2017 | 2 | 2 | 27/2/2017 | MinhDoan | Complete
22 | 6 | Implement "Approve News" function on server | Implement | 27/2/2017 | 13 | 15 | 28/2/2017 | HienNguyen | Complete
22 | 7 | Implement "Approve News" function on server | Implement | 27/2/2017 | 10 | 13 | 28/2/2017 | HaiTran | Complete
22 | 8 | Implement "Approve News" function on frontend | Implement | 27/2/2017 | 12 | 13 | 28/2/2017 | TaiNguyen | Complete
22 | 9 | Implement "Approve News" function on frontend | Implement | 27/2/2017 | 12 | 10 | 28/2/2017 | KhoiNguyen | Complete
22 | 10 | Implement "Deactive News" function on server | Implement | 27/2/2017 | 8 | 7 | 28/2/2017 | HienNguyen | Complete
22 | 11 | Implement "Deactive News" function on server | Implement | 27/2/2017 | 7 | 5 | 28/2/2017 | KhoiNguyen | Complete
22 | 12 | Implement "Deactive News" function on frontend | Implement | 27/2/2017 | 8 | 5 | 28/2/2017 | HaiTran | Complete
22 | 13 | Training Technical | Implement | 2017-01-03 | 2 | 2 | 2017-01-03 | HienNguyen | Complete
22 | 14 | Training Technical | Implement | 2017-01-03 | 2 | 2 | 2017-01-03 | HaiTran | Complete
22 | 15 | Training Technical | Implement | 2017-01-03 | 2 | 2 | 2017-01-03 | TaiNguyen | Complete
22 | 16 | Training Technical | Implement | 2017-01-03 | 2 | 2 | 2017-01-03 | KhoiNguyen | Complete
22 | 17 | Training Technical | Implement | 2017-01-03 | 2 | 2 | 2017-01-03 | MinhDoan | Complete
22 | 18 | Implement "Search News" function on server | Implement | 2017-01-03 | 15 | 16 | 2017-03-03 | HienNguyen | Complete
22 | 19 | Implement "Search News" function on server | Implement | 2017-01-03 | 15 | 14 | 2017-03-03 | HaiTran | Complete
22 | 20 | Implement "Search News" function on frontend | Implement | 2017-01-03 | 17 | 18 | 2017-03-03 | TaiNguyen | Complete
22 | 21 | Implement "Sort News" function on server | Implement | 2017-01-03 | 14 | 16 | 2017-03-03 | HienNguyen | Complete
22 | 22 | Implement "Sort News" function on server | Implement | 2017-01-03 | 12 | 10 | 2017-03-03 | KhoiNguyen | Complete
22 | 23 | Implement "Sort News" function on frontend | Implement | 2017-01-03 | 13 | 13 | 2017-03-03 | TaiNguyen | Complete
22 | 24 | Mentor Meeting | Implement | 2017-03-03 | 2 | 2 | 2017-03-03 | HaiTran | Complete
22 | 25 | Mentor Meeting | Implement | 2017-03-03 | 2 | 2 | 2017-03-03 | HienNguyen | Complete
22 | 26 | Mentor Meeting | Implement | 2017-03-03 | 2 | 2 | 2017-03-03 | TaiNguyen | Complete
22 | 27 | Mentor Meeting | Implement | 2017-03-03 | 2 | 2 | 2017-03-03 | MinhDoan | Complete
22 | 28 | Mentor Meeting | Implement | 2017-03-03 | 2 | 2 | 2017-03-03 | KhoiNguyen | Complete
22 | 29 | Implement "View categories" function on server | Implement | 2017-04-03 | 10 | 10 | 2017-04-03 | HienNguyen | Complete
22 | 30 | Implement "View categories" function on server | Implement | 2017-04-03 | 10 | 12 | 2017-04-03 | HaiTran | Complete
22 | 31 | Import data into database for function "Manage Categories" | Implement | 2017-04-03 | 6 | 5 | 2017-04-03 | KhoiNguyen | Complete
22 | 32 | Implement "View categories" function on frontend | Implement | 2017-04-03 | 10 | 10 | 2017-04-03 | TaiNguyen | Complete
22 | 33 | Implement "View categories" function on frontend | Implement | 2017-04-03 | 9 | 8 | 2017-04-03 | HaiTran | Complete
23 | 1 | Team Meeting | Implement | 2017-06-03 | 2 | 2 | 2017-06-03 | HienNguyen | Complete
23 | 2 | Team Meeting | Implement | 2017-06-03 | 2 | 2 | 2017-06-03 | HaiTran | Complete
23 | 3 | Team Meeting | Implement | 2017-06-03 | 2 | 2 | 2017-06-03 | TaiNguyen | Complete
23 | 4 | Team Meeting | Implement | 2017-06-03 | 2 | 2 | 2017-06-03 | KhoiNguyen | Complete
23 | 5 | Team Meeting | Implement | 2017-06-03 | 2 | 2 | 2017-06-03 | MinhDoan | Complete
23 | 6 | Implement "Add categories" function on server | Implement | 2017-06-03 | 15 | 16 | 2017-07-03 | HienNguyen | Complete
23 | 7 | Implement "Add categories" function on server | Implement | 2017-06-03 | 12 | 14 | 2017-07-03 | HaiTran | Complete
23 | 8 | Implement "Add categories" function on frontend | Implement | 2017-06-03 | 10 | 12 | 2017-07-03 | TaiNguyen | Complete
23 | 9 | Implement "Add categories" function on frontend | Implement | 2017-06-03 | 8 | 6 | 2017-07-03 | KhoiNguyen | Complete
23 | 10 | Implement frontend News on ionic 2 | Implement | 2017-06-03 | 20 |  | 2017-08-03 | MinhDoan | Not implemented
23 | 11 | Implement frontend News on ionic 2 | Implement | 2017-06-03 | 20 |  | 2017-08-03 | XuanThaiHien | Not implemented
23 | 12 | Training Technical | Implement | 2017-07-03 | 2 | 2 | 2017-07-03 | HaiTran | Complete
23 | 13 | Training Technical | Implement | 2017-07-03 | 2 | 2 | 2017-07-03 | HienNguyen | Complete
23 | 14 | Training Technical | Implement | 2017-07-03 | 2 | 2 | 2017-07-03 | TaiNguyen | Complete
23 | 15 | Training Technical | Implement | 2017-07-03 | 2 | 2 | 2017-07-03 | KhoiNguyen | Complete
23 | 16 | Training Technical | Implement | 2017-07-03 | 2 | 2 | 2017-07-03 | MinhDoan | Complete
23 | 17 | Implement "Edit categories" function on server | Implement | 2017-07-03 | 20 | 22 | 2017-09-03 | HienNguyen | Complete
23 | 18 | Implement "Edit categories" function on server | Implement | 2017-07-03 | 18 | 14 | 2017-09-03 | HaiTran | Complete
23 | 19 | Implement "Edit categories" function on frontend | Implement | 2017-07-03 | 17 | 19 | 2017-09-03 | TaiNguyen | Complete
23 | 20 | Implement "Edit categories" function on frontend | Implement | 2017-07-03 | 15 | 16 | 2017-09-03 | MinhDoan | Complete
23 | 21 | Mentor Meeting | Implement | 2017-10-03 | 2 | 3 | 2017-10-03 | HaiTran | Complete
23 | 22 | Mentor Meeting | Implement | 2017-10-03 | 2 | 3 | 2017-10-03 | HienNguyen | Complete
23 | 23 | Mentor Meeting | Implement | 2017-10-03 | 2 | 3 | 2017-10-03 | TaiNguyen | Complete
23 | 24 | Mentor Meeting | Implement | 2017-10-03 | 2 | 3 | 2017-10-03 | MinhDoan | Complete
23 | 25 | Mentor Meeting | Implement | 2017-10-03 | 2 | 3 | 2017-10-03 | KhoiNguyen | Complete
23 | 26 | Mentor Meeting | Implement | 2017-10-03 | 2 | 3 | 2017-10-03 | XuanThaiHien | Complete
23 | 27 | Implement "Delete categories" function on server | Implement | 2017-10-03 | 8 | 6 | 2017-11-03 | HienNguyen | Complete
23 | 28 | Implement "Delete categories" function on server | Implement | 2017-10-03 | 5 | 5 | 2017-11-03 | HaiTran | Complete
23 | 29 | Implement "Delete categories" function on frontend | Implement | 2017-10-03 | 6 | 6 | 2017-11-03 | TaiNguyen | Complete
23 | 30 | Implement "Create Banner" function on server | Implement | 2017-10-03 | 18 | 17 | 2017-11-03 | HienNguyen | Complete
23 | 31 | Implement "Create Banner" function on server | Implement | 2017-10-03 | 14 | 12 | 2017-11-03 | HaiTran | Complete
23 | 32 | Implement "Create Banner" function on frontend | Implement | 2017-10-03 | 18 | 18 | 2017-11-03 | TaiNguyen | Complete
23 | 33 | Implement "Create Banner" function on frontend | Implement | 2017-10-03 | 16 | 18 | 2017-11-03 | HaiTran | Complete
24 | 1 | Team Meeting | Implement | 13/3/2017 | 2 | 2 | 13/3/2017 | HienNguyen | Complete
24 | 2 | Team Meeting | Implement | 13/3/2017 | 2 | 2 | 13/3/2017 | HaiTran | Complete
24 | 3 | Team Meeting | Implement | 13/3/2017 | 2 | 2 | 13/3/2017 | TaiNguyen | Complete
24 | 4 | Team Meeting | Implement | 13/3/2017 | 2 | 2 | 13/3/2017 | MinhDoan | Complete
24 | 5 | Team Meeting | Implement | 13/3/2017 | 2 | 2 | 13/3/2017 | KhoiNguyen | Complete
24 | 6 | Implement "Arrange Banner" function on server | Implement | 13/3/2017 | 16 | 18 | 14/3/2017 | HienNguyen | Complete
24 | 7 | Implement "Arrange Banner" function on server | Implement | 13/3/2017 | 15 | 16 | 14/3/2017 | HaiTran | Complete
24 | 8 | Implement "Arrange Banner" function on frontend | Implement | 13/3/2017 | 14 | 15 | 14/3/2017 | TaiNguyen | Complete
24 | 9 | Training Technical | Implement | 14/3/2017 | 2 | 2 | 14/3/2017 | MinhDoan | Complete
24 | 10 | Training Technical | Implement | 14/3/2017 | 2 | 2 | 14/3/2017 | KhoiNguyen | Complete
24 | 11 | Training Technical | Implement | 14/3/2017 | 2 | 2 | 14/3/2017 | HienNguyen | Complete
24 | 12 | Training Technical | Implement | 14/3/2017 | 2 | 2 | 14/3/2017 | HaiTran | Complete
24 | 13 | Training Technical | Implement | 14/3/2017 | 2 | 2 | 14/3/2017 | TaiNguyen | Complete
24 | 14 | Implement "Create Popups" function on server | Implement | 14/3/2017 | 14 | 12 | 15/3/2017 | HienNguyen | Complete
24 | 15 | Implement "Create Popups" function on server | Implement | 14/3/2017 | 14 | 12 | 15/3/2017 | HaiTran | Complete
24 | 16 | Implement "Create Popups" function on frontend | Implement | 14/3/2017 | 12 | 12 | 15/3/2017 | TaiNguyen | Complete
24 | 17 | Implement "Arrange Popups" function on server | Implement | 15/3/2017 | 16 | 14 | 16/3/2017 | HienNguyen | Complete
24 | 18 | Implement "Arrange Popups" function on server | Implement | 15/3/2017 | 15 | 14 | 16/3/2017 | HaiTran | Complete
24 | 19 | Implement "Arrange Popups" function on frontend | Implement | 15/3/2017 | 12 | 15 | 16/3/2017 | TaiNguyen | Complete
24 | 20 | Create unit test for "News" function | Implement | 17/3/2017 | 9 | 7 | 17/3/2017 | KhoiNguyen | Complete
24 | 21 | Create unit test for "News" function | Implement | 17/3/2017 | 8 | 7 | 17/3/2017 | MinhDoan | Complete
24 | 22 | Research publish code to server | Implement | 17/3/2017 | 7 | 8 | 17/3/2017 | HienNguyen | Pending
24 | 23 | Research publish code to server | Implement | 17/3/2017 | 7 | 8 | 17/3/2017 | HaiTran | Pending
24 | 24 | Research publish code to server | Implement | 17/3/2017 | 7 | 8 | 17/3/2017 | TaiNguyen | Pending
24 | 25 | Mentor Meeting | Implement | 18/3/2017 | 2 | 3 | 18/3/2017 | HaiTran | Complete
24 | 26 | Mentor Meeting | Implement | 18/3/2017 | 2 | 3 | 18/3/2017 | HienNguyen | Complete
24 | 27 | Mentor Meeting | Implement | 18/3/2017 | 2 | 3 | 18/3/2017 | TaiNguyen | Complete
24 | 28 | Mentor Meeting | Implement | 18/3/2017 | 2 | 3 | 18/3/2017 | MinhDoan | Complete
24 | 29 | Mentor Meeting | Implement | 18/3/2017 | 2 | 3 | 18/3/2017 | KhoiNguyen | Complete