## Dash Board
Current Task Status / Priority | High | Medium | Low | Total | % Of Total
New | 0 | 1 | 0 | 1 | 4.167%
Planned | 2 | 3 | 1 | 6 | 25%
In Progress | 3 | 0 | 1 | 4 | 16.67%
Closed | 1 | 3 | 2 | 6 | 25%
Reject | 2 | 3 | 2 | 7 | 29.17%
Total | 8 | 10 | 6 | 24 | 100%
% of Total | 33.33% | 41.67% | 25% | 100%
Risk department summary
Planning | 1
Management | 8
Requirement | 10
Architect | 2
Desgin | 2
Code | 1
Test | 0
Total | 24

## Risk List
ID | Risk Description | Department | Actual Status | Indentified_Date | Status_date | Impact | Probability | Risk score | Priority | Action
1 | Estimates are inaccurate | Planning | In Progress | 2016-10-10 |  | 5 | 4 | 20 | High | Team meeting and re-estimate.
2 | Lack of needed knowledge | Code | In Progress | 2016-10-10 |  | 5 | 4 | 20 | High | Reserch and increase effort to study new programming language.
3 | Errors in key project management processes | Management | Closed | 2016-10-10 |  | 4 | 3 | 12 | Medium | Team meeting to review each key process and modify them.
4 | Change management overload | Management | Planned | 2016-10-10 |  | 3 | 3 | 9 | Medium | List changes, prioritize them and deal with customer
5 | Resource shortfalls | Management | Reject | 2016-10-10 |  | 3 | 2 | 6 | Medium
6 | Learning curves lead to delays and cost overrun | Management | Reject | 2016-10-10 |  | 4 | 4 | 16 | High
7 | Resources are inexperienced | Management | Closed | 2016-10-10 |  | 3 | 4 | 12 | Medium | All member research and read documents of previous course.
8 | Team members with negative attitudes towards the project | Management | Closed | 2016-10-10 |  | 2 | 4 | 8 | Medium | Team meeting to solve the problem.
9 | Resource turnover | Management | Closed | 2016-10-10 |  | 4 | 1 | 4 | Low | Increase effort for other members.
10 | Scope is ill defined | Requirement | Planned | 2016-11-07 |  | 5 | 2 | 10 | Medium | Team meeting to redefine scope and review with customer.
11 | Stakeholder conflict over proposed changes | Requirement | Planned | 2016-11-07 |  | 3 | 1 | 3 | Low | Analyse clearly and review with stakeholeder.
12 | Inaccurate function priorities | Requirement | Closed | 2016-11-07 |  | 5 | 3 | 15 | High | Review with customer to define clearly for function priorities.
13 | Change request conflicts with requirements | Requirement | New | 2016-11-07 |  | 4 | 3 | 12 | Medium
14 | Customer rejects the prototype | Requirement | Closed | 2016-11-07 |  | 4 | 1 | 4 | Low | Request some prototypes of others website to customer, re-design follow the choice of customer.
15 | Stakeholder conflict | Requirement | Reject | 2016-11-07 |  | 3 | 1 | 3 | Low
16 | Project team misunderstand requirements | Requirement | Reject | 2016-11-07 |  | 5 | 4 | 20 | High
17 | Requirements are ambiguous | Requirement | Planned | 2016-11-07 |  | 5 | 5 | 25 | High | Customer meeting to review and make clear that requirement.
18 | Requirements are incomplete | Requirement | Reject | 2016-11-07 |  | 3 | 2 | 6 | Medium
19 | Customer has inaccurate expectations | Requirement | Planned | 2016-11-07 |  | 5 | 3 | 15 | High | Propose to customer for he can understand his expectations.
20 | Delays to training impact the project | Management | In Progress | 2016-12-12 |  | 3 | 5 | 15 | High | Increase effort for all members.
21 | Architecture is infeasible | Architect | In Progress | 2016-12-12 |  | 1 | 2 | 2 | Low | Research and collect advices from professor
22 | Architecture is not fit for purpose | Architect | Reject | 2016-12-12 |  | 4 | 2 | 8 | Medium
23 | Design lacks flexibility | Design | Reject | 2017-01-02 |  | 4 | 1 | 4 | Low
24 | Design is not fit for purpose | Design | Planned | 2017-01-02 |  | 4 | 2 | 8 | Medium | Research and re-design to fit the purpose.
25
26
27
28

## Issue List
ID | Risk Description | Department | Actual Status | Open_Date | Close_Date | Priority | Comment
1 | Estimates are inaccurate | Planning | Active |  |  | Low
2 | Lack of needed knowledge | Code | Active |  |  | Low
3 | Errors in key project management processes | Management | Fixed |  |  | Low
4 | Resources are inexperienced | Management | Fixed |  |  | Low
5 | Team members with negative attitudes towards the project | Management | Fixed |  |  | Low
6 | Resource turnover | Management | Fixed |  |  | Low
7 | Inaccurate function priorities | Requirement | Fixed |  |  | Low
8 | Customer rejects the prototype | Requirement | Fixed |  |  | Low
9 | Delays to training impact the project | Management | Active |  |  | Low
10 | Architecture is infeasible | Architect | Active |  |  | Low
11
12
13
14

## Sheet1 (hidden)
Department
Planning
Requirement
Architect
Design
Code
Test
Management