## Sheet1
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time
1 | Update static view | 21/1/2017 | 21/1/2017 | 4 | 6
2 | Demo index data into mongo db | 16/1/2017 | 18/1/2017 | 4 | 3
3 | Demo connect relastic search with mongo db | 16/1/2017 | 18/1/2017 | 5 | 4